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Task

Time Estimate (Days)

Comment

Functional requirements

Specify deliverables

Design requirements 

document

Work Breakdown structure

SUB-TOTAL DAYS

1

Conceptual design

1

preliminary machine drawings

5

Material/Part procurement

1

SUB-TOTAL DAYS

7

Finalize design

4

Finalize test plan

1

Critical design review

1

Test procedure document

1

SUB-TOTAL DAYS

7

Lab Test

1

Shipboard test

1

SUB-TOTAL DAYS

2

17

TOTAL DAY ESTIMATE

1

Preliminary Design

System Engineering

Detailed Design

Testing & Integration to Service
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		Description		Task		Time Estimate (Days)		Comment

		System Engineering

				Functional requirements		1

				Specify deliverables

				Design requirements document

				Work Breakdown structure

		SUB-TOTAL DAYS				1

		Preliminary Design

				Conceptual design		1

				preliminary machine drawings		5

				Material/Part procurement		1

		SUB-TOTAL DAYS				7

		Detailed Design

				Finalize design		4

				Finalize test plan		1

				Critical design review		1

				Test procedure document		1

		SUB-TOTAL DAYS				7

		Testing & Integration to Service

				Lab Test		1

				Shipboard test		1

		SUB-TOTAL DAYS				2

		TOTAL DAY ESTIMATE				17






