Mapping AUV Project Meeting

25 May 2004

Attending:

Nobody – the team is unable to meet this week due to copious Engineering meetings this week

Virtual Participants:

Dave Caress, Rob McEwen, Mark Sibenac, Bill Kirkwood, Rich Henthorn, Hans Thomas

1. Farley Shane is off the project (the ME work is pretty much done).

a. Thanks Farley!!

2. Battery status

a. Dave, Bill, Hans, and Mark met with the MT yesterday regarding AUV batteries.

b. A proposal for an interim battery solution involving Eagle Picher Li-Ion cells packaged in glass balls was presented.

i. Budget to build two balls, one for each vehicle, is estimated at $101K with $115K

c. MT approved this approach. $50K to come from DMO AUV budget (redirected from building spare tail) and $50K to come from discretionary funds. Funding is tight, so if we can’t fit it into $100K we may defer the second battery into a 2005 project.

d. Hans is working with Eagle Picher on the design, and expects a firm quote by then end of the week.

3. Reson status

a. Mark returned the Reson 7100 receive head to Reson San Luis Obispo last Friday.

b. No word yet on whether Reson thinks they can loan us a 7k flat receive array in late July.

4. Edgetech status

a. Will see how the sonars behave in the tank with new firmware, corrected wiring, and proper grounding. 

b. In the tank by Thursday

5. LARS issues

a. Hans met with the Zephyr crew this afternoon regarding possible modifications to LARS to make deployment/recovery of Mapping AUV easier and safer.

b. Will try running vehicle in reverse during launch to see if that keeps the vehicle straight.

6. At-sea testing next Thursday June 3

a. In the tank by Thursday

i. Primary testing focused on Edgetech  sonars and the 6046 PLC driver

b. Assemble Tuesday

c. Mob Wednesday

d. At sea Thursday

i. Primary goals:

1. Run Edgetech  sonars 

2. Test the 6046 PLC driver

3. Run “lawn mowing” survey pattern.

7. Overall at-sea testing Schedule:

5 Lobos days, 19 Zephyr days:

1. Zephyr April 28, 29: 



AUV tests 
2. Zephyr May 6, 11: 



AUV tests 

3. Zephyr June 3: 




AUV tests with Edgetech  sonars

4. Zephyr June 22, 23, 24, 25: 


Docking AUV tests – might use








 mapping vehicle
5. Zephyr June 28, 29, 30, July 1: 

AUV tests with Edgetech  sonars

6. Zephyr July 19, 20, 21, 22

7. Lobos November 12, 15, 16, 17, 18

8. Zephyr - October 12, 13, 14, 15

9. Zephyr - November 22, 23

Note: the above includes days allocated to Charlie Paull for surveys.

