Mapping AUV Project Meeting

26 October 2004

Attending:

Dave Caress, Hans Thomas, Rob McEwen, Rich Henthorn, Bill Kirkwood, Paul McGill

1. Reson:

a. Last Friday the word was that they would have the multibeam in the test tank at the Goleta facility this Thursday – no response yet today if that schedule is holding.

b. We want to have a presence at the Reson tank tests – we’ll probably send Hans and/or Dave – Dave can’t go if it really happens this week.

2. Vehicle

a. Order deep-rated GPS antenna.

b. Battery #84 is starting to have diminished capacity – may not last more than another couple months.

i. Need to bug Bluefin again

c. Forward junction box – waiting for determination of why the old junction box failed.

d. Rob will be working on the ship-based drop weight server called for in last weeks meeting notes.

e. Rich will check Reson driver against the new data format and sonar command specification.

3. Eagle Picher glass sphere battery package

a. Seems on track for mid-December delivery. 

b. Telecon last Friday.

i. Finishing detailed mechanical drawings this week

ii. Started building prototype cell platters.

c. Finalize layouts this week.

d. Get sphere orders out this week too.

e. Made PCO request for Farley to design bracketry for putting the new battery package into the vehicle noses. Denied, but Farley will try to work it in if possible.

4. Progress towards Ventana-based testing of multibeam

a. Power electronics can – electronics wired and now working, but still needs testing under load – McGill is on vacation so Hans is working on it.

b. Data processing software – have been testing against simulated data – some problems identified – Reson working on it.

c. Will install spare GPS antenna on top of Ventana – need cable made – Hans.

5. We are still planning on using the November 22-23 Zephyr days

a. Will require turning vehicle around from the Ventana tests on Friday Nov 19 and Saturday Nov 20.

5 Lobos days, 19 Zephyr days:

1. Zephyr April 28, 29: 



AUV tests 
2. Zephyr May 6, 11: 



AUV tests 

3. Zephyr June 3: 




AUV tests with Edgetech  sonars

4. Zephyr June 22, 23, 24: 


AUV tests with Edgetech  sonars

5. Zephyr July 19, 20, 21, 22, 23
6. Zephyr - October 12, 13, 14, 18

AUV tests (acoustic modem, 










obstacle avoidance, etc)

7. Lobos November 12, 15, 16, 17, 18

ROV Ventana multibeam testing

8. Zephyr - November 22, 23






Note: the above includes days allocated to Charlie Paull for surveys.

