Internal Project Status 3-10-2020

Mapper 1 Upgrades/Status

- Reson T50 Sonar

  - T50 Receive head in house

  - waiting on T50 SSP bottle return (ETA next week).

- Edgetech

  - sonar bottle due April 1

  - Need to send receive staves to edgetech for trials ASAP

  - Will change out to spare sidescan staves when we change out bottle

    - order cables for sidescan arrays

    - fabricate spacers for spare sidescan staves

- Sea trial of new sonar package April 21 (if components arrive in time, we’ll try to use on Octopus Garden survey) or May 8

- Sonar Wet Cabling

  - Battery to Reson cable shipping from Ocean Innovations (ETA this week)

  - Penetrator for Reson cable in-house

  - Whips and penetrator for edgetech cabling in-house

- Software

  - Control software for reson and edgetech done

- Kearfott Isolation

  - Still pending

- Backup iridium/strobe beacon

  - New mount design needed

  - Wet cabling and dry side wiring identical to CTD tail

Mapper 2 Upgrade/Status

- Reson T50 Sonar

  - Normalized backscatter functionality needs to be verified by vendor

  - 1PPS dropouts - Still chasing this issue

- Kearfott Isolation

  - Bench testing

- Sonar Wet Cabling

  - Battery to Reson cable shipping from Ocean Innovations (ETA this week)

- Backup iridium/strobe beacon

  - New mount design needed

  - Wet cabling and dry side wiring identical to CTD tail

Mapper Spares

- T50 Purchase

  - Based on evaluation of EM2040A during WHOI cruise, Dave and I think the T50 is a better option at this point

  - Awaiting quote from Teledyne – verbal commitment to deliver before pacific northwest cruise, might be able to deliver before April cruise

- New endcap submitted to shop

  - Working with RDI to get solid models of endcap, otherwise we have to redraw in solidworks

- Wet cabling

  - Sonar Section Cables

    - Reson RX and TX cables – in house

    - Edgetech SBP Transmit – need to order qty 1

    - Edgetech Sidescan – whips in-house, need to order 24in spares

    - Extension cable – need to fab (connectors and cable in-house)

    - Battery to reson cable – spare ordered, still being fab’d

    - Battery to Edgetech cable – need to order or fab (whips in house)

  - Battery Section Cables

    - LPIL13M to MINK10/L battery wet cables – terminated, need to mold

    - MCIL8M to SVP – need to fab (whips in house)

  - CTD cable – need to fab

  - MVC cables

    - MVC to kearfott – in house

    - MVC to parosci – in house

    - MVC to avtrak – in house

    - MVC to shore – in house

    - MVC to bus forward – in house (identical to battery section spares)

Upper Water Column/I2MAP Tail Upgrade/Status

- Repairs from flooding

  - RF wet cabling

    - GPS and Iridium replaced, need to be terminated with SMAs

    - VHF and Freewave – termination kits in-house, need to terminate for both DGO and SMA

  - Replace interface washers on penetrators

    - Several penetrators still have leather cushioning washers between the nuts and glass, we will replace these with plastic washers

- Iridium/strobe beacon

  - Mount designed, should get installed this week

  - Wet cabling ready for molding

  - Dry side wiring

    - Designed, Duane needs to rewire

  - Bench testing

    - All three units fully tested

  - Changeout internal iridium beacon

    - Bench testing of beacon is complete

    - Powering

      - Need to identify power supply chain which is independent of Apollo relay power chain so that they are fully redundant

- Software

  - Fix GPS reset bug (currently system will only reset once in a mission)

  - Adjust humidity abort

  - Add iridium telemetry for humidity, battery voltage, other functions

MVC Upgrade

- Software

  - Testing linux port under AUV simulator

  - Ready to start testing I/O modules for Kearfott, tailcone, DVL, and Parosci

    - We have transition cables so I can cable these into existing dry-side connectors

  - Laughlin is testing new vectornav compass module (same as on motherboard) in CTD vehicle