## Sheet1
Task | To Do | In Process | Complete | Notes | Upcoming Missions
Grey Van (DD: NOV 2018) |  |  |  |  | Vehicle | Project | Date(s) | Systems Ready | Check Out | Ready (Date Completed)
Description: |  |  |  |  | Dorado, CTD
Power Converter |  |  | Design Power Converter Chassis |  | i2MAP
|  |  | Order Materials for Power Converter Chassis |  | Iceberg
|  |  | Cut Materials for Power Converter Chassis |  | Mapper 1
|  |  | Weld Materials for Power Converter Chassis |  | Mapper 2
Sandblast and Paint Power Convert Chassis
|  |  | Assemble Power Converter Chassis and Move to Van |  | Meet the Team |  |  | DMO Calender
| Mount Chassis Down to Van |  |  | Waiting for Electrical | Hans T. | Supervisor |  | J | F | M
Electrical Supplies |  |  | Aquire Meltric 60Amp Connectors |  | Duane T. | Electrical |  | A | M | J
[5 empty] | Emery N. | Mechanical |  | J | A | S
[5 empty] | Erik T. | Software |  | O | N | D
|  | Aquire 100 Amp Connectors |  | Need to Find Mounting Method
|  | Determine Moutning Method for 100 Amp Connectors |  |  | Proposed To Dos |  |  | Q&As
Furniture |  |  | Hang up the Cabinets
|  |  | Mount the Tool Drawers to Floor |  | Wishlist
Mount Tool Drawrs to Floor V2
Aquire Tools V1
Organize Tools
Battery Upgrade (DD: Jan 2019)
Description:
Board Upgrade
Final Testing
Longevity Testing
General
Order PPE