Schedule Issues

Major Issues

No time from PDR to complete system design (schedule assumes that mechanical, electrical, AUV minimum speed, and overall system design are completed on same day as PDR)

No time budgeted to evaluate lighting configuration with respect to camera selection

Optical design consultant identified late in overall project flow – potential scheduling issue

Time for syntactic fabrication not called out (potential long lead item)

No milestone identified for ordering of cables & connectors (potential long lead time)

Purchase of camera, lens, recorder and sensor does not reflect realistic lead time

Minor Issues

Time called out for corrective optics fab seems way too short

Fabrication time called out for mechanical components not realistic (does this include housing)

No pressure test called out for completed housing (how much of this housing is a new build?)