## Sheet1
I2MAP Mission Checklist
Mission Details |  | Check | Notes:
| Start Date | 2020-08-11
| Scientists | Benoit-Bird, Waluk
| Vessel | Carson
| AUV Crew | Barker, Thomas
Mission Name
Mission Notes
At Station Time
Pre-Mission Checklist
| AUVOpsEng(s): | Barker, Thomas
| Batteries Charged (Y/N) | Y
| Bioacoustic Sphere Charged (Y/N) | Y
| Magnet in MVC | N/A
| Magnet in BioAcoustics Sphere | N/A
| Lens Cap on Camera | Y
| CTD tubes plugged | Y
| USBL Transponder Batteries Charged and Checked | Y
Tail Cone
| Elevator Actuator Bracket bolts Tight | Y
| Rudder Actuator Bracket bolts Tight | Y
| Elevator Actuator Cotter Pins Installed | Y
| Rudder Actuator Cotter Pins Installed | Y
| Piston Cotter Pin Installed | Y
| Duct Bolts Tight | Y
| Prop Tight | Y
| Oil Comp Charged | Y
| Dropweight Present and Burnwire intact | Y
Foam Installed
| Camera | Y
| Mid Body | Y
| Aft Block | Y
| Aft Half Round | Y
| Tail Cone Bottom | Y
| Tail Cone Top | Y
Fairing rings and bolts secure
Computer Set-Up
| On Hillary, If applicable, copy new mission |  | c:/dorado/missions/CTD_MISSIONS
On Vehicle, Make sure mission profile is for CTD cd<r> rm .profile <r> ln -s .profile_auvdev .profile
| Logout and Log In on vehicle so settings take effect | NA
Bio Acoustics Sphere Check
| Turn On Sphere | Y
| Remote Desktop in to Software to ensure communication to Transceiver (134.89.32.215) | Y
| Magnet in BioAcoustics Sphere | N
Ballasting |  |  | Notes:
| Trim Test (Date) | 2020-08-07
| Full Ballast Test ( Date, Bouyancy Weight) | 2020-08-07 | Added 1.5 lb of 28# foam in tail. Barker and Crawford.
Lead [lbs] in Vehicle Section
Nose
MID FWD
MID
MID AFT
AFT
Total
DIVE CHECK START TIME AND DATE |  |  |  | Notes:
SHOP CHECKS
Physical Checks
| Dropweight | Y
| Strobe | Y
RDF
Fairing rings and bolts secure
| Prop tight | Y
| MVC Magnet out | Y
| BioAcoustics Magnet Out | N/A
| Iridium check | Y
Comms Check
| Check Bridge for RDF (160.785 MHz) | Y
| USBL Transponder (Red Bottle) | Y
| Dropweight Server <resetdw> | Y
TailCone Check
| Ensure correct profile I2MAP = auvdev | Y
| <fanTest, r> MVC environment pressure | 51.4
| MVC environment temperature [C] | 21.8
| MVC environment humidity | 18
| <td parosci> Vehicle Pressure Sensor | Y
| <td compass> | Y |  | m3dmgx1Test –dev /dev/ser5
| <td gps> | Y
| check NTP on MVC | Y
| <td dvl> | Y
| check USBL (qtalk -m /dev/ser14 <r> CS <r> crtl-a, q to quit) | NA
| <td newTailCone> Prop check | Y
| rudder (-10 = starboard) (10 = port), elevator (-10= Up) (10 = down), prop ( 100 = ON, 0 = OFF) | Y
| Enough space on mvc for mission (?) >50% Total Freespace | Y
Batteries <telnet -e 0 134.89.34.XXX 10003> (Turning on Batteries will turn on CARL)
| Time Batteries are turned on (local) | 07:30L
| Aft Battery (IP 134.89.32.148 ) ON ( Section 4) | Y
| MIN | 0
| MAX | 33.18
| AVG | 33.15
| Temperature | 17.6
| Humidity | 6.6
| Battery Pressure [psi] | 4.5
| Mid Battery (IP 134.89.32.138) ON | Y
| MIN | 33.1
| MAX | 33.16
| AVG | 33.13
| Temperature | 17.6
| Humidity | 24.9
| Battery Pressure [psi] | 3.5
| Fwd Battery (IP 134.89.32.146) ON | Y
| MIN | 32.49
| MAX | 33.07
| AVG | 32.83
| Temperature | 17.8
| Humidity | 22.2
| Battery Pressure [psi] | 5
| Enable AUX | Y
BioAcoustics
| Magnet Out | Y
| PSI | 6
| Ping Computer (134.89.32.215) | Y
| Remote Desktop in to Software to ensure communication to Transceiver (Pass :123 ) | Y
Confirm we have NTP on bio acoustics host
| Put in BioAcoustic Magnets |  | N/A
<carlTest>
Turn on Camera
| Test program response indicates success | Y
| Request a 'Camera Check' from the test menu | Y
| Camera check reports '1' | Y
Turn on Recorder (Takes about 35 secs to boot up)
| The only way to check the recorder power is to issue a 'Recorder Check' after 40 seconds | Y
| Recorder check reports '1' | Y
| Check this box if more than one attempt was needed | Y
Turn the lights on
| Lights come on OK | Y
| Ensure that the Modtronix PWM Frequency setting is 9.766 kHz (goto http://134.89.32.55) | Y
| Ensure that the PWM Mode is is set to 8­bit | Y
Perform a light check (10)
| The light check returns a number ending in fifteen, e.g., '5015' | Y
Change the light brightness (11) ­ first '0', then '75'
| The brightness decreased then increased noticeably | Y
| A light check returns '7515' | Y
Turn the lights off (9)
| Lights turned off OK | Y
Turn on the power for the CTD
| Select the menu option for CTD power | Y
| Select the menu option for a CTD power check | Y
| The answer is '1' | Y
Sample the camera housing environmental data
| Celsius Temp is less than 40 | Y
| Humidity is low (< 40%) | 18.7
| Both water sensors show approximately zero | Y
| Water alarm is 0 | Y
Synchronize the MVC and AJA Recorder clocks (18)
| After a delay to allow the MVC time to reach the next minute, carlTest spews message of success | Y | ¦ Your menu choice > 18 ¦ Sync MVC time with Ki Pro... : CARLServer::sync_time() ¦ ¦ Your menu choice > : Modtronix::sync() - : mod-aja KiPro::time_sync() - delaying 39:643060322 seconds : KiPro::time_sync() post url - http://134.89.32.54/values?eParamID_DateSet, params = paramName=eParamID_DateSet&newValue=08/11/2020 14:47 : KiPro::time_sync() response - []paramid":"2097217802","name":"eParamID_TransportState","value":"1","value_name":"Idle"}:--:--:--","last_config_update":"0"},{"param_id":"eParamID_InputTimecode","param_type":"12","int_value":"0","str_value":"14:46:20:33","last_config_update":"0"}]t/html <!DOCTYPE HTML PUBLIC "-//IETF//DTD HTML 2.0//EN"> <html><head><title>404 Not Found</title></head><body> The document requested was not found on this server. </body></html>
Clear the AJA recorder video storage
| Point your browser to 134.89.32.54 | Y
| Select "Media" from lower left column on page | Y
| Check Media State is Record Play | Y
| Press the Format S1 (or S2) button to reset the storage cards | Y
| Switch to the second storage module by pressing the ^ button twice | Y
| Press the Format button to clear that card as wellz | Y
Ensure that the Rollover option is selected
| Go to the Media page of the Ki Pro (134.89.32.54) | Y
| Towards the top of the page, ensure that the 'Rollover' is ON | Y
Reset the clip name by selecting the appropriate carlTest menu item (26)
| Enter a base name for today's video clips (a blank entry sets the name to the current date and time) | Y
| Response from carlTest indicates success | Y | Still seeing indication of 404 error from AJA box.
Take a short test sample video
| Select 'Start Recording' from the test menu, (indication of success) | Y
| After about 5 seconds, select 'Stop Recording' (indication of success) | Y
| A new video clip appears in the 'All Clips' page on your browser | Y
| The name of the clip matches the name in the previous step | Y
View the sample video
| From the test menu, select 'Data Mode' | Y
| The 'All Clips' page should now have controls at the top that allow downloads | Y
| Select the new video clip using the checkbox to the left | Y
| Click "Download". Video files can get big fast, download a short one. | Y
| After downloading the clip, select 'Record Mode' from the test menu | Y
| View the video using VLC or equivalent | Y
| Delete Test Video | Y
Leave the Recorder on or Turn the recorder off (Check ONE)
Turning the recorder off and remembering to turn it on before launch
| OR Leaving the recorder on | Y
Test IRIS motor Function (27)
| Home the iris motor and position it to appropriate fstop (nominally 5.6). | Y
| carlTest indicates motor is moving and sets the position to 660 when complete | Y
Set the desired fstop by selecting the appropriate menu item, respond to the prompt as described below FStops are 31, 32, 33, 41, 42, 43,, 561, 562, 563, 81, 82, 83, 111, 112, 113, 161, 162, 163, and 221
| Each fstop has 3 positions. Move to the first position of fstop 5.6 by entering '561' | Y
| The test program should indicate the motor is moving and stops at position 200 | Y
| Move to the 2nd position of fstop 16 by entering 162 | Y
| The test program should indicate the motor is moving and stops at position X 595 (or the desired fstop) | Y
| Move the fstop back to 561 | Y
| Exit the carlTest program | Y
| If in Shop, Turn off Batteries |  | N/A
Note: Reference Re-Pre-Dive Section if needed
Final Checks Deployment
| Camera Cover Off | Y
| CTD Tubing out | Y
| Iridium | Y
DATE AND TIME COMPLETE |  |  |  | Notes:
TIME AND DATE OF RECOVERY |  | Oct 10, 2019 04:00AM | Notes:
| Vehicle Data Delivered to Science Party? | Y
| CARLData Downloaded (?) | N | R Sherlock was not able to download the last 4 videos. The environmental data said that the internal temp was 32.2 C. Since we're almost to the dock we'll try again tomorrow 13 Aug 2020.
| BioAcoustics Data Downloaded (?) | N
| Vehicle Batteries Charged (?) | N
| Vehicle Freshwater Rinsed (?) | Y
Repair/Improvement Notes:
Motor pressure housing oil cloudy and needs to be drained and changed. Rob and Chad received all of their data on 13 Aug 2020.