## Sheet1
PLC Labor Hours Budget
2027
Project L2 | GLC | Employee | January | February | March | April | May | June | July | August | September | October | November | December | YTD Actual Hours | Budget | Difference | Justification
300078.00 DMO AUV-Dorado_Support-LABOR ONLY | ENG-Electrical Tech
|  | Jose Rosal | [13 empty] | 80 |  | PCB layout support for existing boards
|  | Employee Not Specified | [13 empty] | 120 |  | making wet cable assemblies, internal harness fixes,
| ENG-Electrical Tech - Total | [14 empty] | 200
ENG-Machinist
|  | Employee Not Specified | [13 empty] | 160 |  | producing instrument brackets, making required spare parts, machining parts for AUV capture head
| ENG-Machinist - Total | [14 empty] | 160
ENG-Mechanical Eng-Mfg
|  | Brett Hobson | [13 empty] | 20 |  | MechEng reference (qualified person to ask complicated questions)
|  | Justin Tucker | [13 empty] | 180 |  | 140 hrs redesign of Dorado propeller housing with new gearbox and motor, 40 hrs RC capture head eng support
| ENG-Mechanical Eng-Mfg - Total | [14 empty] | 200
ENG-Mechanical Tech
|  | Employee Not Specified | [13 empty] | 120 |  | help with fabricating vehicle parts
| ENG-Mechanical Tech - Total | [14 empty] | 120
ENG-Electrical Eng
|  | George Stern | [13 empty] | 200 |  | Continuation of Dorado prop motor electronics redesign
|  | Erik Trauschke | [13 empty] | 240 |  | various support tasks of ASO group
| ENG-Electrical Eng - Total | [14 empty] | 200
ENG-Software Eng
|  | Kent Headley | [13 empty] | 100 |  | SW support for existing Dorado code
|  | Rich Henthorn | [13 empty] | 100 |  | SW support for existing Dorado code
| ENG-Software Eng - Total | [14 empty] | 200
DMO-Paragon
|  | Paragon operator | [13 empty] | 30 |  | Tow-out boat driving that can’t be done by ASO folks (vacation, etc.)
| DMO-Paragon - Total | [14 empty] | 30
300078.00 DMO AUV-Dorado_Support-LABOR ONLY - Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110
Report Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110