## Sheet1
File Location
Tailcone Actuators | Descriptive Name | Vender | Part Number |  | Status | Notes
| Actuator Motor (New Style) | Faulhaber |  | 2 | In House | Need to have shafts trimmed
| Shaft Coupler 4.995 to 5.995mm adapter | WM Berg | CTM-16 | 5 | In House | Compatable |  | https://www.wmberg.com/products/couplings/couplings/2/ctm-16?pcomSession=OK
| Shaft Coupler Set Screws | (Unknown Part) |  | 9 | In House | Compatable
| Spring Washer | Smalley | SSB-0063 | 5 | In House | Compatable |  | https://www.smalley.com/wave-spring/ssb-0063
| Spiral Retaining Ring (small) |  |  | 5 | In House | Compatable
| 625H Stainless Steel Ball Bearing | McMaster-Carr | 6153K113 | 10 | Ready to Order (10) | Compatable |  | https://www.mcmaster.com/6153K113/
| Acme Lead Screw | McMaster-Carr (needs machine mod) | P/N 98980A124 | 5 | In House | Compatable
| Mount, Actuator,Liam | Custom Fab |  | 4 | In House | Incompatable
| Mount, Actuator,Liam_v2 | Custom Fab |  | 0;3 | Redesign Required | Incompatable
| Mount, Actuator, Top, Liam* | Custom Fab |  | 2;5 | Needs to be manufactured (5) | Compatable
| Thrust Tube* |  |  | 3;5 | 9 shafts that need fabrication effort | Compatable
| 18-8 STAINLESS STEEL SOCKET HEAD SCREW 4-40 Thread Size, 2-1/2' Long | McMaster-Carr | 92196A122 | 4;12 | Ready to Order (20) | Compatable
| 3dprint-Hard Stop, Limit Switch* | Custom Fab |  | 2;5 | Needs to be manufactured (5) | Compatable
| Spacer, Limit Switch* | Custom Fab |  | 2;5 | Needs to be manufactured (5) | Compatable
| Flange Mount Double Bearing* |  |  | 1;5 | Needs to be manufactured (5) | Compatable
| Thrust Tube Mount | Custom Fab |  | 5 | In House | Compatable
| Support Tube Rev2j* |  |  | 0;5 | need fabrication effort | Compatable
| Disc, LImit Switch | Custom Fab |  | 5 | In House | Compatable
| Circuit Board, Limit Switch | Custom Fab |  | 0;5 | Needs to be manufactured (10) | Compatable
| Limit Switch Pins 0908-x |  |  | 13 | In House | Compatable
| 18-8 STAINLESS STEEL SOCKET HEAD SCREW 0-80 Thread Size, 7/16" Long | McMaster-Carr | 92196A048 | 18 | In House | Compatable
| 18-8 STAINLESS STEEL SOCKET HEAD SCREW 4-48 Thread Size, 3/8" Long | McMaster-Carr | 92196A173 |  | Need Order/fabrication effort (25)
| External Retaining Ring for 5mm OD, DIN 1.4122 Stainless Steel | McMAster-Carr | 90967A109 | ? | ? | Compatable
| Shim Spacers |  |  | ? | ? | Compatable
| Motor Mount, GP-32A Gearhead_v2** | Custom Fab |  | 0;5 | Redesign Required | Compatable
| Motor Mount, GP-32A Gearhead | Custom Fab |  | 3 |  | Incompatable
| LINEAR ACTUATOR HOUSING_V2** | Custom Fab |  | 0;3 | Redesign Required | Compatable
| LINEAR ACTUATOR ENDCAP* | Custom Fab |  | 3;7 | Needs to be manufactured (6) | Compatable (2 need vent hole tapped)
| Endcap O-ring 2-035 |  | 9452K123 | 3;8 | Needs Ordering | Compatable
| Tube Fitting (name unknown) |  |  | 3;9 |  | Compatable
| Acme Nut |  |  | 3;10 | (needs fabricating) | Compatable
| Guide Key |  |  |  | (needs fabricating) | Compatable
| 316 SS Philips Flathead 2-56 Thread Size, 1/8" Long |  | 91500A080 | 10* | Needs to be ordered | Compatable
Tail Cone Prop
| Prop motor |  |  | 3 |  | Need to be checked for circuit board compatablility
Prop motor housing
Prop Motor Bore O-ring
Prop Motor Face O-Ring
Prop motor endcap
Prop motor mounting plate
Prop moter gearbox
Propeller
| Shaft Key* |  |  | 3;5
Motor mount Bolts
Shaft Seal Old
Shaft Seal New
Old Seal Housing
New Seal Housing
| WHM-81-S16 (Spiral Retaining Ring) |  |  | 5
Seal Spacer
Tailcone Misc
Cotter Pin
Short Pins
Long Pins
Junction Box
J-box O-ring
J Box HW
J box top
Tygone Tubing
Tailcone PCB
Tailcone Mount
Duct