## Sheet1
PLC Labor Hours Budget
2021
Project L2 | GLC | Employee | January | February | March | April | May | June | July | August | September | October | November | December | YTD Actual Hours | Budget | Difference | Justification
300083.00 DMO LRAUV_Support-LABOR ONLY | ENG-Electrical Tech
|  | Employee Not Specified | [13 empty] | 160 |  | making wet cable assemblies, internal harness fixes, VB system support
| ENG-Electrical Tech - Total | [14 empty] | 160
ENG-Machinist
|  | Employee Not Specified | [13 empty] | 160 |  | producing instrument brackets, making required spare parts
| ENG-Machinist - Total | [14 empty] | 160
ENG-Mechanical Eng-Mfg
Employee Not Specified
|  | Brett Hobson | [13 empty] | 200 |  | general support of project as previous project leader
|  | Jon Erickson | [13 empty] | 50 |  | reference for mechanical vehicle systems if things need to get fixed
| ENG-Mechanical Eng-Mfg - Total | [14 empty] | 250
ENG-Mechanical Tech
|  | Employee Not Specified | [13 empty] | 40 |  | fixing LARS, work on LRAUV carts
|  | Aaron Schnittger | [13 empty] | 100 |  | building and fixing fairing parts, antenna masts, etc.
| ENG-Mechanical Tech - Total | [14 empty] | 140
ENG-Electrical Eng
Employee Not Specified
|  | Denis Klimov | [13 empty] | 40 |  | PAR sensor calibration and trouble shoot
|  | Ed Mellinger | [13 empty] | 40 |  | LCB troubleshooting support
| ENG-Electrical Eng - Total | [14 empty] | 80
ENG-Software Eng
Employee Not Specified
|  | Brian Kieft | [13 empty] | 195 |  | 120hrs of general sw support, 75hrs of super-user mission support
|  | Ben Ranaan | [13 empty] | 75 |  | Super-user mission support
|  | Carlos Rueda | [13 empty] | 80 |  | Dash support
|  | Thom Maughan | [13 empty] | 120 |  | continuation of higher bandwidth UART project
| ENG-Software Eng - Total | [14 empty] | 470
DMO-Paragon
|  | Paragon operator | [13 empty] | 30 |  | 10 days of LRAUV testing, 3 hours per deployment
| DMO-Paragon - Total | [14 empty] | 30
300083.00 DMO LRAUV_Support-LABOR ONLY - Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260
Report Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260