Date
Milestone

7/9
External Parosci Mounted in tail

7/9
DCON cabling changes complete

7/11
JBOX and Tether fixes complete in ALTEX tailcone (fix connectors, cable external parosci)

7/11
Benchtop Test of HS2

7/19
CTD Nose section changes complete

7/19
Benchtop Test of LISST w/ Pump

7/24 
BP & LISST/Pump mounted in mod-body

7/26
Current Profile driver for ADCP/DVL completed

7/26
Single point lift HW integrated onto vehicle

7/26
Deck test of integrated science payload

7/31
10 Hour run performed in pool on batteries

8/2
3 AgZn battery packs charged

8/2
Final Ballasting for Sea Trials

8/2
Vehicle assembled/ready for Sea Trials

8/2
Hardware Freeze Date

8/2
Complete Mob of  Zephyr for Sea Trials

8/5
Begin Sea Trials

8/9
End Sea Trials/10 Hr run at sea accomplished/Demob Zephyr

8/13
Single Point Lift test in harbor

8/13
Tracking Pole complete (test fit?)

8/19
Complete Mob of Pt Sur

8/20
Depart Moss Landing/First PM science run

8/21
First AM Science Run

8/26
Last AM & PM Science Run

8/27
Return Moss Landing/Demob Pt Sur
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