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Action Items:

1. Reson to provide MBARI with an electronic version of the estimated delivery schedule. Assign Dan Suchman - Due 3/8/02 <DONE>
2. Reson to provide bi-weekly schedule status updates to MBARI (emailed to Dave Caress).  Assign Dan Suchman - Ongoing
3. Reson will provide MBARI with updated 6046 specification, including the 7K data format and the 7K command formats. Wayne will email current one this week (3/8/02) <DONE> and after meeting at MBARI on 3/8/02 will complete specification.  Assign Wayne Arcus - Due 3/22/02.  Awaiting feedback from MBARI to allow finalizing.
4. Reson will provide MBARI with SolidWorks file of ICPU chassis (with available hardware models) in the pressure housing.  Assign Roy Abbot - Due 3/13/02
5. Wayne Arcus will meet with Hans Thomas, Mark Sibenac, and Dave Caress at MBARI at 11 am on Friday, March 8, 2002. This meeting is to work out control format and data format issues relating to the integration of the 6046 package with the Dorado vehicle. Assign Hans Thomas, Mark Sibenac, Dave Caress, and Wayne Arcus <DONE>
6. MBARI will use a Reson supplied sonar simulator and the updated 6046 package (after “phase II development”) to test the integration of the sonar with the vehicle prior to the sonar delivery. This testing is tentatively scheduled for late July 2002, the exact date to be set by Wayne Arcus, Mark Sibenac and Hans Thomas. 

7. It was agreed that the 1 PPS methodology will remain as defined by RESON in the ICD. <DONE>

8. Reson to provide MBARI with quote to rent 8160 multibeam for three months (December 1, 2002 to February 28, 2003), including data logging, etc. Assign Dan Suchman - Due 3/29/02 Commitment made to supply 8160 if needed, quote to be provided if and when MBARI concludes it cannot deploy the AUV multibeam in the Gulf of California>
9. Reson to provide MBARI with Matlab scripts to calculate data volume per ping based on the current data format specification. Assign Wayne Arcus - Due 3/15/02 <DONE>
10. Reson will deliver the MBARI projector in June. If MBARI needs to switch the projector model from TC2158 to TC2168, Reson must be notified by April 10, 2002. Assign Dave Caress - Due 4/10/02
11. MBARI will wire the connectors on the pressure housing using the wire coloring convention agreed to by Roy Abbot, Paul McGill, and Mark Sibenac. This will be after pressure test of the housing.  Assign Paul McGill - Due 4/12/02
12. MBARI will deliver the pressure housing and connectors to Reson  in April, 2002. Assign Dave Caress - Due 4/26/02 <pressure housing fabrication complete and being shipped to MBARI as of 4/9/02>
13. Reson to update ICD (1 to 2 weeks) Assign Dan Suchman - Due 3/22/02 <Waiting on MBARI to complete item 19>
14. MBARI will provide Reson with our test schedule and integration efforts (jointly) leading up to the September 1 delivery. Assign Dave Caress - Due 3/29/02 <Still finalizing our orders for batteries and INS as of 4/9/02>
15. Integration testing of the multibeam system will first occur at MBARI in September 2002. This is not necessarily fully integrated into the vehicle, but cabled up with the rest of the vehicle. Assign Mark Sibenac – Due 9/15/02
16. Reson will provide components of 6046 source code related to 7k data formatting and decoding MATLAB scripts. Assign Wayne Arcus – Originally due 3/8/02 - Reson waiting on MBARI to sign non-disclosure agreement. Note - There will need to be a second update as 7k format has changed between Phase I and II
17. Reson will provide 7k simulator for 6046. Assign Wayne Arcus - date to be advised as this impacts 7k s/w and 6046 development schedules
18. Reson will provide documentation of field serviceable level and any safety concerns / liability for field servicing. Assign Dan Suchman – Due 9/1/02 (on delivery)
19. MBARI to provide CTD message format that will be transmitted to 7K. Assign Hans Thomas – Due 3/12/02.
