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Receive array shown. (actually not our array). Of course doesn’t have receive cards.

Heavy!!!

Command link test board – pressure and electrical test passed.

Board to board tests under pressure in March.

Two 256 Mbit/sec communication.

ASIC Status

Checking individual wafers – found anomalies

Some sort of process problem – bonding problem – short out

Many individual stages working ok.

One major problem - Logic problem – actual VHDL problem – must be fixed.

Building test receiver cards with non-ASIC a/d function – will allow system testing prior to availability of the ASIC chip.

PC cards progressing

Firmware integration starting in March.

Functional test sonar in June/July

Delivery in September?

Edgetek 

Redesign capacitor energy storage unit to fit.

Delivered to Thales two versions of integrated edgetek. Thales is probably going to cancel the second vehicle and return the second electronics.  

Noise problems – cables rerouted. Switching power supply used to isolate systems.

All edgetek power supplies changed

Capacitor bank changed

Remount their transmitter cards

Getting their system to work with the hardware that fits in the can.

Sooner or later you will crash the hard drive – need to change it to do a software shutdown.
Mounting of hard drives bad – easy to break boards when connecting or disconnecting drives.

Lots of ground problems – bad cables too.

All sonars see each other at transmit.

All sonars must end pings simultaneously – triggering must have delays to match ping lengths..

Thales vehicle had continous acoustic modem – don’t know what frequency.

Will get quote from Reson for edgetek integration.

Verify models of Edgetek hardware.

ICD and Test Plan documents

Test Plans for Factory Acceptance Test (FAT) and Sea Acceptance Test (SAT

· Reson to add RVTM requirements verification test matrix

· Reson to do FAT test procedures

· MBARI to draft SAT plan and submit to Reson.

· Reson to give updated specification

-  

Action items


-  Letter to Reson requesting relief from contractual obligation to conduct sea trials within 30 days of delivery

· Reson will draft RVTM

· Reson will provide specification

· MBARI will draft SAT procedures

· Arrange Reson visit to MBARI

· MBARI to accept ICD and 6046

· MBARI provide comments on operations manual

· Verify Edgetek model

· Reson to generate ECD for edgetek integration

Reson visit to MBARI first week of March – Monday, March 3,

