Mapping AUV Project Meeting

26 August 2003

Attending:

Dave Caress, Mark Sibenac, Farley Shane, Andy Hamilton, Bill Kirkwood, Rich Henthorne

1. Welcome back

2. Review status

a. Reson 

i. as of two weeks ago they are testing prototypes of the non-ASIC receiver  cards.

ii. Delivery likely late in year

iii. Delivery could be delayed by MBARI request to integrate Edgetech boards and also by priority of Reson Navy projects.

b. Andy Hamilton

i. Picking up more details on midbody design

ii. Multibeam cable lengths – housing to receive head and to projector.

iii. Don’t have much availability through end of year but working in background to get last plastic pieces drawn and made in shop.

c. Farley

i. Midbody farings have arrived.

ii. Nose faring being fabricated now by Bluefin.

iii. Drawings for nose section foam are being checked now by Andy and will be sent out to CRP this Friday.

iv. Tail section design waiting on hand-off from Hans

v. Foam for midsection should arrive within two weeks.

1. Need to fabricate stands for assembly of midbody

vi. Drawings for nose hardware almost complete. Drawings not yet in shop.

d. Rich

i. Want to start working on software now that PUP is winding down.

ii. Need to define the tasks

1. integration with Reson logger using simulators

2. bench testing with MVC and all sensors and simulators

iii. Seafloor Mapping major effort over rest of year.

e. Dave 

i. At sea on Ewing with Marcia (Bermuda) November 13 through December 18.

ii. Need to write MB-System i/o module for Reson data.

f. Sib

i. Working on interfacing some sensors directly to main vehicle bus – test works.

ii. Ready to get main MVC stack built.

g. Bill

i. AGU coming up – support Drew as lead on AUV poster.

ii. Drew/Robert have offered to help advance the Mapping vehicle build. We will meet with them to see how they can help.

iii. Wants to have us crank through the rest of the vehicle as highest priority.

3. What about spare Edgetech board sets?

a. We have delayed sending these to Reson in case we needed to use the SBP alone this year. We will now ship these boards down.

4. Action items

a. Update Mapping AUV Status spreadsheet – everybody.

b. Get nose section foam drawings to CRP. Farley + Andy.

c. Joining rings – do we have enough in house or do we need to order? How many? 

d. Need to fabricate three stands for assembly of all three vehicle sections in lab. Farley will get techs to do this.

e. Need to get nose hardware drawings into shop. Farley.

f. Need to get to work on integration of MVC with sensors and simulators

i. Move to Linux, dump Qunix. Sib leads porting. Also Rich

ii. Nav integration, Kearfott interface – Rob.

iii. Acoustic modem system, LBL, etc. Rich and Sib.

iv. Make sure data logging is compatible with SDSS - Rich

v. Full bench testing. 

g. Need to have meeting at Reson first week of October, post Oceans meeting

h. Need to ship Edgetech  boards to Reson

