Meeting at Reson San Luis Obispo

February 6, 2004

David Caress, Hans Thomas, Dan Suchman, Steve Weymann, Roy Abbott briefly

· Receive head motherboard

· Transients from power supply damaging receiver cards

· All other functions working

· Working to fix – the motherboards for our head will not be built until this is fixed.

· Beamforming

· Tested with circular and flat arrays

· Hardware on shelf

· The transmit power will be lower than expected when delivered, but the power amp will be switched out later. 

· The present electronics will burn out at full power when connected to our projector. 

· The source will be at 215 dB, down about 5 dB.

· Estimates of performance impact forthcoming

· Fixed by the end of summer.

· Receiver card problem solved – second production run underway.

· I/o board

· Hardware working

· Custom firmware – yet to be done.

· Important for synchronization – impact on testing schedule.

· MBARI would like schematic of i/o board

· Updates to 6046 software

· Formal updates handled through Mindy at Goleta office

· Problem with startup of Edgetech software – needs to be up before the 6046 PLC comes up – ask Wayne to have 6046 keep checking for Edgetech.

· MBARI supplied data sample to Reson.

· MBARI suggests change to networking to use single switch.

· MBARI will try to make it possible for Wayne to use remote desktop and PC anywhere to run the systems remotely.

· Dongle issue?

· Scheduling

· Take I/o board out of electronics for Reson to program

· Hans will supply a timing diagram to Reson by 2/13/2004

· Electronics at Reson March 1-15

· Bring receive head

· Trigger integration (i/o board) – allows synchronization of sonars

· Interim solution to have i/o output constant trigger interval

· Install SPV

· Tx PS Rev D

· Computer PS Rev E

· MBARI needs electronics March 15-26 and April 4-17 for March 23-25 and April 12-16 Zephyr days.

· Electronics can potentially be at Reson March 27-April 3.

· Electronics back to Reson on April 17

· MBARI needs multibeam by May 17 for June 3-9 Lobos days.

