<!--MSProjectTemplate_ProjectTitle-->MOOS mooring 3/27/02 meeting notes

21 weeks to deployment
1. Software weighs in Duane Edgington joins the meeting to contribute on NMC/controller design and integration topics.
2. Update from project scientist. John Ryan needs the mooring replacement cost from Mark Chaffey to include in the NOPP proposal.
3. Data requirements from test mooring Not discussed. Topic is what data products will be required from the test mooring and should the project start working with SSDS to define and chart a path for delivery. Will be continued to future meeting.
4. Project team schedules: Ed Mellinger out through April. Mark Chaffey out week of 4/1 and 4/8 returning Friday 4/12. There is no MOOS meeting scheduled for these weeks.
5. Current task status<!--MSProjectTemplate_Image-->
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ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram On hold pending Ed's return.
8.33 days
Tue 2/12/02
Fri 3/29/02
Mellinger Ed[60%]
70%

4
<DIV STYLE="margin-left:28">power system housing specification/design On hold pending Ed's return.
5 days
Fri 3/29/02
Fri 4/5/02
Mellinger Ed[60%]
0%

9
<DIV STYLE="margin-left:40">battery housing size, design and locate Design in plan check, should be completed 3/29/02. Needs connector hole specified to be complete, then ready-for-fab. 
10 days
Wed 3/6/02
Tue 3/26/02
Mellinger Ed[60%],Erickson Jon[60%]
95%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access Panels specified as BP 3160 model. Need panel mount designed to get good weight estimate so buoyancy and stability can be calculated for foam order.
5 days
Fri 2/22/02
Mon 3/11/02
Mellinger Ed[60%],Erickson Jon[60%]
60%

16
<DIV STYLE="margin-left:40">panel delivery time
15 days
Thu 3/28/02
Wed 4/17/02
 
0%

17
<DIV STYLE="margin-left:40">select solar charge controller/PPT Test units on order.
10 days
Tue 3/19/02
Tue 4/9/02
Mellinger Ed[60%]
10%

24
<DIV STYLE="margin-left:40">turbine mount and access design Test turbine in-house.
1 day
Fri 3/8/02
Fri 3/8/02
Mellinger Ed[60%],Erickson Jon[60%]
75%

27
<DIV STYLE="margin-left:40">select wind charge controller Not needed for test mooring.
8.33 days
Thu 3/28/02
Tue 4/9/02
Mellinger Ed[60%]
50%

32
<DIV STYLE="margin-left:28">temporary controller requirements specified Requirements list refined. Still need better resolution on sampling rate and other analog input details. Source of compass data needs to be determined. 
8.33 days
Mon 2/11/02
Tue 3/26/02
McBride Lance[60%]
95%

34
<DIV STYLE="margin-left:28">wave/acceleration instrument on order On hold pending software approval. Need to resolve compass source. 
35 days
Wed 3/27/02
Tue 5/14/02
 
0%

35
<DIV STYLE="margin-left:28">temporary controller specfied Plan is to use NMC/CERF cube main controller.
8.33 days
Mon 3/4/02
Tue 3/26/02
McBride Lance[60%]
95%

38
<DIV STYLE="margin-left:28">CERF adapter board debugging Greater than desired noise on5V power supply. Lance and Wayne investigating.
12 days
Thu 3/14/02
Fri 3/29/02
McBride Lance[60%],SE[60%]
75%

39
<DIV STYLE="margin-left:28">RF communications specified In progress.
8.33 days
Tue 3/26/02
Fri 4/5/02
McBride Lance[60%]
0%

41
<DIV STYLE="margin-left:28">controller housing and chassis specification/design On hold pending finalization of system diagram and connector specifications.
6 days
Tue 3/26/02
Wed 4/3/02
Chaffey Mark[10%],McBride Lance[60%]
0%

42
<DIV STYLE="margin-left:28">temporary controller on order/fab
30 days
Tue 3/26/02
Tue 5/7/02
 
0%

43
<DIV STYLE="margin-left:28">controller housing fabrication
20 days
Wed 4/3/02
Wed 5/1/02
 
0%

46
<DIV STYLE="margin-left:28">selection of riser cable vendor Final selection down to two vendors. Pending cable diameter sensitivity model. (Note: South Bay selected as vendor 3/29/02).
20 days
Mon 2/11/02
Tue 3/26/02
Chaffey Mark[60%],Mellinger Ed[10%]
95%

47
<DIV STYLE="margin-left:28">riser cable on order Order placed 4/1/02.
80 days
Wed 3/27/02
Tue 7/16/02
 
0%

53
<DIV STYLE="margin-left:28">snubber electro-optical connectors specified Specification complete and order placed 4/1/02.
5 days
Mon 2/18/02
Tue 3/26/02
Chaffey Mark[60%],Mellinger Ed[10%]
80%

55
<DIV STYLE="margin-left:28">bridle/snubber strain gage specified No progress.
8.33 days
Thu 2/28/02
Mon 4/1/02
unassigned EE[60%]
40%

57
<DIV STYLE="margin-left:28">snubber hose final design specifcation Waiting on Walter Paul at WHOI to draft specification.
8.33 days
Wed 3/27/02
Mon 4/8/02
Chaffey Mark[60%],Erickson Jon[60%]
25%

61
<DIV STYLE="margin-left:28">coilcord core cable fabrication Order placed 4/1/02.
35 days
Tue 3/26/02
Mon 5/13/02
 
0%

63
<DIV STYLE="margin-left:28">snubber electo-optical connectors delivery time
100 days
Wed 3/27/02
Tue 8/13/02
 
0%

70
<DIV STYLE="margin-left:28">tower final detailed design Pending solar panel design.
8.33 days
Tue 3/26/02
Fri 4/5/02
Erickson Jon[60%]
0%

71
<DIV STYLE="margin-left:28">bridle final design Pending final snubber specification/design.
5 days
Tue 3/26/02
Mon 4/1/02
Erickson Jon[60%]
0%

75
<DIV STYLE="margin-left:28">float design . Need solar panel mount designed to get good weight estimate so buoyancy and stability can be calculated for foam order.
5 days
Mon 3/4/02
Wed 3/27/02
Erickson Jon[60%]
80%

76
<DIV STYLE="margin-left:28">float order and lead time
40 days
Wed 3/27/02
Wed 5/22/02
 
0%

78
<DIV STYLE="margin-left:28">anchor system preliminary design No progress.
8.33 days
Tue 3/26/02
Fri 4/5/02
Erickson Jon[60%],Chaffey Mark[60%]
0%
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