<!--MSProjectTemplate_ProjectTitle-->MOOS mooring 4/17/02 meeting notes

18 weeks to deployment

Present: Duane Edgington , Jon Erickson, Lance McBride, Tim Meese, Keith Raybould, Mark Chaffey (notes).

1. Software weighs in. Tim Meese will be joining the weekly meetings to help support the MOOS mooring test deployment with the NMC/CERF hardware controller.
2. Update from project scientist. NOPP proposal has been submitted. Full proposal will be available on the web shortly.
3. Data requirements from test mooring. Data requirements are being included with the controller requirements. Mark Chaffey will contact John Graybeal and Duane E. to discuss how to handle test mooring data downloading, archiving and access.
4. Current task status<!--MSProjectTemplate_Image-->
 <!--MSProjectTemplate_TaskTable-->
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram On hold pending Ed's return.
8.33 days
Tue 2/12/02
Fri 3/29/02
Mellinger Ed[60%]
70%

4
<DIV STYLE="margin-left:28">power system housing specification/design On hold pending Ed's return.
5 days
Fri 3/29/02
Fri 4/5/02
Mellinger Ed[60%]
0%

9
<DIV STYLE="margin-left:40">battery housing size, design and locate Design complete and plan checked. CDR final step before putting in shop.
10 days
Wed 3/6/02
Tue 3/26/02
Mellinger Ed[60%],Erickson Jon[60%]
95%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access In progress.
5 days
Fri 2/22/02
Mon 3/11/02
Mellinger Ed[60%],Erickson Jon[60%]
60%

17
<DIV STYLE="margin-left:40">select solar charge controller/PPT On hold pending Ed's return.
10 days
Tue 3/19/02
Tue 4/9/02
Mellinger Ed[60%]
10%

24
<DIV STYLE="margin-left:40">turbine mount and access design Final design pending final tower design.
1 day
Fri 3/8/02
Fri 3/8/02
Mellinger Ed[60%],Erickson Jon[60%]
75%

27
<DIV STYLE="margin-left:40">select wind charge controller On hold pending Ed's return.
8.33 days
Thu 3/28/02
Tue 4/9/02
Mellinger Ed[60%]
50%

32
<DIV STYLE="margin-left:28">temporary controller requirements specified Requirements under review, will be frozen at PDR for controller. 
8.33 days
Mon 2/11/02
Tue 3/26/02
McBride Lance[60%]
95%

34
<DIV STYLE="margin-left:28">wave/acceleration instrument on order On hold pending final controller requirements (above). 
35 days
Wed 3/27/02
Tue 5/14/02
 
0%

35
<DIV STYLE="margin-left:28">temporary controller specfied Done, will be finalized at PDR.
8.33 days
Mon 3/4/02
Tue 3/26/02
McBride Lance[60%]
95%

38
<DIV STYLE="margin-left:28">CERF adapter board debugging Done.
12 days
Thu 3/14/02
Fri 3/29/02
McBride Lance[60%],SE[60%]
75%

39
<DIV STYLE="margin-left:28">RF communications specified.In progress.
8.33 days
Tue 3/26/02
Fri 4/5/02
McBride Lance[60%]
0%

41
<DIV STYLE="margin-left:28">controller housing and chassis specification/design In progress. Craig Okuda has complete design for AL controller housing and expects first unit from shop 4/24/02. MOOS mooring will examine as standard for controller and power can.
6 days
Tue 3/26/02
Wed 4/3/02
Chaffey Mark[10%],McBride Lance[60%]
0%

42
<DIV STYLE="margin-left:28">temporary controller on order/fab Pending complete systems and interface design.
30 days
Tue 3/26/02
Tue 5/7/02
 
0%

55
<DIV STYLE="margin-left:28">bridle/snubber strain gage specified TBD. Mark Chaffey contacting WHOI regarding possible candidate.
8.33 days
Thu 2/28/02
Mon 4/1/02
unassigned EE[60%]
40%

57
<DIV STYLE="margin-left:28">snubber hose final design specifcation TBD. Mark Chaffey working on this with Walter Paul (WHOI).
8.33 days
Wed 3/27/02
Mon 4/8/02
Chaffey Mark[60%],Erickson Jon[60%]
25%

63
<DIV STYLE="margin-left:28">snubber electo-optical connectors delivery time Connectors on order, specified delivery is 8/5/02. Working with Brantner to get faster delivery if possible.
100 days
Wed 3/27/02
Tue 8/13/02
 
0%

70
<DIV STYLE="margin-left:28">tower final detailed design Pending solar panel mount design. 
8.33 days
Tue 3/26/02
Fri 4/5/02
Erickson Jon[60%]
0%

71
<DIV STYLE="margin-left:28">bridle final design Pending snubber specification.
5 days
Tue 3/26/02
Mon 4/1/02
Erickson Jon[60%]
0%

75
<DIV STYLE="margin-left:28">float design Pending final weight and balance calculation that is pending panel mount design.
5 days
Mon 3/4/02
Wed 3/27/02
Erickson Jon[60%]
80%

78
<DIV STYLE="margin-left:28">anchor system preliminary design TBD.
8.33 days
Tue 3/26/02
Fri 4/5/02
Erickson Jon[60%],Chaffey Mark[60%]
0%
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