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15 weeks to deployment
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1. Project schedule.
3. Project budget.
4. Data requirements from test mooring.

5. Current task status:

ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

1
<DIV STYLE="margin-left:4">Mooring test deployment
147.67 days
Mon 2/11/02
Wed 9/4/02
 
20%

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram.
8.33 days
Tue 2/12/02
Thu 4/25/02
Mellinger Ed[60%]
70%

4
<DIV STYLE="margin-left:28">power system housing specification/design 
5 days
Thu 4/25/02
Thu 5/2/02
Mellinger Ed[60%]
0%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access 
5 days
Fri 2/22/02
Mon 3/11/02
Mellinger Ed[60%],Erickson Jon[60%]
60%

17
<DIV STYLE="margin-left:40">select solar charge controller/PPT 
10 days
Tue 3/19/02
Fri 5/3/02
Mellinger Ed[60%]
10%

32
<DIV STYLE="margin-left:28">temporary controller requirements specified Need to finalize instrument package for ambient temperature and compass data. ACTION ITEM: Duane E. will check Kent on effort required for interfacing OASIS metsys.

 Need to finalize wave recorder and photo sensor.

 Concept review tentatively scheduled for 4/29/02 to finalize requirements list.

Software needs final hardware for integration and testing June 17 to meet schedule. 
8.33 days
Mon 2/11/02
Tue 3/26/02
McBride Lance[60%]
95%

34
<DIV STYLE="margin-left:28">wave/acceleration instrument on order Not on order yet pending finalization of controller requirements. Need to finalize where compass data is coming from.
35 days
Tue 4/23/02
Mon 6/10/02
 
0%

35
<DIV STYLE="margin-left:28">temporary controller specified NMC/CERF architecture.
8.33 days
Mon 3/4/02
Tue 3/26/02
McBride Lance[60%]
95%

39
<DIV STYLE="margin-left:28">RF communications specified Options are existing packet radio, "freewave" modem and Iridum or Globalstar satcom.
8.33 days
Tue 3/26/02
Mon 4/29/02
McBride Lance[60%]
50%

41
<DIV STYLE="margin-left:28">controller housing and chassis specification/design Pending final systems wiring layout. Craig Okuda has design for AL version of OASIS controller housing. MOOS will consider as controller and power housing.
6 days
Tue 3/26/02
Thu 4/25/02
Chaffey Mark[10%],McBride Lance[60%]
50%

43
<DIV STYLE="margin-left:28">controller housing fabrication Pending final wiring/interconnect design.
20 days
Fri 4/26/02
Thu 5/23/02
 
0%

48
<DIV STYLE="margin-left:28">riser cable termination socket design
8.33 days
Fri 4/19/02
Wed 5/1/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

55
<DIV STYLE="margin-left:28">bridle/snubber strain gage specified
8.33 days
Thu 2/28/02
Mon 4/29/02
unassigned EE[60%]
40%

57
<DIV STYLE="margin-left:28">snubber hose final design specification

Need to finalize flange material, 319SST, Mild steel or galvanized mild steel.
8.33 days
Wed 3/27/02
Mon 4/29/02
Chaffey Mark[60%],Erickson Jon[60%]
50%

61
<DIV STYLE="margin-left:28">coilcord core cable fabrication In progress at Cortland Cable.
35 days
Mon 4/1/02
Fri 5/17/02
 
49%

64
<DIV STYLE="margin-left:28">bending strain relief specified
3 days
Mon 4/15/02
Wed 4/17/02
Erickson Jon[60%]
0%

70
<DIV STYLE="margin-left:28">tower final detailed design
8.33 days
Wed 4/17/02
Mon 4/29/02
Erickson Jon[60%]
0%

71
<DIV STYLE="margin-left:28">bridle final design
5 days
Tue 3/26/02
Thu 4/25/02
Erickson Jon[60%]
50%

72
<DIV STYLE="margin-left:28">tower and bridle CDR 
0 days
Mon 4/29/02
Mon 4/29/02
Erickson Jon
0%

75
<DIV STYLE="margin-left:28">float design 
5 days
Mon 3/4/02
Tue 4/23/02
Erickson Jon[60%]
90%

78
<DIV STYLE="margin-left:28">anchor system preliminary design 
8.33 days
Tue 4/23/02
Fri 5/3/02
Erickson Jon[60%],Chaffey Mark[60%]
0%
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