<!--MSProjectTemplate_ProjectTitle-->MOOS mooring system 6/12/02 meeting notes

Present: Ed M., Lance M., Tom O., Mike R., Tim M., Jon E., Keith R. (last half), Mark C. (notes).

1. Project budget update. Budget is staying in the black currently as estimated expenses are turned into PO's. Funds remain very tight for the balance of 2002 however.

2. Current task status:<!--MSProjectTemplate_Image-->
<!--MSProjectTemplate_TaskTable-->
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram In progress. Ed's time having to be split with Microbial Oceanography while he characterizes pump motor.
8.33 days
Tue 2/12/02
Thu 6/13/02
Mellinger Ed[60%]
80%

4
<DIV STYLE="margin-left:28">power system housing specification/design Current Al housing design has possible problem with O-ring seal design. Jon Erickson following, still not known if we can use the same prints
5 days
Thu 4/25/02
Mon 6/17/02
Mellinger Ed[60%]
70%

10
<DIV STYLE="margin-left:40">charge controller and monitoring Design of power monitoring circuitry in progress.
10 days
Mon 5/20/02
Fri 5/31/02
Mellinger Ed[60%]
50%

11
<DIV STYLE="margin-left:40">fabricate and wire battery housing Battery housings in manufacture.
8.33 days
Mon 6/3/02
Thu 6/13/02
Mellinger Ed[60%],Erickson Jon[60%]
0%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access Details of panel mounts still TBD. Jon investigating availability of 'Z' Al channel for mounting. Will get more attention as Jon finishes bridle design.
5 days
Fri 2/22/02
Thu 6/13/02
Mellinger Ed[60%],Erickson Jon[60%]
75%

17
<DIV STYLE="margin-left:40">select solar charge controller/PPT All charge controllers selected for evaluation are in-house.
10 days
Tue 3/19/02
Tue 6/18/02
Mellinger Ed[60%]
75%

32
<DIV STYLE="margin-left:28">temporary controller requirements specified Hardware specification complete with the exception of possible review of adding camera enable and power switching. GPS data requirements specified as the "standard output string that includes position". No special processing required. Software specification currently being reviewed. Mike Risi writing software, "micro C" OS is probably not powerful enough for reading number of channels we have at specified interval. Writing BASIC scheduler.
8.33 days
Mon 2/11/02
Tue 3/26/02
McBride Lance[60%]
95%

34
<DIV STYLE="margin-left:28">wave/acceleration instrument on order Instrument on order, will arrive late July. Rental unit available for software check-out. Will coordinate decision on procuring rental unit based on controller hardware availability.
36 days
Wed 6/5/02
Wed 7/24/02
 
17%

39
<DIV STYLE="margin-left:28">RF communications specified Complete. Globalstar modem under evaluation. Preliminary analysis of RF interference in progress. High attenuation of antenna signals through DGO penetrators is leading to using separate housings for each RF device.    
8.33 days
Tue 3/26/02
Thu 5/23/02
McBride Lance[60%]
75%

40
<DIV STYLE="margin-left:28">controller wiring design complete In progress. Overall system architecture complete as well as most of the major wiring layout. Details of wire runs between controller and power can TBD.
8.33 days
Mon 4/29/02
Mon 6/17/02
McBride Lance[60%]
60%

41
<DIV STYLE="margin-left:28">controller housing and chassis specification/design TBD. Preliminary connector layout complete.
6 days
Tue 3/26/02
Fri 6/14/02
Chaffey Mark[10%],McBride Lance[60%]
50%

42
temporary controller on order/fab. Board stuffing for Sidekick and DPA being bid currently. Could be delay before hardware arrival. Considering in-house build depending on timeline.
20 days
Tue 5/21/02
Mon 6/17/02
 
85%

48
<DIV STYLE="margin-left:28">riser cable termination socket design No progress.
8.33 days
Fri 4/19/02
Thu 6/20/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

58
<DIV STYLE="margin-left:28">snubber hose fabrication Specification from Walter Paul complete and submitted to vendor for bid. Estimated 6 weeks ARO for fabrication depending on time to procure 4" weld-neck pipe flange, class 150, 316L.
40 days
Wed 6/12/02
Tue 8/6/02
 
0%

59
<DIV STYLE="margin-left:28">bridle/snubber/anchor strain gage on order Both snubber and anchor strain gages have been ordered. Delivery scheduled for 9/23/02.
30 days
Wed 6/12/02
Tue 7/23/02
Erickson Jon[60%]
0%

60
<DIV STYLE="margin-left:28">coilcord core cable fabrication No update. Initial run of 200 feet complete and forwarded to Whitney Blake for construction of test coilcord (two week process). After testing is successful 1000 more feet will be run and at least four coil-cords constructed
35 days
Mon 4/1/02
Fri 5/24/02
 
90%

61
<DIV STYLE="margin-left:28">coilcord fabrication See above. Final build specification and PO have been sent to Whitney Blake. Still waiting for initial run of four test coils to be fabricated. MBARI will perform optical measurements and Duane T. is building cyclic test stand. This work will be highest priority so we can quickly analyze the results and release the final build.
35 days
Fri 5/24/02
Thu 7/18/02
 
25%

63
<DIV STYLE="margin-left:28">bending strain relief specified No progress. Mark C. to forward TMT modeling results of South Bay cable.
3 days
Wed 6/12/02
Fri 6/14/02
Erickson Jon[60%]
0%

70
<DIV STYLE="margin-left:28">bridle final design In progress.
5 days
Tue 3/26/02
Thu 6/13/02
Erickson Jon[60%]
75%

72
<DIV STYLE="margin-left:28">tower fabrication Received bid from PROMETCO, waiting 2nd bid from local fabricator. 
35 days
Wed 6/12/02
Tue 7/30/02
 
0%

75
<DIV STYLE="margin-left:28">float order and lead time Float on order from Gilman manufacturing. Delivery scheduled for 8/7/02.
40 days
Wed 6/12/02
Tue 8/6/02
 
0%

77
<DIV STYLE="margin-left:28">anchor system preliminary design No progress.
8.33 days
Wed 6/12/02
Mon 6/24/02
Erickson Jon[60%],Chaffey Mark[60%]
0%

<!--MSProjectTemplate_ResourceTableTitle-->
<!--MSProjectTemplate_ResourceTable-->
<!--MSProjectTemplate_AssignmentTableTitle-->
<!--MSProjectTemplate_AssignmentTable-->
