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1. Update from the project scientist

2. Project schedule update.   <!--MSProjectTemplate_TaskTable
3. Current task status.
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram In progress, CDR planned for week of July 8.
8.33 days
Tue 2/12/02
Wed 6/26/02
Mellinger Ed[60%]
80%

4
<DIV STYLE="margin-left:28">power system housing specification/design Update on Craig Okuda design? Can use the same prints?
5 days
Thu 4/25/02
Fri 6/28/02
Mellinger Ed[60%]
70%

11
<DIV STYLE="margin-left:40">fabricate and wire battery housing Battery housings in manufacture. When will they be done?
8.33 days
Mon 7/1/02
Thu 7/11/02
Mellinger Ed[60%],Erickson Jon[60%]
25%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access Details of panel mounts still TBD. Jon investigating availability of 'Z' Al channel for mounting. Any progress?
5 days
Fri 2/22/02
Wed 6/26/02
Mellinger Ed[60%],Erickson Jon[60%]
75%

21
<DIV STYLE="margin-left:40">layout and fab power system board Pending CDR, expected two weeks later.
20 days
Tue 7/2/02
Mon 7/29/02
Mellinger Ed[20%],Duane Thompson[40%]
0%

33
<DIV STYLE="margin-left:28">temporary controller requirements specified Hardware specification complete with the exception of possible review of adding camera enable and power switching.
8.33 days
Mon 2/11/02
Tue 6/25/02
McBride Lance[60%]
95%

35
<DIV STYLE="margin-left:28">wave/acceleration instrument on order Due 7/3/02.
36 days
Wed 6/5/02
Wed 7/24/02
 
42%

41
<DIV STYLE="margin-left:28">controller wiring design complete Details of wire runs between controller and power can TBD. Need to add 4 weeks to procure cable and 2 weeks to connectorize to schedule.
8.33 days
Mon 4/29/02
Tue 7/2/02
McBride Lance[60%]
70%

42
<DIV STYLE="margin-left:28">controller housing and chassis specification/design TBD. Preliminary connector layout complete
6 days
Tue 3/26/02
Thu 6/27/02
Chaffey Mark[10%],McBride Lance[60%]
55%

43
<DIV STYLE="margin-left:28">temporary controller on order/fab Additional CERF adapter boards in progress. DPA and SideKick available week of July 1. This will complete all hardware required for test deployment controller.
20 days
Tue 5/21/02
Mon 6/17/02
 
85%

44
<DIV STYLE="margin-left:28">fiber test card design In progress by Scott Jensen.
20 days
Thu 6/20/02
Wed 7/17/02
Scott Jensen[20%]
20%

46
<DIV STYLE="margin-left:28">controller housing fabrication  See power housing status.
20 days
Thu 6/27/02
Thu 7/25/02
 
0%

47
<DIV STYLE="margin-left:28">RF transceivers housing design and fab. No update.
25 days
Thu 6/27/02
Thu 8/1/02
Erickson Jon[10%],McBride Lance[10%]
0%

48
<DIV STYLE="margin-left:28">compass driver software No update.
5 days
Tue 6/25/02
Mon 7/1/02
SE[50%]
0%

49
<DIV STYLE="margin-left:28">heave sensor software driver Assigned to Rich Henthorn, meeting with instrument maker at MBARI July 3rd.
15 days
Tue 6/25/02
Mon 7/15/02
Rich Henthorn
0%

50
<DIV STYLE="margin-left:28">Globalstar modem software driver Need VPN setup before further testing. IS working on it and should be completed within one or two days. 
15 days
Tue 6/25/02
Mon 7/15/02
Tim Meese[50%]
0%

51
<DIV STYLE="margin-left:28">Z-Star sampling software driver In progress, should be completed by the end of the week.
15 days
Tue 6/25/02
Mon 7/15/02
Mike Risi
0%

56
<DIV STYLE="margin-left:28">riser cable termination socket design No progress.
8.33 days
Fri 4/19/02
Wed 7/3/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

59
<DIV STYLE="margin-left:28">specify riser cable floats No progress.
4 days
Tue 6/25/02
Fri 6/28/02
Chaffey Mark
0%

68
<DIV STYLE="margin-left:28">snubber hose fabrication Waiting for final fabrication quote.
40 days
Tue 6/25/02
Mon 8/19/02
 
0%

69
<DIV STYLE="margin-left:28">bridle/snubber/anchor strain gage on order Both snubber and anchor strain gages have been ordered. Delivery scheduled for 9/23/02.
30 days
Wed 6/12/02
Tue 7/23/02
Erickson Jon[60%]
33%

70
<DIV STYLE="margin-left:28">coilcord core cable fabrication Still waiting for initial run of four test coils to be fabricated( now scheduled for July 1). MBARI will perform optical measurements and Duane T. is building cyclic test stand. This work will be highest priority so we can quickly analyze the results and release the final build.
35 days
Mon 4/1/02
Fri 6/28/02
 
90%

71
<DIV STYLE="margin-left:28">coilcord fabrication see above.
35 days
Fri 5/24/02
Mon 8/5/02
 
25%

73
<DIV STYLE="margin-left:28">bending strain relief specified No progress.
3 days
Tue 6/25/02
Thu 6/27/02
Erickson Jon[60%]
0%

80
<DIV STYLE="margin-left:28">bridle final design Final design proceeding, expect CDR week of July 8.
5 days
Tue 3/26/02
Wed 6/26/02
Erickson Jon[60%]
75%

87
<DIV STYLE="margin-left:28">anchor system preliminary design No progress.
8.33 days
Tue 6/25/02
Fri 7/5/02
Erickson Jon[60%],Chaffey Mark[60%]
0%

94
<DIV STYLE="margin-left:28">Design and Fab. of stand-up support Existing stand design can be duplicated with minor modifications. John Ferreira working on design.
20 days
Wed 6/26/02
Tue 7/23/02
Erickson Jon
0%
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