<!--MSProjectTemplate_ProjectTitle-->MOOS mooring system 7/17/02 meeting agenda

1. Update from the project scientist

2. Project schedule update.   <!--MSProjectTemplate_TaskTable
3. Current task status.
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

3
<DIV STYLE="margin-left:28">power system prelim. design & diagram Can the CDR be scheduled for this week?
8.33 days
Tue 2/12/02
Wed 6/26/02
Mellinger Ed[60%]
80%

4
<DIV STYLE="margin-left:28">power system housing specification/design Update on Craig Okuda design? Can use the same prints?
5 days
Thu 4/25/02
Fri 6/28/02
Mellinger Ed[60%]
70%

11
<DIV STYLE="margin-left:40">fabricate and wire battery housing Battery housings in manufacture. When will they be done?
8.33 days
Mon 7/1/02
Thu 7/11/02
Mellinger Ed[60%],Erickson Jon[60%]
25%

14
<DIV STYLE="margin-left:40">design panel mounts and tower access Details of panel mount progress?
5 days
Fri 2/22/02
Wed 6/26/02
Mellinger Ed[60%],Erickson Jon[60%]
75%

21
<DIV STYLE="margin-left:40">layout and fab power system board 
20 days
Tue 7/2/02
Mon 7/29/02
Mellinger Ed[20%],Duane Thompson[40%]
0%

33
<DIV STYLE="margin-left:28">temporary controller requirements specified Hardware specification complete with the exception of possible review of adding camera enable and power switching. Mark, when is this camera going to be finalized?
8.33 days
Mon 2/11/02
Tue 6/25/02
McBride Lance[60%]
95%

41
<DIV STYLE="margin-left:28">controller wiring design complete Details of wire runs between controller and power can TBD. When can a CDR be scheduled for this so the wire and cables can be ordered? Any progress on specifying cables?
8.33 days
Mon 4/29/02
Tue 7/2/02
McBride Lance[60%]
70%

42
<DIV STYLE="margin-left:28">controller housing and chassis specification/design TBD. When can we start on the chassis design?
6 days
Tue 3/26/02
Thu 6/27/02
Chaffey Mark[10%],McBride Lance[60%]
55%

43
<DIV STYLE="margin-left:28">temporary controller on order/fab Any hardware issues remaining?.
20 days
Tue 5/21/02
Mon 6/17/02
 
85%

44
<DIV STYLE="margin-left:28">fiber test card design.
20 days
Thu 6/20/02
Wed 7/17/02
Scott Jensen[20%]
20%

46
<DIV STYLE="margin-left:28">controller housing fabrication 
20 days
Thu 6/27/02
Thu 7/25/02
 
0%

47
<DIV STYLE="margin-left:28">RF transceivers housing design and fab.
25 days
Thu 6/27/02
Thu 8/1/02
Erickson Jon[10%],McBride Lance[10%]
0%

48
<DIV STYLE="margin-left:28">compass driver software.
5 days
Tue 6/25/02
Mon 7/1/02
SE[50%]
0%

49
<DIV STYLE="margin-left:28">heave sensor software driver.
15 days
Tue 6/25/02
Mon 7/15/02
Rich Henthorn
0%

50
<DIV STYLE="margin-left:28">Globalstar modem software driver Any results from preliminary pitch/roll testing?
15 days
Tue 6/25/02
Mon 7/15/02
Tim Meese[50%]
0%

51
<DIV STYLE="margin-left:28">Z-Star sampling software driver.
15 days
Tue 6/25/02
Mon 7/15/02
Mike Risi
0%

56
<DIV STYLE="margin-left:28">riser cable termination socket design
8.33 days
Fri 4/19/02
Wed 7/3/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

59
<DIV STYLE="margin-left:28">specify riser cable floats.
4 days
Tue 6/25/02
Fri 6/28/02
Chaffey Mark
0%

68
<DIV STYLE="margin-left:28">snubber hose fabrication.
40 days
Tue 6/25/02
Mon 8/19/02
 
0%

69
<DIV STYLE="margin-left:28">bridle/snubber/anchor strain gage on order 
30 days
Wed 6/12/02
Tue 7/23/02
Erickson Jon[60%]
33%

70
<DIV STYLE="margin-left:28">coilcord core cable fabrication
35 days
Mon 4/1/02
Fri 6/28/02
 
90%

71
<DIV STYLE="margin-left:28">coilcord fabrication 
35 days
Fri 5/24/02
Mon 8/5/02
 
25%

73
<DIV STYLE="margin-left:28">bending strain relief specified When can this get moving - could have along lead time.
3 days
Tue 6/25/02
Thu 6/27/02
Erickson Jon[60%]
0%

80
<DIV STYLE="margin-left:28">bridle final design Quote from Prometco yet? Local machine shop?

Do we have an estimated date from the shop for the top and bottom plate fab.?
5 days
Tue 3/26/02
Wed 6/26/02
Erickson Jon[60%]
75%

87
<DIV STYLE="margin-left:28">anchor system preliminary design
8.33 days
Tue 6/25/02
Fri 7/5/02
Erickson Jon[60%],Chaffey Mark[60%]
0%

94
<DIV STYLE="margin-left:28">Design and Fab. of stand-up support
20 days
Wed 6/26/02
Tue 7/23/02
Erickson Jon
0%

<!--MSProjectTemplate_ResourceTableTitle-->
<!--MSProjectTemplate_ResourceTable-->
<!--MSProjectTemplate_AssignmentTableTitle-->
<!--MSProjectTemplate_AssignmentTable-->
