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1. Test deployment schedule. Schedule is very tight - especially for the power system, which is about two weeks over schedule needed to have full integration and checkout time available.

3. 2003 proposal update. Proposal work in progress. Will be submitted to Keith for incorporation in the overall MOOS 2003 proposal.

3. Current task status.

ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

8
<DIV STYLE="margin-left:40">fabricate and wire battery housing No update.
8.33 days
Mon 7/1/02
Mon 8/12/02
Mellinger Ed[60%],Erickson Jon[60%]
70%

11
<DIV STYLE="margin-left:40">design panel mounts and tower access Z-channel specification and PO only outstanding item.
5 days
Fri 2/22/02
Wed 8/7/02
Mellinger Ed[60%],Erickson Jon[60%]
80%

16
<DIV STYLE="margin-left:40">solar panel mount fabrication Pending Z channel procurement, backing material final specification,  and instruction procedure.
13 days
Thu 8/8/02
Mon 8/26/02
shop[50%]
0%

23
<DIV STYLE="margin-left:28">power system wiring detailed design No update.
16.67 days
Wed 6/26/02
Fri 8/9/02
Mellinger Ed[60%]
92%

24
<DIV STYLE="margin-left:28">power system distribution board concept design Can we still have this review this week? Need to pick up two weeks in the schedule!
1 day
Fri 8/9/02
Mon 8/12/02
 
0%

25
<DIV STYLE="margin-left:28">power system distribution board schematic Pending concept review and PDR.
16.67 days
Mon 8/12/02
Tue 9/3/02
Mellinger Ed[60%]
0%

26
<DIV STYLE="margin-left:28">power system connectors on order No update. We need these connectors to start wiring battery boxes!
14.29 days
Fri 8/9/02
Thu 8/29/02
Mellinger Ed[7%]
0%

27
<DIV STYLE="margin-left:28">power system housing specification/design Pending finalizing power system design.
5 days
Thu 4/25/02
Tue 8/13/02
Mellinger Ed[60%]
75%

42
<DIV STYLE="margin-left:28">controller housing and chassis specification/design Scott to work with Lance to make sure FOFEB board is going to fit in chassis and housing design.
6 days
Tue 3/26/02
Wed 8/7/02
Chaffey Mark[10%],McBride Lance[60%]
90%

43
<DIV STYLE="margin-left:28">temporary controller on order/fab All hardware in place. Problems with disk drive subsystem but this is not needed for tier 1 capabilities. 
20 days
Tue 5/21/02
Mon 6/17/02
 
95%

44
<DIV STYLE="margin-left:28">fiber test card design Need to establish mechanical configuration within one week so housing design can proceed. See controller housing above.
20 days
Thu 6/20/02
Tue 8/13/02
Scott Jensen[20%]
75%

45
<DIV STYLE="margin-left:28">fiber test card fabrication and test No update.
15 days
Wed 8/14/02
Tue 9/3/02
Scott Jensen[20%],Duane Thompson[40%]
0%

46
<DIV STYLE="margin-left:28">controller housing and chassis fabrication Fit and function will be coordinated by Lance and fabricated by Duane T. Need to pass on length dimensions to Jon E. as soon as known.
20 days
Wed 8/7/02
Wed 9/4/02
 
0%

47
<DIV STYLE="margin-left:28">RF transceivers housing design and fab. Cots housings on order.
15 days
Wed 8/7/02
Tue 8/27/02
Erickson Jon[10%],McBride Lance[10%]
0%

48
<DIV STYLE="margin-left:28">compass software driver No update. Waiting on NMC deployment.
10 days
Wed 8/7/02
Tue 8/20/02
Tom O'Reilly[50%]
0%

49
<DIV STYLE="margin-left:28">heave sensor software driver No update. Waiting on NMC deployment..
15 days
Fri 7/26/02
Fri 8/16/02
Rich Henthorn
50%

50
<DIV STYLE="margin-left:28">GPS software driver No update. Waiting on NMC deployment.
10 days
Wed 8/7/02
Tue 8/20/02
Kent Headley[50%]
0%

51
<DIV STYLE="margin-left:28">Globalstar modem software driver No update. Waiting on NMC deployment.
15 days
Wed 8/7/02
Tue 8/27/02
Tim Meese[50%]
0%

52
<DIV STYLE="margin-left:28">Z-Star sampling software driver No update. Waiting on NMC deployment.
15 days
Tue 6/25/02
Mon 8/12/02
Mike Risi
75%

53
<DIV STYLE="margin-left:28">SSDS instrument metadata plan No update. Waiting on NMC deployment.
3 days
Tue 8/13/02
Thu 8/15/02
John Graybeal[20%]
0%

58
<DIV STYLE="margin-left:28">riser cable termination socket design Technical method  research started.
8.33 days
Fri 4/19/02
Thu 8/15/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

61
<DIV STYLE="margin-left:28">specify riser cable floats Done, ready for PO.
4 days
Tue 6/25/02
Wed 8/7/02
Chaffey Mark
90%

70
<DIV STYLE="margin-left:28">snubber hose fabrication In progress.
40 days
Tue 6/25/02
Mon 8/19/02
 
80%

71
<DIV STYLE="margin-left:28">snubber union/instrument cage assembly design In progress
4 days
Tue 6/11/02
Thu 8/15/02
Erickson Jon[15%]
25%

73
<DIV STYLE="margin-left:28">bridle/snubber/anchor strain gage on order Done.
57 days
Wed 6/12/02
Thu 8/29/02
Erickson Jon[60%]
72%

74
<DIV STYLE="margin-left:28">coilcord core cable fabrication In progress.
35 days
Mon 4/1/02
Tue 8/13/02
 
90%

75
<DIV STYLE="margin-left:28">coilcord fabrication Test piece in progress.
35 days
Tue 8/13/02
Tue 10/1/02
 
0%

76
<DIV STYLE="margin-left:28">snubber electro-optical connectors delivery time Waiting on coilcord fabrication.
131 days
Mon 4/22/02
Tue 10/22/02
 
60%

78
<DIV STYLE="margin-left:28">bending strain relief delivery time On order, delivery time?
50 days
Tue 7/9/02
Tue 9/17/02
 
45%

86
<DIV STYLE="margin-left:28">tower fabrication In progress.
35 days
Tue 6/25/02
Mon 8/12/02
 
91%

87
<DIV STYLE="margin-left:28">bridle fabrication In progress.
35 days
Wed 6/26/02
Mon 8/19/02
 
75%

89
<DIV STYLE="margin-left:28">float order and lead time Scheduled arrival 8/19/02.
41 days
Wed 6/12/02
Fri 8/16/02
 
85%

91
<DIV STYLE="margin-left:28">anchor system preliminary design No progress.
8.33 days
Wed 8/7/02
Mon 8/19/02
Erickson Jon[60%],Chaffey Mark[60%]
0%

98
<DIV STYLE="margin-left:28">Design and model test mooring configuration Cable samples sent to Mark Grosenbaugh at WHOI. Mark will assist with final configuration modeling.
50 days
Thu 8/8/02
Wed 10/16/02
Chaffey Mark[20%]
0%

99
<DIV STYLE="margin-left:28">Design and Fab. of stand-up support Original plan had John F. duplicating existing stands. Craig Okuda has updated design concept but no information available from Craig on progress. Project will either adopt Craig design or duplicate existing stands based on design progress.
20 days
Wed 8/7/02
Tue 9/3/02
Erickson Jon
0%
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