<!--MSProjectTemplate_ProjectTitle-->MOOS mooring 8/21/02 meeting agenda

1. Update from project scientist.

2. MOOS mooring 2003 proposal.

3. Schedule update.

4. Special action items:

· Optical connector expedite - Mark C.

· IS group AR request for local VPN for Globalstar/"operational software host". - Tim M.

5. Current task status:<!--MSProjectTemplate_Image--> <!--MSProjectTemplate_TaskTableTitle--><!--MSProjectTemplate_TaskTable-->
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

8
<DIV STYLE="margin-left:40">fabricate and wire battery housing
8.33 days
Mon 7/1/02
Thu 8/22/02
Mellinger Ed[60%],Erickson Jon[60%]
70%

11
<DIV STYLE="margin-left:40">design panel mounts and tower access
5 days
Fri 2/22/02
Tue 8/20/02
Mellinger Ed[60%],Erickson Jon[60%]
85%

16
<DIV STYLE="margin-left:40">solar panel mount fabrication
13 days
Tue 8/20/02
Fri 9/6/02
shop[50%]
0%

23
<DIV STYLE="margin-left:28">power system wiring detailed design
16.67 days
Wed 6/26/02
Wed 8/21/02
Mellinger Ed[60%]
92%

24
<DIV STYLE="margin-left:28">power system distribution board concept design
1 day
Fri 8/9/02
Wed 8/21/02
 
80%

25
<DIV STYLE="margin-left:28">power system distribution board schematic
16.67 days
Wed 8/21/02
Fri 9/13/02
Mellinger Ed[60%]
0%

26
<DIV STYLE="margin-left:28">power system connectors on order
14.29 days
Wed 8/21/02
Tue 9/10/02
Mellinger Ed[7%]
0%

27
<DIV STYLE="margin-left:28">power system housing specification/design
5 days
Thu 4/25/02
Thu 8/22/02
Mellinger Ed[60%]
75%

42
<DIV STYLE="margin-left:28">controller housing and chassis specification/design
6 days
Tue 3/26/02
Tue 8/20/02
Chaffey Mark[10%],McBride Lance[60%]
90%

44
<DIV STYLE="margin-left:28">fiber test card design
20 days
Thu 6/20/02
Mon 8/26/02
Scott Jensen[20%]
75%

45
<DIV STYLE="margin-left:28">fiber test card fabrication and test
15 days
Tue 8/27/02
Mon 9/16/02
Scott Jensen[20%],Duane Thompson[40%]
0%

46
<DIV STYLE="margin-left:28">controller housing and chassis fabrication
20 days
Tue 8/20/02
Tue 9/17/02
 
15%

48
<DIV STYLE="margin-left:28">compass software driver
10 days
Tue 8/20/02
Mon 9/2/02
Tom O'Reilly[50%]
0%

49
<DIV STYLE="margin-left:28">heave sensor software driver
15 days
Fri 7/26/02
Thu 8/29/02
Rich Henthorn
50%

50
<DIV STYLE="margin-left:28">GPS software driver
10 days
Tue 8/20/02
Mon 9/2/02
Kent Headley[50%]
0%

51
<DIV STYLE="margin-left:28">globalstar modem software driver
15 days
Tue 8/20/02
Mon 9/9/02
Tim Meese[50%]
0%

52
<DIV STYLE="margin-left:28">Z-Star sampling software driver
15 days
Tue 6/25/02
Fri 8/23/02
Mike Risi
75%

53
<DIV STYLE="margin-left:28">SSDS instrument metadata plan
3 days
Tue 8/20/02
Thu 8/22/02
John Graybeal[20%]
0%

58
<DIV STYLE="margin-left:28">riser cable termination socket design
8.33 days
Fri 4/19/02
Wed 8/28/02
Chaffey Mark[60%],Erickson Jon[60%]
20%

62
<DIV STYLE="margin-left:28">riser cable floats on order
35 days
Tue 8/20/02
Mon 10/7/02
 
0%

70
<DIV STYLE="margin-left:28">snubber hose fabrication
40 days
Tue 6/25/02
Mon 8/19/02
 
80%

71
<DIV STYLE="margin-left:28">snubber union/instrument cage assembly design
4 days
Tue 6/11/02
Thu 8/22/02
Erickson Jon[15%]
25%

74
<DIV STYLE="margin-left:28">coilcord core cable fabrication
35 days
Mon 4/1/02
Fri 8/23/02
 
90%

75
<DIV STYLE="margin-left:28">coilcord fabrication
35 days
Fri 8/23/02
Fri 10/11/02
 
0%

86
<DIV STYLE="margin-left:28">tower fabrication
35 days
Tue 6/25/02
Wed 8/21/02
 
95%

87
<DIV STYLE="margin-left:28">bridle fabrication
35 days
Wed 6/26/02
Wed 8/28/02
 
80%

89
<DIV STYLE="margin-left:28">float order and lead time
41 days
Wed 6/12/02
Thu 8/22/02
 
95%

91
<DIV STYLE="margin-left:28">anchor system preliminary design
8.33 days
Tue 8/20/02
Fri 8/30/02
Erickson Jon[60%],Chaffey Mark[60%]
0%

98
<DIV STYLE="margin-left:28">Design and model test mooring configuration
50 days
Tue 8/20/02
Mon 10/28/02
Chaffey Mark[20%]
0%

99
<DIV STYLE="margin-left:28">Design and Fab. of stand-up support
20 days
Tue 8/20/02
Mon 9/16/02
Erickson Jon
0%
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