<!--MSProjectTemplate_ProjectTitle-->MOOS mooring system 10/30/02 meeting notes
Present: Ed M., Kevin Gomes (SSDS), Jon E., Duane E., Keith., Tim M., Duane T., Mike K., Mark C. (notes)
1. <!--MSProjectTemplate_Image-->Schedule update. Just under 5 weeks to deployment!
Lance out October 25-Nov. 4.

Zorba out after October 26.

Andy Hamilton out Oct. 28-Nov.7

Scott Jensen out Oct. 28-30

2. Special action items:
· Software integration and move to deployed hardware. Just in time for our "drop-dead decision" point on using radio backup Tim and Tom got the RMI benchmark running over the Globalstar modem dial-up connection. Aggregate throughput was 6200 Baud. Next milestone is running an end-to-end test coordinated with prototype archival system developed by SSDS is scheduled on Nov. 7 or 8.

3. Special action items:
· Purchase antenna to have on hand (Duane E.). Pending.
· C-channel pending for solar panels (Mike P.) Pending.
· Order SST snubber bolts (Jon E.)
· Set up pre-move to buoy and pre-deployment test plan (Mark C.)
4. <!--MSProjectTemplate_Image-->Current task status: <!--MSProjectTemplate_TaskTableTitle--><!--MSProjectTemplate_TaskTable--><!--MSProjectTemplate_TaskTable-->
ID
Task Name
Duration
Start
Finish
Resource Names
% Complete

28
<DIV STYLE="margin-left:28">power system housing fabrication Jon checking on status. Grounding contact finger still TBD part of design.
15 days
Thu 9/5/02
Tue 10/22/02
shop[75%]
98%

31
<DIV STYLE="margin-left:28">assemble solar system housing and test Still on track for mating with controller Thursday or Friday to start full-up functional testing.
4 days
Thu 10/24/02
Wed 10/30/02
Mellinger Ed[50%]
0%

48
<DIV STYLE="margin-left:28">compass software driver In test.
10 days
Tue 8/20/02
Tue 10/22/02
Tom O'Reilly[50%]
95%

49
<DIV STYLE="margin-left:28">heave sensor software driver In test.
15 days
Fri 7/26/02
Tue 10/22/02
Rich Henthorn
95%

50
<DIV STYLE="margin-left:28">GPS software driver. In test.
10 days
Tue 8/20/02
Tue 10/22/02
Kent Headley[50%]
95%

51
<DIV STYLE="margin-left:28">Globalstar modem software driver In test.
15 days
Tue 8/20/02
Wed 10/23/02
Tim Meese[50%]
90%

52
<DIV STYLE="margin-left:28">Z-Star sampling software driver In test.
15 days
Tue 6/25/02
Tue 10/22/02
Mike Risi
95%

54
<DIV STYLE="margin-left:28">temporary controller final assembly, test and software integration New power figures show system right at 20 Watt power usage maximum requirement.
16.67 days
Mon 9/9/02
Wed 10/23/02
McBride Lance[60%]
90%

55
<DIV STYLE="margin-left:28">Controller and power system lab integration and test Scheduled to start Friday, Nov. 1 - as soon as power housing is checked out.
5 days
Wed 10/30/02
Wed 11/6/02
Mellinger Ed[50%],Duane Thompson[50%],McBride Lance[50%],Kent Headley[25%]
0%

56
<DIV STYLE="margin-left:28">Move controller and power housing to mooring Still on schedule is to move all electrical hardware to buoy Nov. 7 or 8. Will depend on lab checkout progress.
1 day
Wed 11/6/02
Thu 11/7/02
Mellinger Ed[50%],McBride Lance[50%],Duane Thompson[50%]
0%

61
<DIV STYLE="margin-left:28">riser cable termination socket CDR Second CDR planned for Thursday PM for those that missed the first one.
0 days
Wed 10/23/02
Wed 10/23/02
 
0%

62
<DIV STYLE="margin-left:28">riser cable termination socket fabrication CDR fabrication split between outside shop and our staff. All available machinists pitching in. Expect enough items to be able to start testing by 11/11/02.
10 days
Wed 10/23/02
Wed 11/6/02
shop[75%]
0%

63
<DIV STYLE="margin-left:28">Test riser cable termination Pending parts fabrication.
6 days
Wed 11/6/02
Thu 11/14/02
Chaffey Mark[50%]
0%

74
<DIV STYLE="margin-left:28">snubber hose fabrication In progress at Thermoid. Material promised for arrival by 11/15/02 including shipping. 
87.5 days
Tue 6/25/02
Tue 10/29/02
 
94%

76
<DIV STYLE="margin-left:28">snubber union/instrument cage assembly fabrication In shop, scheduled for completion Nov. 15.
10.67 days
Tue 10/22/02
Tue 11/5/02
shop[75%]
0%

79
<DIV STYLE="margin-left:28">coilcord fabrication Complete, being FedExed to SeaCon.
6 days
Tue 10/22/02
Tue 10/29/02
 
50%

80
<DIV STYLE="margin-left:28">snubber electo-optical connectors delivery time SeaCon still quoting 2 weeks after receiving our material.
151.5 days
Mon 4/22/02
Tue 11/19/02
 
87%

96
<DIV STYLE="margin-left:28">anchor system PDR Held 10/23/02. Notes available on the MOOS website. Tri-moor proposed that would put less stress on cable during deployment and have better bottom holding characteristics.
0 days
Thu 10/24/02
Thu 10/24/02
Andrew Hamilton[50%],Chaffey Mark[50%]
0%

97
<DIV STYLE="margin-left:28">anchor system final design Mike Kelly reviewing deployment issues (footprint size).
3 days
Fri 10/25/02
Tue 10/29/02
Andrew Hamilton,Erickson Jon
0%

98
<DIV STYLE="margin-left:28">anchor system CDR Scheduled for week after Andy back from travel.
0 days
Tue 10/29/02
Tue 10/29/02
Andrew Hamilton,Erickson Jon
0%

99
<DIV STYLE="margin-left:28">anchor system fabricate Pending CDR. 
8 days
Wed 10/30/02
Fri 11/8/02
shop[80%]
0%

102
<DIV STYLE="margin-left:28">Design and model test mooring configuration Complete. Float position fixed. Calculations support anchor last free-fall deployment.
43 days
Tue 8/20/02
Fri 10/25/02
Andrew Hamilton[20%],Chaffey Mark[60%]
93%

104
<DIV STYLE="margin-left:28">final assembly of surface float mechanical components C-channel pending for solar panels from Mike P. Quite a few small brackets and similar items remain to be done. John F. can stick with fab. until done. Also need hand winch for instrument cage(Mike P.), notch bridle(John F.), order snubber bolts (Jon E.).
10 days
Fri 9/20/02
Wed 10/23/02
Chaffey Mark[60%],Erickson Jon[60%],Mellinger Ed[60%],observatrory support[200%],Etech[80%],Mtech[80%],shop[80%]
90%

106
<DIV STYLE="margin-left:28">Wire mooring and tower Clark B. working on finishing panel and battery wiring. Must be complete by Nov. 7.
5 days
Thu 10/17/02
Tue 10/29/02
Chaffey Mark[60%],Kelley Mike,Mellinger Ed,observatrory support,Etech[75%],Duane Thompson
20%

111
<DIV STYLE="margin-left:28">Prepare deployment plan. Minor progress only, need to detail out and  finalize plan.
11 days
Wed 10/16/02
Wed 10/30/02
Kelley Mike[50%],Chaffey Mark[50%],Erickson Jon[5%],Andrew Hamilton[50%]
9%

