MOOS Mooring 10/29/03 Meeting Notes

1) Budget Ordering parts for second mooring!


MMC titanium Benthic housings (Jon) Pending bulkhead area review (Mark C.)


MMC surface housings (Jon) Pending surface MMC and power systems chassis review.


Additional coilcord (Mark C.)

 Snubber (Mark C.)

railroad wheels.

Hold put on buying parts for 3rd mooring (test #4, November 04) pending budget update.

2) Documentation. New project folder.
3) NSF Project: 

· Weekly phonecon summary Informed Dan of our intention of squeezing out funds for 3rd mooring and controller electronics. Costs for instrumentation, floats and cable still need to be found in the NSF grant funds.
· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats
· Cable float redesign.  Flotec/Dunlaw proposal coming?CRP received, Flotec expected. Call from “bad cop” eminent!
Terminations

· Termination design. No progress.
· Termination bending strain relief specification and purchase. Bundled in with cable float transition design.
· New cable order status.

· Sample procurement. All samples received.
· TMT testing. Testing of first sample complete. Gen. #1 cable broke at 46% strength after test, new design broke at 88%. Definitely an improvement. Further sample tests underway.
· Deployment/recovery winch requirements/specifications (Jon E./Mike K.) Pengo Capabilities? Firm quotes from vendors? Date for proposal review? All bids received except Inter-Ocean. Planning review.
Cable test jig

· Design and schedule for fabrication. Progress on completion date? CDR held on design and fabrication underway.
5) Deployment. and test plan

· Instrument requirements list for each mooring. No update.
· Strain gage data logging requirements. No update.
· Schedule. March March March!  
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. Delay in fabrication due to vendor. All parts in except two connector parts.
· Comms PCB

Order FO transceivers – verify delivery (Mark C.) Finalizing FO specification.
· Integration of SideARM, DPAs and Java status (Wayne/Tim/Kent) 
· Power management application development. (Bob H.) On hold pending Bob’s return. – March deployments won’t require power management.

· RF board design. (Lance). Plan on scheduling PDR next week.
7) Power system (Ed) 
· Power system embedded micro status. Strain gage reading resolved. Plan A is to fabricate A/D subsystem in Power Can for permanent powering and reading of the upper strain gage. Lower strain gage will run through current loop and connect to clone of power can persistor A/D system installed in the MMC housing. Same layout as first test mooring with persistor replacing the Smart Star. 
8) Surface Assembly

· Surface electronics assembly (Lance).
· Surface mechanical assembly (Jon) All parts on order or in fabrication? Housing bulkheads in shop que? Housing bulkhead ends not yet in shop que.
9) Anchor system (Andy) Pigtail cable needs to be spec’d, before termination design can be completed. No update.
10) BINs (Mark C.)  CD building a new BIN for lower canyon that incorporates results of  “Lessons Learned” meeting. BIN for test mooring deployment will be one of existing designs. No update.
11) Puck development status. (Lance/Mike R.). Meeting help on  requirements and timeline for redesign. Power target?Revised design has three variants, current design with power cut-off, and  232 and 485 non-isolated low power  designs. Target is to reduce the power consumption to approximately ¼ of current design for non-isolated designs. 
12) SIAM update. (Tom)  Globalstar installed in building G for SIAM comms testing.
SIAM PDR scheduled for Nov 17th-18th 

13) Download status from "parking lot deployment". Switchover to current SIAM/MMC release schedule. Installation of a PUCK.   Status update?Power can comms having some problems resolved?. Power can PUCK comms problems not resolved, put on hold. Data loading into SSDS OK. Feature of being able to download data from specified time periods not re-implemented after loading latest release.






