MOOS Mooring 11/05/03 Meeting Notes

Present: Kent, Wayne, Andy, Lance, Keith, Mark C.

1) Budget Ordering parts for second mooring!


MMC titanium Benthic housings (Jon) Pending bulkhead area review (Mark C.)


MMC surface housings (Jon) Pending MMC and Power chassis review (Lance & Ed)


Additional coilcords and Y cable Mark C.

Snubber Mark C.

railroad wheels. Pending PO from Mike K.

2) Documentation. New project folder.
3) NSF Project: 

· Weekly phonecon summary No phonecon.
· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats
· Cable float redesign.  Schedule review of cable float purchase? Floatation design CDR planned for Friday. Good quotes received from Flotec and CRP.
Terminations

· Termination design. No update (Mark C.)
· Termination bending strain relief specification and purchase. Still associated with float system purchase?Yes, part of floatation package.
· New cable order status.

· TMT sample testing progress. Cortland, JDR and Rochester cables have all been tested. Cortland cable lost no strength due to fatigue test but has poor torque rotation qualities. Other cables had reduced strength to various degrees. Several samples remain to be run.
· Deployment/recovery winch requirements/specifications (Jon E./Mike K.) Date for proposal review still next Monday? Yes Monday necessary due to other conflicts. Rich Mueller cannot attend but is has verified winch fit on the Pt. Sur.
Cable test jig

· Design and schedule for fabrication. Schedule for completion date? Still TBD, drawings are still being completed by Larry.
5) Deployment. and test plan

· Instrument requirements list for each mooring.

· Strain gage data logging requirements.
· Schedule. Deployment schedule March 23-24. 
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. Expect first articles of completed boards Tuesday next week.
· Comms PCB

Order FO transceivers – verify delivery (Mark C.) Alternate part with internal power monitoring specified. Industry standard package available from multiple vendors.

F/O network design. Preliminary topology being forwarded to Wayne for predicting network switching characteristics.

· Integration of SideARM, DPAs and Java status (Wayne/Tim/Kent) NO update.
· Power management application development. (Bob H.) On hold pending Bob’s return. – March deployments won’t require power management.

· RF board design. (Lance). Reviewed interface with backplane and SideARM. Next step PDR.
7) Power system (Ed) 
· Prototype power converter build. Work started by Jose.
· Battery voltage down-converter build.

· HV up-converter build.

· HV down-converter build.

· Power system embedded micro.

· Aux. A/D board.

· Chassis design.

8) Surface Assembly

· Surface electronics assembly (Lance). Cable order nearly complete.
· Surface mechanical assembly (Jon) All parts on order or in fabrication? Housing bulkheads in shop que?

9) Anchor system (Andy) Pigtail cable needs to be spec’d, before termination design can be completed. Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom lay cable.
10) BINs (Mark C.) Bin design selection pending Ti sphere selection pending finalizing network topology.
11) Puck development status. (Lance/Mike R.).  Power target ¼ of current use. No update.
12) SIAM update. (Tom) 

SIAM PDR scheduled for Nov 17th-18th 

13) Download status from "parking lot deployment". Ok.






