MOOS Mooring 11/26/03 Meeting Notes

Present: Keith, Lance, Andy H., Ed M., Wayne R., Tom O., Mark C.

1) Budget Current mooring build plan.

Ordering major parts for second mooring

· Load cells

· MMC titanium Benthic housings (Jon) Pending bulkhead area review (Mark C.) We can go ahead and order one standard sphere.
· MMC surface housings (Jon) Pending MMC and Power chassis review (Lance & Ed)

· Additional coilcords and Y cable Mark C.

· Snubber Mark C.

2) Documentation. New project folder migration (Mark C.) Pending
3) NSF Project: 

· Weekly phonecon summary

· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats

· Cable float redesign. Vendor selection still under review. Will re-review purchase decision Monday.
Terminations

· Termination design. (Mark C.) This can start now that cable is specified.
· Termination bending strain relief specification and purchase. Part of floatation package.
· New cable delivery status.

· Deployment/recovery winch review status.
Cable test jig

· Design and schedule for fabrication. Schedule for completion date? Planned for before Xmas holiday.
5) Deployment. and test plan

· Need to meet and fix test #2 location for further planning and permit.
· Instrument requirements list for each mooring. (Lance)  Use of four or two wires for anchor load cell needs to be determined? (Mark C.) Will investigate.
· Schedule. Deployment schedule March 23-24. 16 Weeks away!
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. Backplane test article ready? Review scheduled for 2PM next Wed. (Dec. 3)
· Comms PCB & F/O network design. Review scheduled for 2 weeks, Dec. 10.
· Integration of SideARM, DPAs and Java status (Wayne/Tim/Kent) No update.
· Power management application development. (Bob H.) On hold pending Bob’s return. – March deployments won’t require power management.

· RF board design. (Lance). Review scheduled for 2 weeks, Dec. 10.
· Chassis design. Discussion on leveraging off of power system chassis deign to develop an overall chassis hardware plan for MMC housing.
· Component orders for through 2005. Every effort being made to have all components of MMC system on order by the end of the year. 
7) SIAM update. (Tom) Request for ROV access to subsea console port status. Will be incorporated in design. Need new portal machine. Mark C. will check with IS.
8) Puck development status. (Lance/Mike R.) Non-isolated PUCK in the works. Lance and Mark STILL NEED to work out timeline and build quantities needed for each type through 2005.

9) Download status from "parking lot deployment". Back up after SIAM demonstration? Not known.
10) Power system (Ed) Power system design review schedule?Pending.
· 48V to 12V power converter build. Proto-design PCB in  fab.?
· HV up-converter build.

· HV down-converter build.

· Power system embedded micro/data acquisition system.

· Chassis design.

· Component orders for through 2005.
11) Surface Assembly No udate.
· Surface electronics assembly (Lance).
· Surface mechanical assembly status (Jon)
· Anchor system (Andy) Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom lay cable.
12) BINs (Mark C.) Bin design selection pending Ti sphere selection pending finalizing network topology. Canyon Dynamic “simple BIN design” recommended choice. Drawings would have to be created to send fabrication out. Need to include “console port” access in subsurface BIN.






