MOOS Mooring 12/10/03 Meeting Notes

Present: Tom O., Andy H., Mike K., Ed M., Keith, Mark C. (notes)

1) Budget Current mooring build plan.

Ordering major parts for second mooring

· Load cells. On order.
· MMC titanium Benthic housings (Jon) Jon E., will order one sphere. No update.
· MMC surface housings (Jon) Pending MMC and Power chassis review (Lance & Ed) Still pending review.
· Additional coilcords and Y cable Mark C. On order for 8 meter snubber extension.
· Snubber Mark C. Existing stock OK.
2) Documentation. New project folder migration (Mark C.) Subsystem matrix set up under project folder, “drawings”. Please use for released documentation. Additional folder organization underway. Email distributed with official subsystem list and naming conventions.
3) NSF Project: 

· Weekly phonecon summary No update.
· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats

· Cable float purchase (Andy) Andy to visit CRP to review bending strain relief and floatation design.
Terminations

· Termination design. (Mark C.)Pending.
· Termination bending strain relief specification and purchase. Part of floatation package.
· New cable delivery status. Andy to visit vendor and investigate adding cable weight for upper section. 
· Deployment/recovery winch review status. CDR review of Dynacon plans?Jon trying to arrange review at MBARI by Dynacon.
Cable test jig

· Design and schedule for fabrication. Major pieces arriving. Final assembly pushed back to third week of January.
5) Deployment. and test plan

· Test #2 location determination and MBMS permit application. (Mark C.) Arranging meeting with John Ryan, Mike Kelley and interested scientists for next week.
· Instrument requirements list for each mooring. (Lance) 

· Schedule. Deployment schedule March 23-24. 14 weeks away!
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. Backplane test article ready? CDR review on SideARM rev. 4 schedule. Backplane in checkout. Possible problems talking to DPA cards. Wayne investigating. SideARM rev. 4 review scheduled for next week when Kent and Bob can attend.
· Comms PCB & F/O network design. CDR schedule. Review scheduled for next week.
· Integration of SideARM, DPA’s and Java status (Wayne/Tim/Kent)
· Power management application development. (Bob H.) On hold pending Bob’s return. – March deployments won’t require power management.

· RF board design. (Lance). CDR schedule. Next week.
· Chassis design. Review next week
· Component orders for through 2005. Carolyn waiting for BOMS.

7) SIAM update. (Tom) Request for portal computer. SIAM developing responses to review comments and considering PUCK software specification revision.
8) Puck development status. (Lance/Mike R.) Non-isolated PUCK in the works. Lance and Mark STILL NEED to work out timeline and build quantities needed for each type through 2005.
9) Download status from "parking lot deployment". No update
10) Power system (Ed) Power system PDR design review to be held on Friday. 
· 48V to 12V power converter build.

· HV up-converter build.

· HV down-converter build.

· Power system embedded micro/data acquisition system.

· Chassis design.

· Component orders for through 2005.
11) Surface Assembly

· Surface electronics assembly (Lance).
· Surface mechanical assembly status (Jon)
· Anchor system (Andy) Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom lay cable. 2 meter pigtails are available from CD. May have to be modified or new pigtail ordered. Mark C. still needs to investigate and resolve.
12) BINs (Mark C.) Bin design selection pending Ti sphere selection pending finalizing network topology. Further research into BIN designs leads to recommendation of ”Broadband type” with fiberglass frame for Ti sphere. Final determination may be influenced by mooring deployment location and Benthic instrument meeting. 






