MOOS Mooring 12/17/03 Meeting Notes

Present: Lance, Ed M., Kent, Mike K., Jon E., Johnny F., Wayne, Andy, Mark C. (notes) 

1) Budget Current mooring build plan.

Ordering major parts for second mooring

· MMC titanium Benthic housings (Jon) . Sphere ordered, for $5300. 16 week delivery, McGill can loan (trade sphere for project deployment if necessary.
· MMC surface housings (Jon) Pending MMC and Power chassis review (Lance & Ed) Still pending review.
2) Documentation. New project folder migration (Mark C.) Project folder available for released design documentation, organized by subsystem.
3) NSF Project: 

· Weekly phonecon summary No update.
· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats

· Cable float purchase (Andy) On schedule.
Terminations

· Termination design. (Mark C.)
· Termination bending strain relief specification and purchase. Part of floatation package.
· New cable delivery status. On schedule.
· Deployment/recovery winch review status. CDR review of Dynacon plans arranged by Jon? Andy reports cable lay angle/direction must be matched by direction of initial wrap on winch drum. Drum appears correct for cable specification, cable dissection needed to confirm lay direction (Mark C.).
Cable test jig

· Design and schedule for fabrication. In progress, final assembly will slip into January when Andy returns from ORION.
5) Deployment. and test plan

· Test #2 location determination and MBMS permit application. (Mark C.) TBD
· Instrument requirements list for each mooring. (Lance) Lance will update.
· Schedule. Deployment schedule March 23-24. 13 weeks away!
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. SA4 review held Monday, new layout in progress, waiting for backplane verification. Backplane layout complete, also waiting on verification.
· Comms PCB & F/O network design. CDR scheduled for tomorrow (Thurs.). Layout in progress. BOM to TOCA Monday.
· Integration of SideARM, DPA’s and Java status (Wayne/Tim/Kent)
· Power management application development. (Bob H.) Bob returning Jan. 7.
· RF board design. (Lance). Review held Monday, In layout.
· Chassis design. Hard parts scheduled to be complete by January 21.
· Component orders for through 2005. In progress.
7) SIAM update. (Tom) Request for portal computer.

8) Puck development status. (Lance/Mike R.) Non-isolated PUCK in the works. Lance and Mark worked up build quantity. Next milestone is CDR of simplified PUCK.

9) "Parking lot deployment" status. Teardown schedule? No specific tear-down schedule. Housings will be needed by CIMT eventually.
10) Power system (Ed) Power system PDR design review results? 
· 48V to 12V power converter build. 

· HV up-converter build.

· HV down-converter build.

· Power system embedded micro/data acquisition system. CDR pending.
· Chassis design. Done.
· Component orders for through 2005. In progress.
· Need to design load sink housings for power system.
11) Surface Assembly

· Surface electronics assembly (Lance). No update.
· Surface mechanical assembly status (Jon) No update.
· Anchor system (Andy) Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom lay cable. 2 meter pigtails are available from CD. May have to be modified or new pigtail ordered. Mark C. still needs to investigate and resolve! No update.
12) BINs (Mark C.) Plans to use broadband style modified after meeting with John Ryan, Charlie Paull and Jim Barry. Current plan is to use a similar design to the one being built for CD Shepard’s Meander. Next milestone: PDR.






