MOOS Mooring 12/24/03 Meeting Notes

1) Budget Current mooring build plan.

Ordering major parts for second mooring

· MMC surface housings (Jon) Pending MMC and Power chassis review (Lance & Ed) Still pending review.

2) Documentation. New project folder migration (Mark C.)
3) NSF Project: 

· Weekly phonecon summary No update.
· Agenda for next phonecon.

4) Riser Cable Assembly  (Andy/Mark C.)

Floats

· Cable float purchase (Andy) No update.
Terminations

· Termination design. (Mark C.)
· Termination bending strain relief specification and purchase. Part of floatation package.
· New cable delivery status. No update.
· Deployment/recovery winch review status. Need to have this CDR review of Dynacon plans!

Cable test jig

· Design and schedule for fabrication. No update.
5) Deployment. and test plan

· Test #2 location determination and MBMS permit application. (Mark C.)

· Instrument requirements list for each mooring. (Lance) In progress.
· Schedule. Deployment schedule March 23-24. 12 weeks away!
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4 and 6 DPA backplane build. Backplane test article has bounce on clock lines, DPA’s do not respond. Debugging.
· Comms PCB & F/O network design. CDR held last Thursday. Mark needs to check clearance on SFP modules.
· Integration of SideARM, DPA’s and Java status (Wayne/Tim/Kent) No update
· Power management application development. (Bob H.) On hold pending Bob’s return. – March deployments won’t require power management.

· RF board design. (Lance). Review items and release to layout?
· Chassis design. Done.
· Component orders for through 2005. Carolyn waiting for BOMS.

7) SIAM update. (Tom) Request for portal computer.

8) Puck development status. (Lance/Mike R.) Non-isolated PUCK in the works. Lance and Mark STILL NEED to work out timeline and build quantities needed for each type through 2005!!!

9) "Parking lot deployment" status. Teardown schedule? No update.
10) Power system (Ed) Power system PDR design review results? 
· 48V to 12V power converter build.

· HV up-converter build.

· HV down-converter build.

· Power system embedded micro/data acquisition system. CDR review next week.
· Chassis design. Done.
· Component orders for through 2005. In progress.
11) Surface Assembly

· Surface electronics assembly (Lance). No update.
· Surface mechanical assembly status (Jon) No update.
· Anchor system (Andy) Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom lay cable. 2 meter pigtails are available from CD. May have to be modified or new pigtail ordered. Mark C. still needs to investigate and resolve!
12) BINs (Mark C.) Bin design selection. No update.






