MOOS Mooring 01/14/04 Meeting Notes

Present: Jon E., Johnny F., Bob H., Jim S., Wayne R., Keith R., Lance, Tom O., Kent, Tim M., John G., Andy, Ed M., Alana S., Mark C. (notes)

1) Budget Current mooring build plan.

· MMC surface housings (Jon) Housings due March 1.
2) Documentation. New project folder migration (Mark C.) File names need modification to remove spaces allowing hypertext use. Mark C. will follow-up.
3) NSF Project: 

· Weekly phonecon summary No update.
· Agenda for next phonecon. No update.
4) Riser Cable Assembly  (Andy/Mark C.)

Floats

· Cable float and termination bending strain relief delivery schedule (Andy) On schedule.
Terminations

· Termination design. (Mark C.)In progress, quote request out for underwater mateable FO connector.
· New cable delivery status. Request from vendor to slip delivery date. Denied.
· Deployment/recovery winch delivery status. In fabrication. Last issues resolved.
Cable test jig

· Design and schedule for fabrication. Larry starting to work on rotation platform.
5) Deployment and test plan

· Instrument requirements list for test#2 mooring. (Lance) Request to add secondary radio link using LOS radios. Hardware will be provided as part of MMC setup. Instrument assignments still TBD.
· Schedule. Deployment schedule March 23-24. 10 weeks away!
· Lab integration set-up deadline February 11, 4 weeks away!
6) MMC development  Design documentation available at  \\Tornado\Engineering\Rawa\DesignRelease
· SideARM rev. 4. Layout complete, last check is to verify matches backplane signal pin-outs. Deadline for first articles to SIAM is February 1!

· 6 DPA backplane build. 485, power supply, layout and load check tests will be completed by this afternoon. Then layout (completed) can be released for fabrication.
· Comms PCB & F/O network design. Layout in progress. Scheduled completion next week.
· Integration of SideARM, DPA’s and Java status (Wayne/Tim/Kent) Some SA3 boards need completion of revision upgrade.
· Power management application development. (Bob H.) No update on SA3 RTC “dead bug” upgrade for power manager.
· RF board design. (Lance). Duane completing final checks on layout. Board must go out this week for fabrication.
· Chassis build? Parts scheduled for delivery January 21.
7) SIAM update. (Tom) Daily SIAM team scrums underway.
8) Puck development status. (Lance/Mike R.) CDR on the simple PUCK design scheduled for tomorrow.
9) "Parking lot deployment" status. Compact flash filled again due to pilot error. Will be reinitialized.
10) Power system (Ed) Power system PDR design review results? 
· 48 to 12 power converter build. Layout 95% complete.
· 48-400 converter build. Layout 95% complete.
· P2 board build (power system embedded micro/data acquisition system) Placement finishing today then final routing. Board promised to Mike and Alana by February 1.
· Solar board build No update.
· Load dump build No update.
· Converter feed board build. In progress.
· Chassis build Hardware due Jan 21.
· Load dump loads Ed working with Jon on this, in progress. Technical problem that in-air operation my cause load dump  overheating needs to be resolved.
· Safety switch box No update.
· 400-12 converter No update.
· Tower power system wiring. Job took 2 days last deployment so not yet critical path. Battery box wiring underway.
· Need updated power figures for instruments and infrastructure as they become available.
11) Surface Assembly

· Surface electronics assembly (Lance). On track.
· Surface mechanical assembly status (Jon)On track.
· Anchor system (Andy) Current plan calls for 10 meter pigtails at base of mooring which ROV will attach to bottom laid cable. 2-meter pigtails are available from CD. Quote request in to ODI for connector and 10 meter cable.
12) BINs (Mark C.) Bin design selection. BIN PDR scheduled for Thursday (tomorrow).






