MOOS Mooring 03/03/04 Meeting Agenda
1) Budget
2) Schedule.

· Lab integration set-up. Still need RF/I/O, POWER SYSTEM with load cells and COMMS card?
· Closed can testing rescheduled to March 19, 2 weeks away.
· Readiness review March 19.
· On-buoy testing begins March 24. 3 weeks away.
· Deployment rescheduled to April 21-22. 7 weeks away!
3) Documentation and tracking..
· MMC Design doc. currently available at  \\Tornado\ProjectLibrary\900325.MMC 
· Additional doc. Available in \\Tornado\ProjectLibrary\600027.MOOS.Mooring\Project.Drawings
4) NSF Project.
5) Deployment and test plan

· Predeployment testing plan. First draft plan release date is March 5.
· Deployment plan. (Mike, Andy and Mark C.) First draft release date is March 15.
· Instrument integration status and (data verifier). (from Lance)
Globalstar  (Lance  - stand alone testing in progress, Integration in progress

Pager  (Lance  - Integrated

Power Can   (Ed) & load cells (Andy)   - Preliminary integration testing in progress, full integration pending power can delivery

Optical ADC (Lance)   - Integration testing in progress, Data verification in progress

Compass   (Lance & Tim)   - standalone software testing in progress, integration pending driver delivery

Longwave PRR (TBD - Chassis integration complete, Data verification in progress

Freewave      - Integration testing in progress 

Ethernet      - Integrated, further testing pending MEDUSA

ADCP   (Paul)     - Integration testing in progress

Shortwave PRR (TBD - Chassis integration complete, Data verification in progress

Wind/Heading (TBD - Chassis integration complete, Data verification in progress

RH/Temp   (TBD    - Chassis integration complete, Data verification in progress

Wave Sensor  (Andy) - Integration testing in progress

Console       - Integrated

Garmin GPS   (TBD)  - Chassis integration complete, Data verification in progress

MSP430   (Tim)     - standalone software testing in progress, integration pending driver delivery

BIN Instruments Not a priority until after buoy deployment.
17 HS-2 - Backscatter & Florescence HOBILabs HS-2 BIN 1500m (Kent) 

18 SBE-16 CTD Sea-Bird Electronics with pumped conductivity cell SBE-16 BIN 1500m (Kent

19 RDI Workhorse Sentinel 600 kHz ADCP BIN 1500m.
6) MMC development  
· SideARM rev. 4. Any issues besides compass serial port interface problem? Flash testing update?
· Compass turns counter application. (Tim). Should be rolled into “deployed” system?
· 6 DPA backplane build.
· Medusa/Comms PCB. Checkout status? Embedded software progress?
· DPA second build (25). Done!
· Power management application development. (Bob H.)
· RF board design. (Lance). Status?
· MMC surface housings (Jon). Status?
· Buoy light! (Will reuse existing stand-alone light).
7) SIAM update. (from Tom O’Reilly)  Given reschedule MTM still needs new deadline from SIAM for the arrival of working hardware – if it needs software support i.e. Medusa card. Memory size issue, how often are we sampling?
  - Chaffey suggests "shmoo" test of system with compact flash – who will do this?

8) SSDS. Power instrument data format resolved.
9) Puck development status. (Lance/Mike R) Status on hardware build and design for shallow housing mold?

10) Power system (Ed) 

P2 board build (power system embedded micro/data acquisition system) P2 backplane Rev. 1 status? Still on track to have  all SW enabled PCB’s in chassis by end of this week (Converter/GF, Solar/Battery and Wind/load sink PCB’s)?

· Converter/GF board build. Testing status?
· Solar/battery board build. PCB stuff and checkout status?
· 48 to 12 power converter build. Done?
· 48-400 converter build.

· Wind load sink PCB build. Parts stuffing schedule?
· Load sink resistive load housings. Out for fabrication?
· Chassis build. Completion date?
· Safety switch box

· 400-12 converter Pending completion of surface electronics.
· Power system surface housings (Jon) 
· Battery box wiring. Lids screwed on?
· Solar array wiring. Done.
11) Surface Assembly

· Surface electronics assembly (Lance). Schedule for overall instruments mounting and wiring completion is to have all complete by March 24. What do we need to complete this?
· Surface mechanical assembly status (Jon)
12) "Parking lot deployment" status. How to decommission the power system? Still an open question.
13) Riser Cable Assembly  (Andy)

Floats (Andy)
· Cable float and termination bending strain relief delivery schedule (Andy) Scheduled for February 13 delivery. Floats and manual banding tools are supposed ship last week by air freight, did they? Should be in-house this week. The clamp assembly still scheduled  to ship March 19?
Snubber assembly (Mark C.)
· Length extension. SeaCon now promising needed parts by March 12. End plates completion date is March 19 from MBARI shop. 
New cable (Andy)
· Delivery status. Not on schedule for February 13 delivery date, vendor still scheduled to ship March 11 and MBARI receipt March 19. Still on track?
· Termination design. (Mark C.) Status?
Cable Handling Equipment (Jon, Andy)
· Deployment/recovery winch, Delivery status. Still on schedule for early March delivery?
· Cable spooling stands. Finish weld fork pockets still outstanding (Frank)?
Cable test jig (Andy)
· Design and schedule for fabrication.

14) Anchor system (Andy)

15) BINs (Mark C.)






