MOOS Mooring 03/17/04 Meeting Notes
1) Budget No update.
2) Schedule.

· Closed can testing begins March 19, Friday.
· Instrument readiness review March 19, Friday (SIAM).
· On-buoy testing scheduled to begin March 24. 1 week away. May be adjusted out a few days depending on power can delivery status.
· Deployment rescheduled to April 21-22. 5 weeks away!
· Load winch Tuesday April 20, load buoy and snubber Wednesday April 21.

3) Documentation and tracking..
· MMC Design doc. currently available at  \\Tornado\ProjectLibrary\900325.MMC
· Additional doc. Available in \\Tornado\ProjectLibrary\600027.MOOS.Mooring\Project.Drawings
4) NSF Project. No update.
5) Deployment and test plan

· Predeployment testing plan. In progress.
· Deployment plan. (Mike, Andy and Mark C.) First draft release date is March 15. Moved to March 24.
· Instrument integration status and (data verification).  Instrument verification status:
Globalstar(Lance/Kent)
- Portal connection OK. In test.

Freewave (Bob?)

- Integrated. Status?
Garmin GPS (Kent)
- Data OK except error message on start-up. Kent pursuing.
Ethernet 


- Integrated.
Console Port

- Integrated. Status?
RF Pager reset (Lance) 
- Integrated. Status?

P2 Power Can (Ed/Mike)
- Preliminary integration testing in progress, full integration pending power can delivery (next week) (Ed).
P2 OpticADC (Lance/Mike)- Data checked out by Lance and Mike. Still need to confirm calibration strategy.
MSP430/compass turns (Kent/Lance)
- Data checked out by Lance and Kent.
Asimet Longwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Shortwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Wind/Heading (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet RH/Temp (Tom/John R.)

- Data verification in progress.(Tom,Ryan)
Long Ranger ADCP (Kent/Paul)

- Kent and Fred Barr checking data. Full integration pending battery installation.
Wave Sensor (Tom/Andy)


- Data verification in progress.(Tom,Andy)
BIN Instruments Not a priority until after buoy deployment.
17 HS-2 - Backscatter & Florescence HOBILabs HS-2 BIN 1500m (Kent) 

18 SBE-16 CTD Sea-Bird Electronics with pumped conductivity cell SBE-16 BIN 1500m (Kent

19 RDI Workhorse Sentinel 600 kHz ADCP BIN 1500m.
6) MMC development  
· SideARM rev. 4. Outstanding issue is compass serial port interface. Also error from flash on start-up. 15 in stock, decision to build 12 more pending. 2GB memory card will be used for MTM#2 deployment.
· Compass turns counter application. (Tim). Done, in final test.
· Medusa/Comms PCB. Switch not loading configuration, Wayne checking. I2C protocol in development. SIAM interface not yet defined. Decision made to not place on initial deployment, will be installed as a can-swap.
· DPA second build (25). Done!
· Power management application development. (Bob H.) No update.
· RF board design. (Lance). Done!
· MMC surface housings (Jon). Delivery Friday, March 19 or Monday.
· Buoy light! (Will reuse existing stand-alone light). Installed.
7) SIAM update. (from Tom O’Reilly)  

· Software frozen.

· Instrument data quality checks in progress.

· Instrument readiness review Friday, March 19, 10:00AM in building G.

· Portal up and running with modem connection to Globalstar.
8) SSDS. Instrument data available at  http://ssds.shore.mbari.org:8080/access/siamRawDataStep1.jsp
9) Puck development status. (Lance/Mike R) 
· New puck PCBs complete and fully tested.

· PDR held for molded shallow design. Looked good, question of developing additional variant with cables out same side.

· Memory/power firmware bug status unknown.

10) Power system (Ed)  Deliver power can to SIAM Friday?  
· P2 board build (power system embedded micro/data acquisition system) Done.
· Backplane.  Done.
· Converter/GF board build. Done.
· Solar/battery board build. Done.
· 48 to 12 power converter build. Done.
· 48-400 converter build.  Testing.  

· Wind load sink PCB build. Done. 
· Load sink resistive load housings. Out for fabrication. Current shop delivery Mar. 29 then further treating – too late for testing before Ed leaves. Must bring in date.  
· Chassis build. In final mechanical assembly. Wiring start Thursday or Friday.  
· Safety switch box   Tested, needs mounting.
· 400-12 converter Pending completion of surface electronics.  
· Power system surface housings (Jon) Delivery Friday, March 19 or Monday.
· Battery box wiring. Done.
· Software.  Checkout in progress, freezing code by end of the week. Will not be revised unless fatal bugs discovered.
11) Surface Assembly

· Buoy Standup.  March 24

· Wiring (Lance, Ed)
· Instrument Brackets (Jon)  In progress.

· Mechanical assembly (Jon) Plan is to wire tower before final assembly, move parts outside for final assembly. Location for tower wiring TBD, best site is inside with view of sun through open doorway for power system testing.  

· Location.  Still TBD, possible sites are next to building B, in N rear, outside buoy assembly room and on dock.  

· Surface electronics assembly (Lance, Ed).  Assembled on bench.
· Surface mechanical assembly status (Jon) In progress.
12) "Parking lot deployment" status. 

· Date for decommissioning will be done after MTM2 deployment.  Housings not needed until then.  
13) Riser Cable Assembly  (Andy)

Floats (Andy)
· Cable float and termination bending strain relief delivery schedule (Andy) Parts on-site. Need to order additional bands for test purposes.
Snubber assembly (Mark C.)
· Length extension. SeaCon parts on-site. End plates completion date is March 19 from MBARI shop.
New cable (Andy)
· Delivery status. Arrived SFO. Schedule for clearing customs and trucking to MBARI TBD.
· Termination design. (Mark C.)  ODI committed to completing design and installing terminations at MBARI in early April. MBARI providing housings and several inner pieces. Plan on shipping most articles Friday, March 19 to ODI.
Cable Handling Equipment (Jon, Andy)
· Deployment/recovery winch, Delivery status. On-site. Chris G. working with Pt. Sur on installation. Jon E. will make sure winch operates properly on Pt. Sur. 
· Cable spooling stands. Weld of fork pockets still outstanding (Frank)?
Cable test jig (Andy)
· Design and schedule for fabrication. No update.
14) Anchor system (Andy) No update.
15) BINs (Mark C.) No update.






