MOOS Mooring 03/24/04 Meeting Notes
Present: Andy H., Tim M., Tom O., Kent, Wayne, Kevin G., Mike K., Keith R., Lance, Jon E., Mark C.

1) Budget No update.
2) Schedule.

· Closed can testing begins March 19, Friday. Update!
· On-buoy testing scheduled to begin March 24. Update!
· Deployment rescheduled to April 21-22. 4 weeks away!
· Load winch Tuesday April 20, load buoy and snubber Wednesday April 21.

3) Documentation and tracking..
· MMC Design doc. currently available at  \\Tornado\ProjectLibrary\900325.MMC
· Additional doc. Available in \\Tornado\ProjectLibrary\600027.MOOS.Mooring\Project.Drawings
4) NSF Project.
5) Deployment and test plan

· Predeployment testing plan. Checklist distributed, comments welcome.
· Deployment plan. (Mike, Andy and Mark C.) Pending, Mark C. will produce first draft.
· Instrument integration status and (data verification).  Instrument verification status:
Globalstar(Lance/Kent)
- Ok. Some SIAM/PPP connection issues remaining.

Freewave (Bob?)

- Ok.
Garmin GPS (Kent)
- Data OK except error message on start-up. Kent pursuing.
Ethernet 


- Ok,integrated.
Console Port

- Some possible intermittent problems. Could be cable.
RF Pager reset (Lance) 
- Ok, integrated. Status?

P2 Power Can (Ed/Mike)
- Deployed board set running in a test chassis. Deployed chassis to be installed next week. (Ed).
P2 OpticADC (Lance/Mike)- Ok, data checked out by Lance and Mike.
MSP430/compass turns (Kent/Lance)
- Ok.
Asimet Longwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Shortwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Wind/Heading (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet RH/Temp (Tom/John R.)

- Data verification in progress.(Tom,Ryan)
Long Ranger ADCP (Kent/Paul)

- Kent and Fred Barr checking data..Running on batteries.
Wave Sensor (Tom/Andy)


- Problems running off of PUCK, fix in progress.
BIN Instruments Not a priority until after buoy deployment.
17 HS-2 - Backscatter & Florescence HOBILabs HS-2 BIN 1500m (Kent) 

18 SBE-16 CTD Sea-Bird Electronics with pumped conductivity cell SBE-16 BIN 1500m (Kent

19 RDI Workhorse Sentinel 600 kHz ADCP BIN 1500m.
6) MMC development  
· SideARM rev. 4. Outstanding issue still remaining is compass serial port interface. Error message from flash on start-up does not appear critical. 15 SA4’s  in stock, decision to build 12 more pending.
· Medusa/Comms PCB. In progress.
· Power management application development. (Bob H.) No update.
7) SIAM update. (from Tom O’Reilly)  Final instrument checkout under way. Several outstanding issues being resolved before can closure and lab overnight test tonight.
8) SSDS. Instrument data available at  http://ssds.shore.mbari.org:8080/access/siamRawDataStep1.jsp
9) Puck development status. (Lance/Mike R) 
· CDR for new mould not yet scheduled.

· Memory/power firmware bug still outstanding. Affects instrument on power consumption.

10) Power system (Ed)
· 48-400 converter build.  Still testing. Transformer not performing as well as design predicted, need to resolve.  

· Load sink resistive load housings. Out for fabrication. Can test without but still need by early April.  
· Chassis build. In progress.
· Safety switch box   Mounting today, then wire and remount.
· 400-12 converter Pending completion of surface electronics.  
· Software. Done and frozen unless fatal bug discoverd.
11) Surface Assembly

· MMC installation on buoy. Tomorrow, pending SIAM release..

· Wiring (Lance, Ed) In progress.

· Instrument Brackets (Jon) In progress.

· Surface mechanical assembly status (Jon) Plan is to wire tower and add MMC. Tower will be moved on pallet between the corner of building B (sky view) and AUV operations area (lab work site). Tower will not be bolted to float until power testing complete.  
12) "Parking lot deployment" status. Date for decommissioning will be after MTM2 deployment.  Housings not needed until then.  
13) Riser Cable Assembly  (Andy)

Floats (Andy)
· Cable float and termination bending strain relief delivery schedule (Andy) Additional bands on order for test purposes, should arrive in 1-2 days.
Snubber assembly (Mark C.)
· Length extension. SeaCon parts on-site. End plates and other parts coming out of shop in next day or two. Additional work of post-weld machining adding delay.
New cable (Andy)
· Status. Received from SFO. Some handling damage, severity unknown, could be only cosmetic. JDR representative to inspect early April before cable moved from reel.
· Termination design. (Mark C.)  MBARI supplied parts have mostly been shipped. Outstanding items should go out tomorrow. ODI currently quoting termination starting April 12, only 7 days before loading ship. Mark keeping pressure on to make sure there is no slippage.
Cable Handling Equipment (Jon, Andy)
· Deployment/recovery winch. Power unit checked out on Pt. Sur and OK. Need longer power cord. 
· Cable spooling stands. Weld of fork pockets still outstanding (Frank)?
Cable test jig (Andy)
· Design and schedule for fabrication. No update.
14) Anchor system (Andy) Fabrication underway. Andy considering lowering overall weight slightly. Mike Kelley retrieving skid plate and stern radius plate from Castroville.
15) BINs (Mark C.) No update






