MOOS Mooring 04/07/04 Meeting Agenda
1) Budget No update.
2) Schedule.

· Deployment rescheduled to April 21-22. 2 weeks away!
· Load winch Tuesday April 20, load buoy and snubber Wednesday April 21.

3) Documentation and tracking..
· MMC Design doc. currently available at  \\Tornado\ProjectLibrary\900325.MMC
· Additional doc. Available in \\Tornado\ProjectLibrary\600027.MOOS.Mooring\Project.Drawings
4) NSF Project. Norm Farr and John Kemp observing on cruise.
5) Deployment and test plan
· Predeployment testing plan. Siam items for checklist. Any others?

· Deployment plan. (Mike, Andy and Mark C.) Preliminary version sent to Sur and Mike. Detailed plan still in progress. Important items are bouy and snubber staging positions, assembly/deployment sequence. Personnel list.
· Instrument integration status and (data verification).  Instrument verification status:
Globalstar(Lance/Kent)
- Ok. Some SIAM/PPP connection issues remaining?

Freewave (Bob?)

- Ok.
Garmin GPS (Kent)
- Startup error message on OK? Kent?
Ethernet 


- Ok..
Console Port

- Ok?
RF Pager reset (Lance) 
- Ok?

P2 Power Can (Ed/Mike)
- Load cell checkout? Any other outstanding items? (Ed)
P2 OpticADC (Lance/Mike)- Ok
MSP430/compass turns (Kent/Lance)
- Ok.
Asimet Longwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Shortwave PRR (Tom/John R.)
- Data verification in progress.(Tom,Ryan)
Asimet Wind/Heading (Tom/John R.)
- Data verification in progress. Status? (Tom,Ryan)
Asimet RH/Temp (Tom/John R.)

- Data error, needs verification. Status? (Tom,Ryan)
Long Ranger ADCP (Kent/Paul)

- Kent and Fred Barr data check OK?.Running on batteries.
Wave Sensor (Tom/Andy)


- Problems running off of PUCK fixed?
BIN Instruments Not a priority until after buoy deployment.
17 HS-2 - Backscatter & Florescence HOBILabs HS-2 BIN 1500m (Kent) 

18 SBE-16 CTD Sea-Bird Electronics with pumped conductivity cell SBE-16 BIN 1500m (Kent

19 RDI Workhorse Sentinel 600 kHz ADCP BIN 1500m.
6) MMC development  
· SideARM rev. 4. Outstanding issue still remaining is compass serial port interface (not critical for this deployment). Error message from flash on start-up does not appear critical. 15 SA4’s  in stock, go-ahead decision made to build final 12. 
· Medusa/Comms PCB. No update.
· Power management application development. (Bob H.) No update.
7) SIAM update. (from Tom O’Reilly) Comms issue connecting to portal resolved? No update but SSDS downloads appear normal.
8) SSDS. Instrument data available at  http://ssds.shore.mbari.org:8080/access/siamRawDataStep1.jsp Presentation work offically frozen for MTM deployment unless bug emerges. Ed requests feature to suppress graphing of static data.
9) Puck development status. (Lance/Mike R) 
· CDR for new mould? No update.
· Memory/power firmware bug still outstanding. Affects instrument on power consumption. No update.
10) Power system (Ed)
· 48-400 converter build.  Some issues remain with transformer that severly impact efficiency. Most likely will not be ready for MTM deployment and will require swap of power can when MMC can is swapped later this summer.
· Load sink resistive load housings. Fabricated parts shipping today. 
· Chassis build. Complete, system in test. Need GND finger bracket which should be done today. 
· Safety switch box. Mounting plan complete, being wired.
· 400-12 converter.  Pending other power items completed.
· Software. Frozen unless serious bugs emerge.
· Wind generator mast being reworked by Johnny.
11) Surface Assembly

· MMC installation on buoy.
· Wiring (Lance, Ed) No update.
· Instrument Brackets (Jon) No update.
· Surface mechanical assembly status (Jon) Plan is to assemble complete buoy next week, exact date TBD depending on power system, instrument and SIAM status. Goal is to assemble Wednesday.
12) "Parking lot deployment" status.

13) Riser Cable Assembly  (Andy)

Floats (Andy)
· Cable float and termination bending strain relief delivery schedule (Andy) Additional bands in transit.
Snubber assembly (Mark C.)
· Length extension. Final part (spiral wrap) arrives tomorrow. Complete assembly will follow.
New cable (Andy)
· Status. JDR representative to inspect this Friday. Pending confirmation of termination date, plan is to spool onto winch drum next week.
· Termination design. (Mark C.)  ODI currently quoting termination starting April 12, only 7 days before loading ship. Will have update this Friday. Plan is to pull test terminations next week and immediately ship back to ODI for disassembly and inspection. Need to have test rig all set up BEFORE specimen arrives to prevent delay.
· Still need penetrator part from shop before termination can be completely assembled.
· Anchor load cells #1 and #2 (spare) have been pressure tested. #2 failed test and has been FedExed back to vendor for repair.
Cable Handling Equipment (Jon, Andy)
· Deployment/recovery winch. Chris, Jon and Mike K. working on staging installation.
· Cable spooling stands. Weld of fork pockets DONE. (go Frank!)
Cable test jig (Andy)
· Design and schedule for fabrication.

14) Anchor system (Andy) Plan for securing and deploying 10 meter FO hose section needed.
15) BINs (Mark C.) No update.






