MOOS Mooring 1/19/05 Meeting Notes
Present: Tim M., Lance M., Ed, Kent, Keith R., Jon E., Andy H., Mark C.

1) January Schedule

Status of MTM2 and BIN deployment.

MTM2 Optical connector at mooring base would not mate with test connector when tested on deck during redeployment. Some mechanical abuse noted on shell. Project considered another redeployment and replacing connector at base of riser but decided against based on:

1. Risk that riser cable would be damaged invalidating the primary test goal.

2. Effort expended to repair MTM2 damage (which can be traced back to deployment issues) could impact successfully deploying MTM4 (MSE) in October.

All further efforts to install BIN and Benthic cable lay on MTM2 are cancelled.

MTM2B housing swap: Is there any reason to swap surface housing? No reason at this time.

Use MTM2B for MTM3 or new chassis? Current MTM2B chassis will be redesignated MTM3 and used for that deployment. “Spare” MMC and Power system chassis will continue to be built up as spares.

If MTM2B what modifications to MTM2B MMC for MTM3.


Remove node-to–node communications card.

Add additional optical channel. MTM3 requires two measurement channels 

Need system drawing for MTM3 and details of interface connection to WHOI cable. Mark C. in contact with WHOI on this.

Battery boxes and solar panels. Hardware exists, need cable inventory etc.

Other parts? See instrument section below.

2) – Project plan for the year. 

a) Review and refinement of overall project plan for 2005.

1. I have 2005 work breakdowns input from Ed, Tim, Wayne, and Jon. Have rough estimates for Andy and Lance and will refine and review with same. Andy will forward detailed WBS today. Mark can work with Lance’s current input. Detailed 2005 project plan will be complete and available for review Monday, January 24.
Important schedule dates are:

MTM2 Recovery, April 11-12. Action items: need to test and practice with Dynacon levelwind mechanism well before recovery cruise.

MTM3 Deployment April 14-15.

MTM3 schedule details.

Tentative MTM4 Deployment (Shepard Meander) October 26-27.

For the Record: 2005 Current MTM3 Instruments and Reps
Surface

Globalstar (Lance) (can we swap with MTM2 for MTM3?) Yes, this should not be a problem.

Pager  (Lance) (work offshore?) Lance will test be coordinating with WF transit.

MMC Can (Lance) Need to investigate turns counter issues.

Power Can (Ed)
Upper load cell (Mark) Need to consider better sealing on load cell.
Lower Load cell (Mark)

Optical ADC  (Lance)

Compass   (Lance & Tim)

Freewave (Lance)
Wind/Heading (Lance)

Wave Sensor (Andy) Mark will check into having grant pay for updating to directional unit.

Garmin GPS  (Kent)
