MOOS Mooring 2/2/05 Meeting Notes

Present: Andy H., Tom O., Wayne, Carolyn T., Ed M., Jon E., John G., Tim M., Johnny., Lance, Kent, Mark C.

1. Resource assignments and issues.

a. ME time. Jon Erickson’s time working with Andy on the lower termination design has been replaced by Mark Brown.
b. SE time. P2 board software upgrades need to Mike Risi time. SE time on the project was not specifically called out as Risi. Mark C. to talk to Doug Au about time allocations.
2. Task details.

	ID
	Task Name
	Duration
	Start
	Finish
	Resource Names
	% Complete

	3
	MTM3 instrument list freeze Instrument list frozen. Heave sensor will not be upgraded to directional unit.
	0 days
	Tue 2/1/05
	Tue 2/1/05
	 
	100%

	4
	MTM3 Analog isolation PCB (load cell) Layout start planned for end of next week.
	16.67 days
	Mon 1/24/05
	Tue 2/15/05
	Ed Mellinger[60%],Jose Rosal,Tom Marion
	20%

	5
	MTM3 Analog isolation software driver See note above. Need cable spec. from Mark C.
	16.67 days?
	Tue 2/1/05
	Wed 2/23/05
	Ed Mellinger[60%],Mike Risi[60%]
	0%

	6
	MTM3 power system final build and test Need to find housing leak. Will try helium sniffer. Need standard MTM configuration drawing from Mark C.
	16.67 days
	Tue 2/1/05
	Wed 2/23/05
	Ed Mellinger[60%],Tom Marion[75%]
	0%

	8
	Order, receive and install second optical channel Part ordered.
	7 days
	Mon 2/7/05
	Tue 2/15/05
	Lance McBride[7%]
	20%

	9
	MTM3 assemble buoy tower
	2 days
	Mon 1/24/05
	Tue 1/25/05
	Johnny Ferrira
	90%

	26
	Fix MTM4 location and depth to +/-50 meters Needed before configuration modeling can start.
	0 days
	Fri 1/28/05
	Fri 1/28/05
	Mark Chaffey[60%]
	0%

	27
	MTM4 Draft of overall system topology Will fall out of the MSE science plan.
	10 days?
	Mon 2/7/05
	Fri 2/18/05
	Mark Chaffey[40%],John Ryan,Jim Barry,Charlie Paull
	0%

	45
	MTM4 configuration modeling Waiting on depth information.
	13.33 days
	Fri 1/28/05
	Wed 2/16/05
	Andrew Hamilton[60%]
	0%

	60
	MMC software, upgrade bootloader Not needed this year.
	1 day?
	Tue 2/1/05
	Tue 2/1/05
	Tim Meese[60%]
	0%

	61
	MMC software, upgrade Linux OS Not absolutely required this year. Will be scheduled out of critical path and evaluated in two months.
	55 days?
	Tue 2/1/05
	Mon 4/18/05
	Tim Meese[60%]
	0%

	62
	MMC software, upgrade J9 JVM release Task of trying upgrade will be scheduled for after Medusa board completion.
	1.67 days?
	Tue 2/1/05
	Wed 2/2/05
	Tim Meese[60%]
	0%

	63
	MMC software, test software upgrades on target hardware This task becomes “test SIAM against new Linux OS” and should be given 20 days (not in critical path).
	1 day?
	Tue 2/1/05
	Tue 2/1/05
	Tim Meese[60%]
	0%

	65
	Medusa complete ver. 2 schematic changes Schematic changes complete. Ready to go to layout. CDR next week.
	15 days?
	Mon 1/24/05
	Fri 2/11/05
	Wayne Radochonski[20%],Mark Chaffey[20%]
	0%

	71
	MMC software, ethernet driver to full duplex No update.
	2 days
	Wed 2/9/05
	Thu 2/10/05
	Tim Meese[60%]
	0%

	73
	Medusa complete Zarlink chip interrupt support No update.
	8.33 days
	Mon 1/24/05
	Thu 2/3/05
	Tim Meese[60%]
	0%

	74
	Medusa add rollover support for SNMP counters No update.
	8.33 days
	Thu 2/3/05
	Tue 2/15/05
	Tim Meese[60%]
	0%

	97
	MTM4 finalize BIN requirements Need penetrator requirements before BIN top-hat can be finalized.
	2 days
	Mon 1/24/05
	Tue 1/25/05
	Jon Erickson[60%],Mark Chaffey[60%]
	0%

	98
	MTM4 design BIN penetrator top hat No update.
	21.67 days?
	Wed 1/26/05
	Thu 2/24/05
	Jon Erickson[60%]
	0%

	116
	MTM4 respecify coilcord cable No update.
	1.67 days?
	Mon 1/24/05
	Tue 1/25/05
	Mark Chaffey[60%]
	0%

	117
	MTM4 fabricate coilcord cable No update.
	30 days
	Tue 1/25/05
	Tue 3/8/05
	Mark Chaffey[3%]
	0%


Additional items discussed that need to get on list:

MTM3 webpage.

MMC watchdog implementation (to replace pager reset.)

MMC Test wake-up from sleep on UART activity – Tim (schedule for mid April)

MMC CF interface, add power-on reset function for CF. – Kent and Wayne

MMC Real-time clock distribution.

Other items considered lower priority:

RF/IO software interface.

MSP430 Turns counter checkout and upgrade.

