MOOS Mooring 4/13/05 Meeting Notes

Present: Lance, Dick, Tom O., Tim, Ed, Johnny, Keith, Mark.

1) Overall schedule issues. MTM3 deployment in August? WHOI considering chartering the Gordon Sproul to deploy MTM3 but latest communication makes this sound unlikely. October still considered most likely MTM3 deploy date.  
2) MTM2 recovery.  Post-recovery testing and data recovery. Mark requests that each subsystem lead evaluate the performance of their equipment and summarize in a page of less of text. Goal is to capture any lessons learned, design/fabrication issues, wear and tear data, etc. from the year long deployment that will allow us to accurately predict system performance and service life. Mostly a hardware issue but they may be some key software items also. Would like to put out an overall system performance summary by May 15th.  
3) ECO issues:

a. Housing end plates due to corrosion Jon Erickson modifying to polymer end cap. Pressure rating for housing will now be 3PSI MAXIMUM. Pressure charging will now require use of regulator to prevent over-pressurization.
b. OSG again raised issue of HV manual switch location. Ed investigating.
4) Action items from last meeting:

a. MTM3 pucks, have parts in stock. Mark C. and Lance to checkout best configuration before deciding on molded or cylinder housing. Still pending.

b. Watchdog timer meeting today. Postponed.
5) Need to add WHOI vane to tower (Johnny).

6) MMC Linux upgrade. Tim bringing over and installing 2.4.27 kernel version. Also will test CF flash power cycle capability. Will be tested for one week and decision made to forge ahead or revert to 2.4.9
7) Current task list:

	
ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	4
	MTM3 Analog isolation PCB (load cell) Placed and 50% routed. Finish this week.
	16.67 days
	Mon 1/24/05
	Fri 3/11/05
	-5.67 days
	70%
	Ed Mellinger[60%],Jose Rosal,Tom Marion

	5
	MTM3 Analog isolation software driver Pending hardware completion.
	5 days
	Tue 2/15/05
	Thu 3/17/05
	-6.5 days
	80%
	Ed Mellinger[60%],Mike Risi[60%]

	28
	MTM4 Draft of overall system topology In progress.
	10 days
	Mon 2/7/05
	Thu 3/3/05
	0 days
	90%
	Mark Chaffey[40%],John Ryan,Jim Barry,Charlie Paull

	30
	MTM4 Power budget In progress.
	20 days
	Thu 3/17/05
	Wed 4/13/05
	8.33 days
	0%
	Ed Mellinger[10%]

	31
	Fix number of BINs and topological layout Critical to complete.
	0 days
	Wed 3/16/05
	Wed 3/16/05
	13.75 days
	0%
	Mark Chaffey[60%]

	32
	Final revisions of instrument list Critical to complete
	26 days
	Fri 3/4/05
	Fri 4/8/05
	11.33 days
	80%
	Mark Chaffey[4%],John Ryan[2%],Jim Barry[2%],Charlie Paull[2%]

	37
	MTM4 Complete MMC configuration drawings Pending final instrument list.
	7 days
	Wed 3/2/05
	Thu 3/24/05
	8.08 days
	25%
	Lance McBride[60%]

	48
	Medusa ver. 2 board fabrication and stuff First articles due around April 18.
	20 days
	Tue 3/22/05
	Mon 4/18/05
	40.33 days
	0%
	Wayne Radochonski[10%]

	53
	Medusa power management testing In progress.
	3.33 days
	Thu 3/17/05
	Tue 3/22/05
	75 days
	0%
	Tim Meese[60%]

	54
	Medusa test port mirroring/failover support In progress.
	8.33 days
	Thu 3/17/05
	Tue 3/29/05
	70 days
	0%
	Tim Meese[60%]

	55
	Medusa SPI communications support In progress.
	13.33 days
	Thu 3/17/05
	Tue 4/5/05
	65 days
	0%
	Tim Meese[60%]

	59
	MMC software, Verify watchdog function In progress.
	2 days
	Thu 3/17/05
	Fri 3/18/05
	5 days
	0%
	Tim Meese[60%]

	61
	MMC software, test UART wake-up from sleep function Done.
	1.67 days
	Tue 4/12/05
	Wed 4/13/05
	68.66 days
	0%
	Tim Meese[60%]

	69
	Complete assembly of spare power can Two spare cans under fabrication by Jim, one for CIMT, one for MOOS.
	18.67 days
	Mon 3/28/05
	Thu 4/21/05
	181.33 days
	0%
	Jim Scholfield[75%],Tom Marion[75%],Ed Mellinger[10%]


