MOOS Mooring 7/06/05 Meeting Agenda
1) Project schedule.

.

2) High priority software tasks.

a. XAR UART/RFIO interaction on wakeup from sleep. Sleep enabled ethernet driver testing progress? Software has wakeup from sleep on receive serial character testing.
3) Action items:

a. MTM3 pucks, have parts in stock. Mark C. and Lance to checkout best configuration before deciding on molded or cylinder housing. Still pending. Which pucks to use, low power vs. high power version? Progress on discussions with Satlantic on adding puck functionality to ISUS?
4) New tasks to add:

a. 20 meter MMC housing (Jon)..
b. Radiometer obstruction (Jon). Topic for next science instrument meeting.
c. MMC card extenders (Mark/Jose).

d. Specification and fabrication of BIN-to-profiler benthic copper cable. (Mark C.) Added to project list.
e. Testing Oasis super-cap board. (Ed). In progress, will be added to project list.
f. Resolving wind generator/wind speed measurement interference (not assigned).
g. Need top level reference drawing that has all subsystem top-level drawings reference numbers.
Current task list:
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	4
	MTM3 Analog isolation PCB (load cell) Need to complete test, and SW checkout.
	16.67 days
	Mon 1/24/05
	Tue 5/3/05
	21.83 days
	90%
	Ed Mellinger[60%],Jose Rosal,Tom Marion

	5
	MTM3 Analog isolation software driver Hardware ready for SW integration test. No update.
	5 days
	Tue 2/15/05
	Thu 4/28/05
	27 days
	80%
	Ed Mellinger[60%],Mike Risi[60%]

	6
	MTM3 power system final build and test Still pending analog and modified P2 board completion and new end caps from shop. Current plan is to turn around MTM2 into MTM4 first so that it can be swapped out with MTM2/3 (currently on bench) with minimum downtime for SIAM. Status of power can build? What’s needed for controller build?
	13.33 days
	Wed 5/4/05
	Mon 5/23/05
	10.67 days
	0%
	Ed Mellinger[60%],Tom Marion[75%]

	8
	Order, receive and install second optical channel Waiting for MTM3 power system rebuild.
	64.8 days
	Mon 2/7/05
	Fri 5/6/05
	21.2 days
	6%
	Lance McBride[7%]

	28
	MTM4 Draft of overall system topology Draft is two seafloor BINS, a 20 meter MMC  and a second surface MMC for over 12 instruments.
	10 days
	Mon 2/7/05
	Thu 3/3/05
	43 days
	90%
	Mark Chaffey[40%],John Ryan,Jim Barry,Charlie Paull

	30
	MTM4 Power budget 
	20 days
	Wed 5/4/05
	Tue 5/31/05
	-30 days
	0%
	Ed Mellinger[10%]

	31
	Fix number of BINs and topological layout 
	0 days
	Tue 5/3/05
	Tue 5/3/05
	0 days
	0%
	Mark Chaffey[60%]

	32
	Final revisions of instrument list Current revision available in project folder: X:\600027.MOOS.Mooring\Project.Documents\MSEInstrumentConfiguration\ MTM4MasterInstrumentList.xls Engineering sensors added to instrument list. Column reserved for tracking assigned ports and individual board serial numbers and/or instrument ID’s.
	48.2 days
	Fri 3/4/05
	Wed 5/11/05
	-15.2 days
	89%
	Mark Chaffey[4%],John Ryan[2%],Jim Barry[2%],Charlie Paull[2%]

	34
	MTM4 order and receive instrumentation 
	60 days
	Wed 6/1/05
	Tue 8/23/05
	-30 days
	0%
	Mark Chaffey[2%],John Ryan[1%],Lance McBride[2%]

	35
	MTM4 go-no decision Decision made to reschedule deployment from October 05 to spring 06. Exact date TBD depending on ship availability.
	0 days
	Thu 5/19/05
	Thu 5/19/05
	1 day
	0%
	Mark Chaffey[60%],Andrew Hamilton[60%],Keith Raybould,John Ryan[60%]

	37
	MTM4 Complete MMC configuration drawings 
	7 days
	Wed 3/2/05
	Wed 5/11/05
	-30.25 days
	25%
	Lance McBride[60%]

	38
	MTM4 Modify MTM2 MMC for MTM4 In progress by Tom M. New endcaps being used. Status?
	4 days
	Wed 5/11/05
	Tue 5/17/05
	29.75 days
	0%
	Lance McBride[60%],Dick Littlefield[75%]

	39
	MTM4 Specify and order surface instrument cables In progress.
	10 days
	Wed 5/11/05
	Wed 5/25/05
	-30.25 days
	0%
	Lance McBride[60%]

	40
	MTM4 Fabricate instrumentation cables and PUCK connectors In progress.
	60 days
	Wed 5/25/05
	Wed 8/17/05
	-30.25 days
	0%
	Lance McBride[3%]

	53
	Medusa power management testing Status of Medusa wakeup-SideArm-on-broadcast packet code?( Now that SideArm sleep mode is in test this is the highest priority.)
	3.33 days
	Wed 5/4/05
	Mon 5/9/05
	35.66 days
	0%
	Tim Meese[60%]

	54
	Medusa test port mirroring/failover support 
	8.33 days
	Thu 3/17/05
	Tue 5/10/05
	34.83 days
	50%
	Tim Meese[60%]

	55
	Medusa diagnostic data serial interface port Diagnostic serial interface API done, needs to be tested with SIAM.
	13.33 days
	Wed 5/4/05
	Mon 5/23/05
	25.66 days
	0%
	Tim Meese[60%]

	57
	Medusa full function testing with SIAM Pending completion of Medusa tasks #53, 54, and 55 above.
	11 days
	Mon 5/23/05
	Tue 6/7/05
	25.66 days
	0%
	Tim Meese[60%],Mark Chaffey[60%],Wayne Radochonski[60%]

	60
	MMC software, test UART wake-up from sleep function Not fully tested with sleep enabled. SIAM will test.
	1.67 days
	Tue 4/12/05
	Thu 6/9/05
	23.83 days
	90%
	Tim Meese[60%]

	67
	Revise P2 PCB for MMC rev. 2 backplane Ready for test.
	10 days
	Mon 2/28/05
	Fri 5/6/05
	-22.34 days
	70%
	Ed Mellinger[60%],Tom Marion

	70
	Design modifications, 400-12 w/switch Block diagram underway to provide programming notes for Mike R.
	30 days
	Tue 5/31/05
	Fri 8/12/05
	-45.34 days
	0%
	Ed Mellinger[60%],Jose Rosal[75%],Tom Marion

	83
	MTM4 BIN chassis machining and plating In progress. BIN spheres are received and in machine shop.
	23.33 days
	Tue 5/31/05
	Thu 7/7/05
	2.67 days
	10%
	Machine shop,Jon Erickson[60%]

	88
	Specify Benthic interconnect cable and connectors CRITICAL.
	5 days
	Fri 3/4/05
	Tue 5/10/05
	-24.25 days
	15%
	Mark Chaffey[60%]

	89
	Order Benthic cable and connectors 
	0 days
	Tue 5/10/05
	Tue 5/10/05
	-24.25 days
	0%
	 

	93
	Test MTM2 residual strength 
	25 days
	Fri 4/15/05
	Thu 5/19/05
	1 day
	52%
	Andrew Hamilton[20%],Jim Scholfield[8%]

	101
	MTM4 configuration modeling 
	13.33 days
	Fri 2/4/05
	Tue 5/17/05
	-8 days
	30%
	Andrew Hamilton[60%]

	102
	MTM4 float clamp redesign Underway at CRP.
	40 days
	Wed 2/23/05
	Thu 6/30/05
	-28.33 days
	20%
	Andrew Hamilton[20%]

	103
	MTM4 float bending strain relief redesign spec. to CRP In progress.
	4 days
	Tue 5/17/05
	Mon 5/23/05
	-0.33 days
	0%
	Andrew Hamilton[50%]

	104
	MTM4 cable stop clamp design 
	11.67 days
	Tue 5/17/05
	Wed 6/1/05
	-8 days
	0%
	Andrew Hamilton[60%]

	105
	MTM4 bottom termination redesign 
	25 days
	Fri 3/11/05
	Thu 6/16/05
	-18.83 days
	10%
	Andrew Hamilton[60%],Mark Brown[60%]

	117
	Test MTM2 snubber residual strength
	10 days
	Thu 5/19/05
	Thu 6/2/05
	-3 days
	0%
	Mark Chaffey[30%]

	118
	Finalize MTM4 snubber design 
	5 days
	Thu 6/2/05
	Thu 6/9/05
	-3 days
	0%
	Mark Chaffey[60%]

	119
	MTM4 Snubber assembly CDR 
	0 days
	Thu 6/9/05
	Thu 6/9/05
	-3 days
	0%
	Mark Chaffey[60%]

	120
	MTM4 fabricate snubber hose Still waiting for firm quote from vendor.
	65 days
	Thu 6/9/05
	Thu 9/8/05
	-3 days
	0%
	Mark Chaffey[2%]

	122
	MTM4 fabricate coilcord cable In progress.
	30 days
	Wed 5/4/05
	Tue 6/14/05
	-31.67 days
	0%
	Mark Chaffey[3%]

	123
	MTM4 fabricate coilcord Pending 122 completion.
	25 days
	Wed 6/15/05
	Tue 7/19/05
	-31.67 days
	0%
	Mark Chaffey[8%]

	127
	MTM4 inspect and refurbish MTM2 tower In progress.
	5 days
	Wed 5/4/05
	Tue 5/10/05
	71.67 days
	20%
	Johnny Ferrira

	128
	MTM4 repaint MTM2 float In progress.
	6 days
	Wed 5/4/05
	Wed 5/11/05
	70.67 days
	0%
	Johnny Ferrira[17%]

	130
	MTM4 Install solar panels and batteries 
	4 days
	Mon 5/30/05
	Thu 6/2/05
	60.67 days
	0%
	Johnny Ferrira[50%],Jim Scholfield[50%]

	134
	MTM4 inspect and refurbish MTM2 bridle In progress.
	3 days
	Wed 5/4/05
	Fri 5/6/05
	94 days
	0%
	Johnny Ferrira[75%]

	141
	Installation planning meeting with Tiburon group Next meeting scheduled for today, July 6 to review deployment plan and testing requirements.
	0.83 days
	Fri 6/10/05
	Fri 6/10/05
	60.17 days
	0%
	Mark Chaffey[60%],Andrew Hamilton, Jon Erickson,JohnnyFerrira,Dale Graves


