MOOS Mooring 9/14/05 Meeting Notes

1) MTM3 deployment schedule update.

a. Bridle installation still Friday Sept. 16.

b. Predeployment readiness review Monday Sept. 19. We’ll run through the dockside pre-deployment checklist.
c. MTM3 serial and network cables will be disconnected on Friday. 
d. Crew list for deployment.

Charles Schafer (winch operator)

Mike Kelley (Observer/deck support)

Kent Headley (Software support)

Hardware engineer TBD

Mark Chaffey (Observer/mooring support)
2) Action items:

a. Any remaining wiring? Wiring complete but a few retention bushing need to be tightened and wires tie-wrapped. All buoy work needs to be completed before Friday when the mooring will be tipped on it’s side and no longer easily accessible.
b. Who should lead MBARI side of cable unloading, respooling and loading? Johnny Ferreira has agreed to be the MBARI contact person on cable efforts.
c. SSDS feed to WHOI. Kevin Gomes will work with Steve Lerner at WHOI to get them what they need for a data source. Kevin also will set up a simple CIMT-like page for MTM3 as he has time available (the inclusion of xml metadata in the data streams makes this a very fast operation).
d. SIAM outstanding action items?

i. Watchdog test. Successful, mooring rebooted right on schedule.
ii. SIAM checklist. Tom working on it.
iii. PUCK configuration test. Revision control….. Working out appropriate person to load PUCK firmware into hardware. Needs to be done as part of hardware checkout on incoming boards.
e. Other outstanding hardware and software items?

i. Need to send MTM3 anchor location to Kevin Gomes for watch circle plot.
ii. Need to set-up FreeWave on Pt. Sur. Lance checking into having George Badger check on set-up and antenna feed. 

3) Checklist run-through Suggest each subsystem engineer check items on check list before Monday before readiness review.
4) MTM3 instrument list status:
	Instrument
	Sample rate
	Notes

	Globalstar (Lance)
	1 hour
	Globalstar service error messages are of some concern. Came during a three hour outage several days ago. Appears that instrument service is getting an error message from the modem on start up. Have not seen any error messages in the last 24 hours. – Tom.

	MMC Can (Lance) 
	
	Pressure OK.

	Power Can (Ed) 
	10 min.
	GF status? 48V GF located to solar panel short to ground. Replacement or repair being considered.

	Upper load cell (Mark)
	10 min./4Hz
	Need field calibration (Thursday)

	Lower Load cell (Mark)
	10 min./4Hz
	Need field calibration (Thursday)

	P2 - Optical ADC (Lance)
	10 min.
	

	ADC03 - reference
	10 min./4Hz
	Looks OK

	ADC02 – optical loop 1
	10 min./4Hz
	Looks OK

	ADC04 – optical loop 2
	10 min./4Hz
	Looks OK.

	Compass   (Lance)
	10 min.
	Looks OK

	Freewave (Lance)
	7 min.
	Looks OK, Kent needs to get set-up parameters for the record. Has been set to high power.

	Wind/Heading (Lance) 
	10 min.
	Looks OK

	Wave Sensor (Heave only) (Andy)
	30 min.
	No update from Andy.

	Garmin GPS  (Kent)
	10 min.
	Looks OK


