MOOS Mooring 10/12/05 Meeting Notes

Present: Jon, Cherie, Lance, Kent, Mark.

1) Action items:

a. MTM3 GPA failure. Investigating over-current trip (since resolved).

b. Order new HPU for cable testing. (Andy).
c. Schedule next science meeting and mail agenda. (Mark C.) Scheduled for next Tuesday.
2) New tasks to add:

a. Add second GPS to MTM4, what about Globalstar? GPS will be added to instrument list. Need to consult with SIAM on feasibility of second Globalstar unit.
b. Need to add Seahorse to MTM4 instrument list.
c. Radiometer obstruction (Jon). Topic for next science instrument meeting.
d. Testing Oasis super-cap board. (Ed). In progress?
e. Resolving wind generator/wind speed measurement interference Topic for next science instrument meeting.
Current task list:
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	35
	Satlantic HyperSpectral Radiometers Not on order yet, planning on getting loaner unit.
	52 days?
	Thu 8/11/05
	Fri 10/21/05
	29.67 days?
	0%
	 

	36
	Satlantic/MBARI ISUS Not on order yet, planning on getting loaner unit.
	53 days?
	Thu 8/11/05
	Mon 10/24/05
	28.67 days?
	0%
	 

	37
	SBE 37MCTD Not on order yet.
	1 day?
	Thu 8/11/05
	Thu 8/11/05
	80.67 days?
	0%
	 

	38
	Nortek AquaDOPP ADCP In transit to MBARI.
	47 days
	Mon 8/1/05
	Tue 10/4/05
	42.67 days
	28%
	 

	41
	Seahorse Profiler controller available
	44.5 days
	Thu 9/1/05
	Wed 11/2/05
	0 days
	0%
	Andrew Hamilton[4%]

	48
	MTM4 Mold PUCKs and test Pending final BIN hardware instrument interface design. (Mark C.)
	5 days
	Wed 8/17/05
	Wed 8/24/05
	72.42 days
	0%
	Lance McBride,Jim Scholfield

	60
	Medusa power management testing Pending arrangements for Bob H. to work on project. Goal is to start the effort Nov. 1.
	3.33 days
	Wed 5/4/05
	Fri 10/7/05
	37.25 days
	50%
	Tim Meese[60%]

	61
	Medusa test port mirroring/failover support Pending arrangements for Bob H. to work on project.
	8.33 days
	Thu 3/17/05
	Thu 10/13/05
	33.5 days
	35%
	Tim Meese[60%]

	62
	Medusa diagnostic data serial interface port Pending arrangements for Bob H. to work on project.
	13.33 days
	Wed 5/4/05
	Thu 10/6/05
	38.25 days
	95%
	Tim Meese[60%]

	64
	Medusa full function testing with SIAM Pending arrangements for Bob H. to work on project.
	11 days
	Mon 5/23/05
	Tue 10/18/05
	33.5 days
	75%
	Tim Meese[60%],Mark Chaffey[60%],Wayne Radochonski[60%]

	69
	MMC software, clock distribution application Pending arrangements for Bob H. to work on project.
	33.33 days
	Thu 10/6/05
	Tue 11/22/05
	8.34 days
	0%
	Wayne Radochonski[60%]

	74
	Revise P2 PCB for MMC rev. 2 backplane Need to verify compatible with new Persistor release.
	10 days
	Mon 2/28/05
	Wed 8/3/05
	365.5 days
	95%
	Ed Mellinger[60%],Tom Marion

	75
	Design modifications 48-12 converter Layout fixes and new PCB’s are needed.
	16.67 days
	Wed 8/3/05
	Fri 8/26/05
	349.83 days
	25%
	Ed Mellinger[60%],Jose Rosal,Tom Marion

	76
	Complete assembly of spare power cans Waiting for completion of converted above to finish assembly.
	18.67 days
	Wed 5/4/05
	Fri 8/26/05
	-4.96 days
	40%
	Jim Scholfield[75%],Tom Marion[75%],Ed Mellinger[10%]

	77
	Design modifications, 400-12 w/switch No progress.
	30 days
	Sun 5/29/05
	Wed 8/31/05
	67.5 days
	40%
	Ed Mellinger[60%],Jose Rosal[75%],Tom Marion

	78
	400 Volt switch P2 driver Waiting on API and function diagram.
	16.67 days
	Mon 8/29/05
	Tue 9/20/05
	65 days
	0%
	Ed Mellinger[60%],Mike Risi[60%]

	80
	MTM4 recycle MTM2 power components and test Done.
	20 days
	Mon 5/9/05
	Thu 8/11/05
	365 days
	95%
	Ed Mellinger[60%],Tom Marion[75%]

	81
	MTM4 fabricate and test 3 BIN power systems Pending #77
	16.67 days
	Mon 9/19/05
	Tue 10/11/05
	55 days
	0%
	Ed Mellinger[60%],Tom Marion[75%]

	86
	MTM BIN order and receive instrument penetrators/cables Order still has not been submitted, finalizing instrument interface.
	65 days
	Thu 8/11/05
	Wed 11/9/05
	24.67 days
	0%
	Mark Chaffey[7%],Jon Erickson[3%]

	92
	MTM4 BIN first assembly Mechanical and chassis assembly in progress.
	3.33 days
	Thu 10/6/05
	Tue 10/11/05
	46.34 days
	0%
	Jon Erickson[60%],Johnny Ferrira

	97
	Fabricate Spare Benthic interconnect optical cable In progress at South Bay, delivery delayed by one month.
	57.75 days?
	Thu 8/11/05
	Mon 10/31/05
	25.92 days?
	69%
	 

	99
	Order Benthic optical cable connectors Pending.
	1 day
	Fri 8/12/05
	Fri 8/12/05
	9.67 days
	0%
	 

	102
	MTM4 specify copper Benthic instrument cable  Pending.
	1 day
	Thu 8/11/05
	Thu 8/11/05
	37.67 days
	0%
	Mark Chaffey[50%]

	107
	Test MTM2 residual strength In progess, final test of improved float profile due to complete next week.
	128.5 days
	Fri 4/15/05
	Wed 10/12/05
	13.5 days
	90%
	Andrew Hamilton[20%],Jim Scholfield[8%]

	108
	MTM4 cable assembly CDR Pending #107 above.
	0 days
	Wed 10/12/05
	Wed 10/12/05
	13.5 days
	0%
	Andrew Hamilton[60%],Mark Brown[60%]

	110
	MTM4 go-no decision Delayed until after test above.
	0 days
	Wed 10/12/05
	Wed 10/12/05
	13.5 days
	0%
	Mark Chaffey[60%],Andrew Hamilton[60%],Keith Raybould,John Ryan[60%]

	118
	MTM4 configuration modeling In progress.
	64.67 days
	Fri 2/4/05
	Mon 10/10/05
	304 days
	97%
	Andrew Hamilton[60%]

	122
	MTM4 bottom termination redesign In progress.
	25 days
	Fri 3/11/05
	Wed 10/26/05
	311.5 days
	50%
	Andrew Hamilton[60%],Mark Brown[60%]

	129
	MTM4 load cell revision and testing Proposal received for Titanium version that should eliminate corrosion problems. Checking budget before purchase. 
	12.33 days
	Wed 10/12/05
	Fri 10/28/05
	24.83 days
	0%
	Mark Chaffey[60%],Jim Scholfield[75%],Cheri Everlove[75%]

	136
	MTM4 fabricate snubber hose In progress.
	65 days
	Mon 7/18/05
	Fri 10/14/05
	77.33 days
	89%
	Mark Chaffey[2%]

	138
	MTM4 fabricate coilcord cable In progress.
	59.38 days
	Mon 5/30/05
	Fri 8/19/05
	40.46 days
	89%
	Mark Chaffey[3%]

	139
	MTM4 fabricate coilcord Pending #138 above.
	46.13 days
	Fri 8/19/05
	Mon 10/24/05
	6.83 days
	0%
	Mark Chaffey[8%]

	143
	MTM4 20 meter MMC housing fabrication In progress.
	10 days?
	Thu 8/25/05
	Mon 10/10/05
	35.17 days?
	75%
	Machine shop

	149
	MTM4 Install high efficiency solar panels and batteries Panels pending Jim S. fabrication test. Batteries will not be ordered until closer to launch date.
	4 days
	Thu 8/11/05
	Tue 8/16/05
	112.67 days
	0%
	Johnny Ferrira[50%],Jim Scholfield[50%]

	161
	Installation planning meeting with Tiburon group Initial meeting held by Andy related to bottom termination design. Some plug-in tests conducted on Shepard Meander cruise.
	0.83 days
	Fri 8/26/05
	Fri 8/26/05
	112.17 days
	0%
	Mark Chaffey[60%],Andrew Hamilton,Jon Erickson,Johnny Ferrira,Dale Graves

	167
	Cable laying toolsled testing No update.
	15 days?
	Mon 8/15/05
	Fri 9/2/05
	117 days?
	0%
	 


