MOOS Mooring 05/17/06 Meeting Agenda
1) Project Schedule update, major upcoming dates are repeated below. The final software checkout period is 7 working days.

a. Software Freeze: April 28.

b. Power hardware/BINS assembly complete May 19. (All hardware done)

c. End of lab integration and test period May 24. (NOW JUNE 9)
d. Cold soak and wet test May 25. (NOW JUNE 9-11)
e. Dockside end-to-end test start June 2 (NOW JUNE 16-23)
f. Load Pt. Sur June 23-26

g. Deploy MTM4 buoy June 27 (NOW JUNE 29).
h. Load Western Flyer July 5

i. Western Flyer Shelf BIN deployment cruise July 6-12.
2) Individual schedules:

a. Anyone out next week??. 

3) Action items.
a. Full system lab testing plan (Mark C.)
b. Chaffey and McBride to deliver "final" current limits for all instruments.
Current task list (tasks in progress or scheduled to start within seven days) Red=critical path items:
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	30
	MTM4 Power budget
	148 days
	Wed 5/4/05
	Fri 5/12/06
	32 days
	99%
	Ed Mellinger[10%]

	64
	Fix Medusa power-up glitch
	5 days
	Thu 4/13/06
	Fri 5/12/06
	-2.46 days
	75%
	 

	65
	Medusa full function testing with SIAM
	18.95 days
	Mon 5/23/05
	Tue 5/16/06
	-17.29 days
	80%
	Bob Herlien[60%],Mark Chaffey[60%],Wayne Radochonski[60%]

	69
	MMC SideArm, replace RTC xstal
	1 day
	Thu 4/20/06
	Thu 5/11/06
	-19 days
	50%
	 

	70
	MMC software, clock distribution application
	2 days
	Thu 1/5/06
	Mon 5/15/06
	-19 days
	95%
	Bob Herlien[60%]

	71
	MMC RTC, calibrate RTC register
	1 day
	Mon 5/15/06
	Tue 5/16/06
	-19 days
	0%
	 

	72
	MTM4 power system
	322.77 days?
	Mon 2/28/05
	Wed 5/17/06
	-4 days?
	95%
	 

	79
	Design modifications 48-400 converter
	16.67 days?
	Mon 11/7/05
	Thu 5/11/06
	-14.83 days?
	95%
	Ed Mellinger[60%]

	80
	Complete assembly of spare power cans
	34.37 days
	Wed 5/4/05
	Fri 5/12/06
	-12.72 days
	95%
	Jim Scholfield[75%],Tom Marion[75%],Ed Mellinger[10%]

	82
	400 Volt switch P2 driver
	16.67 days
	Fri 3/17/06
	Thu 5/11/06
	-20.77 days
	95%
	Ed Mellinger[60%],Mike Risi[60%]

	84
	400-12 w/switch converter PCB Fab. and stuff
	10 days
	Mon 4/17/06
	Sat 4/29/06
	-11.5 days
	75%
	Etech[75%],Ed Mellinger[5%]

	85
	MTM4 fabricate and test 3 BIN power systems
	5 days
	Wed 5/10/06
	Wed 5/17/06
	-20.77 days
	0%
	Ed Mellinger[60%],Tom Marion[75%]

	86
	MTM4 BINS
	348.77 days
	Mon 1/24/05
	Thu 5/18/06
	-2.27 days
	99%
	 

	99
	MTM4 BIN mold penetrator cables
	7 days
	Thu 4/27/06
	Tue 5/16/06
	-20.5 days
	50%
	Jim Scholfield[75%]

	100
	MTM4 BIN assemble final articles
	2 days
	Tue 5/16/06
	Thu 5/18/06
	-20.77 days
	0%
	Johnny Ferrira[60%],Jim Scholfield[75%]

	101
	MTM4 Benthic cable assemblies
	387.33 days?
	Fri 3/4/05
	Tue 8/15/06
	7.67 days?
	54%
	 

	107
	Fabricate Benthic optical cable connector spares
	72 days
	Thu 1/26/06
	Wed 6/7/06
	46 days
	56%
	Mark Chaffey[1%]

	109
	MTM4 specify copper Benthic instrument cable
	1.33 days
	Thu 5/11/06
	Fri 5/12/06
	7.67 days
	0%
	Mark Chaffey[50%],Larry Bird[75%]

	110
	MTM4 Fabricate copper Benthic instrument cable
	50 days
	Fri 5/12/06
	Mon 7/17/06
	7.67 days
	0%
	Mark Chaffey[1%],Larry Bird[2%]

	111
	MTM4 Benthic instrument cable schematic
	1 day?
	Fri 5/12/06
	Mon 5/15/06
	56.67 days?
	0%
	 

	114
	MTM4 Riser cable assembly
	345 days?
	Fri 2/4/05
	Thu 5/25/06
	22 days?
	98%
	 

	126
	MTM4 respool cable if necessary
	2 days
	Thu 4/27/06
	Thu 5/11/06
	17 days
	50%
	Andrew Hamilton[60%],Johnny Ferrira[75%]

	127
	MTM4 terminate cable
	10 days
	Fri 5/12/06
	Thu 5/25/06
	17 days
	0%
	Mark Chaffey[50%],Cheri Everlove[33%]

	131
	MTM4 cable stop clamp design
	8.33 days
	Thu 11/10/05
	Thu 5/11/06
	32.17 days
	90%
	Andrew Hamilton[60%]

	139
	MTM4 bottom termination final assembly
	5 days
	Mon 3/27/06
	Fri 5/12/06
	26.75 days
	75%
	Andrew Hamilton[20%],Mark Brown[20%],Larry Bird[50%]

	140
	MTM4 Snubber assembly
	335.25 days?
	Fri 2/4/05
	Fri 5/12/06
	26.75 days?
	99%
	 

	158
	MTM4 Snubber assembly final assembly and test
	5 days
	Thu 4/27/06
	Fri 5/12/06
	26.75 days
	75%
	Mark Chaffey[60%],Jon Erickson,Johnny Ferrira

	159
	MTM4 System final integration and testing
	302.77 days?
	Sun 5/8/05
	Tue 6/27/06
	45.23 days?
	86%
	 

	160
	Surface - Globalstar modems
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	161
	Surface - Freewave LOS radio (console)
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	162
	Surface - Freewave LOS radio (SeaHorse VP)
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	163
	Surface - Heave sensor
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	164
	Surface - GPS sensors
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	165
	Surface - RDI Long Ranger ADCP
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	166
	Surface - SBE 37SM CTD
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	167
	Surface - load cell
	58 days
	Mon 1/2/06
	Thu 5/11/06
	20.42 days
	99%
	Mark Chaffey[60%],Jim Scholfield[75%],Cheri Everlove[75%]

	168
	Snubber - SBE 37SM CTD
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	169
	Surface - ISUS
	1.67 days
	Mon 2/27/06
	Thu 5/11/06
	-18.52 days
	99%
	Lance McBride[60%]

	170
	Surface - ASIMET Barometric pressure
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	171
	Surface - ASIMET Long Wave radation
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-13.66 days
	99%
	Lance McBride[6%]

	172
	Surface - ASIMET Short Wave radation
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	173
	Surface - ASIMET Temp and Humidity
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	174
	Surface - ASIMET Wind speed/direction
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	175
	Surface - PCO2
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	176
	Surface - Satlantic Hyperspectral Es (air, downwelling)
	2 days
	Mon 2/27/06
	Thu 5/11/06
	-18.52 days
	99%
	Lance McBride[50%]

	177
	Snubber - Satlantic Hyperspectral Ed-W (water, downwelling)
	1.67 days
	Mon 2/27/06
	Thu 5/11/06
	-18.52 days
	99%
	Lance McBride[60%]

	178
	Snubber - Satlantic Hyperspectral Lu-W (water, upwelling)
	1.67 days
	Mon 2/27/06
	Thu 5/11/06
	-18.52 days
	99%
	Lance McBride[60%]

	179
	Snubber - Wetlabs FLNTU-SB
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Lance McBride[6%]

	180
	BIN - RDI Sentinal ADCP
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Mark Chaffey[6%]

	181
	BIN - Nortek Aquadopp HR profiler
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Mark Chaffey[6%]

	182
	BIN - Digital still camera
	33.33 days
	Wed 2/8/06
	Wed 6/21/06
	49.33 days
	5%
	Mark Chaffey[60%]

	183
	BIN - SeaBird SBE 16+
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Mark Chaffey[6%]

	184
	BIN - Wetlabs ECO BB2F triplett
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Mark Chaffey[6%]

	185
	BIN - Aanderaa O2
	16 days
	Wed 2/8/06
	Thu 5/11/06
	-18.66 days
	99%
	Mark Chaffey[6%]

	186
	BIN - McLane profiler
	16.5 days
	Wed 2/8/06
	Fri 5/12/06
	-20.15 days
	90%
	Andrew Hamilton[6%],Mark Chaffey[6%]

	187
	MTM4 All nodes and instrumentation software integration test
	43 days
	Mon 2/27/06
	Tue 4/25/06
	-1.5 days
	98%
	Mark Chaffey[60%],Andrew Hamilton,Ed Mellinger,Lance McBride,Wayne Radochonski,Tom O'Reilly,John Ryan,Dick Littlefield[75%]

	188
	MTM4 Verify instrument current draw
	0.83 days?
	Mon 5/8/06
	Mon 5/8/06
	-7.83 days?
	0%
	Mark Chaffey[60%],Lance McBride[60%]

	190
	MTM4 system software freeze
	0 days
	Fri 4/28/06
	Fri 4/28/06
	0 days
	0%
	 

	193
	MTM4 Surface float final mechanical assembly
	294.77 days
	Sun 5/8/05
	Thu 6/15/06
	0.23 days
	85%
	 

	201
	MTM4 Apply lettering to float
	1 day
	Thu 5/11/06
	Thu 5/11/06
	22 days
	0%
	Mark Chaffey[60%],Johnny Ferrira[75%]

	207
	Cable laying toolsled testing
	28 days?
	Thu 2/9/06
	Thu 5/4/06
	37 days?
	71%
	 

	209
	Deployment and installation planning
	267 days
	Mon 5/2/05
	Wed 5/3/06
	38 days
	48%
	 

	210
	First draft buoy deployment plan
	5 days
	Mon 5/2/05
	Sat 4/29/06
	40.33 days
	40%
	Mark Chaffey[60%],Andrew Hamilton

	211
	Deployment planning meeting with OSG
	0.83 days
	Sun 4/30/06
	Sun 4/30/06
	40.33 days
	0%
	Mark Chaffey[60%],Andrew Hamilton[60%]

	212
	Final draft deployment plan
	0.83 days
	Sun 4/30/06
	Mon 5/1/06
	40.33 days
	0%
	Mark Chaffey[60%],Andrew Hamilton,Mike Kelley

	215
	Final draft installation plan
	10 days
	Fri 1/20/06
	Wed 5/3/06
	38 days
	30%
	Mark Chaffey[60%],Andrew Hamilton

	216
	MSE Surface System deployment
	263 days?
	Tue 10/18/05
	Wed 10/4/06
	0 days?
	10%
	 

	240
	MSE maintain mooring and instrument system
	238 days?
	Tue 1/17/06
	Wed 11/29/06
	22 days?
	33%
	Mark Chaffey[20%],Andrew Hamilton[7%],Ed Mellinger[12%],Tom O'Reilly[5%],Jon Erickson[3%],Tim Meese[5%]

	242
	Recover McLane profiler
	1 day?
	Tue 1/17/06
	Tue 1/17/06
	259 days?
	0%
	 


