MOOS Mooring 05/31/06 Meeting Agenda
1) Project Schedule update, major upcoming dates are repeated below. The final software checkout period is 7 working days.

a. Software Freeze: April 28.

b. Power hardware/BINS assembly complete May 19. (All hardware done)

c. End of lab integration and test period May 24. (JUNE 9)
d. Cold soak and wet test May 25. (JUNE 9-11)
e. Dockside end-to-end test start June 2 (JUNE 16-23)
f. Load Pt. Sur June 23-26

g. Deploy MTM4 buoy June 27 (JUNE 29).
h. Load Western Flyer July 5

i. Western Flyer Shelf BIN deployment cruise July 6-12.
2) Test schedule.

3) Individual schedules:

a. Anyone out next week? 

4) Action items.
a. Schedule full system lab testing plan details. (Mark C.)
b. Chaffey and McBride to deliver "final" current limits for all instruments.
Current task list (tasks in progress or scheduled to start within seven days) Red=critical path items:
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	30
	MTM4 Power budget
	148 days
	Wed 5/4/05
	Fri 6/2/06
	17 days
	99%
	Ed Mellinger[10%]

	71
	MMC RTC, calibrate RTC register
	1 day
	Thu 6/1/06
	Thu 6/1/06
	158 days
	0%
	 

	80
	Complete assembly of MTM4 deployed power can
	34.37 days
	Wed 5/4/05
	Thu 6/1/06
	1.31 days
	98%
	Jim Scholfield[75%],Tom Marion[75%],Ed Mellinger[10%]

	81
	Complete assembly of MTM4 spare power can
	2 days
	Thu 6/1/06
	Mon 6/5/06
	1.31 days
	0%
	 

	86
	MTM4 fabricate and test 3 BIN power systems
	5 days
	Wed 5/10/06
	Thu 6/1/06
	4.75 days
	95%
	Ed Mellinger[60%],Tom Marion[75%]

	100
	MTM4 BIN mold penetrator cables
	7 days
	Thu 4/27/06
	Thu 6/1/06
	5.45 days
	95%
	Jim Scholfield[75%]

	101
	MTM4 BIN assemble final articles
	1 day
	Thu 6/1/06
	Fri 6/2/06
	4.65 days
	80%
	Johnny Ferrira[60%],Jim Scholfield[75%]

	108
	Fabricate Benthic optical cable connector spares
	72 days
	Thu 1/26/06
	Wed 6/7/06
	46 days
	93%
	Mark Chaffey[1%]

	109
	Terminate Benthic optical cable spare
	15 days
	Thu 6/8/06
	Mon 6/26/06
	46 days
	0%
	Mark Chaffey[13%]

	110
	MTM4 specify copper Benthic instrument cable
	1.33 days
	Thu 6/1/06
	Fri 6/2/06
	-7.33 days
	0%
	Mark Chaffey[50%],Larry Bird[75%]

	111
	MTM4 Fabricate copper Benthic instrument cable
	50 days
	Fri 6/2/06
	Sun 8/6/06
	-7.33 days
	0%
	Mark Chaffey[1%],Larry Bird[2%]

	112
	MTM4 Benthic instrument cable schematic
	1 day?
	Fri 6/2/06
	Mon 6/5/06
	41.67 days?
	0%
	 

	128
	MTM4 terminate cable
	10 days
	Thu 6/1/06
	Mon 6/12/06
	3 days
	0%
	Mark Chaffey[50%],Cheri Everlove[33%]

	132
	MTM4 cable stop clamp design
	8.33 days
	Thu 11/10/05
	Thu 6/1/06
	17.17 days
	90%
	Andrew Hamilton[60%]

	140
	MTM4 bottom termination final assembly
	5 days
	Mon 3/27/06
	Fri 6/2/06
	11.75 days
	75%
	Andrew Hamilton[20%],Mark Brown[20%],Larry Bird[50%]

	161
	Surface - Globalstar modems
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	162
	Surface - Freewave LOS radio (console)
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	163
	Surface - Freewave LOS radio (SeaHorse VP)
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	164
	Surface - Heave sensor
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	165
	Surface - GPS sensors
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	166
	Surface - RDI Long Ranger ADCP
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	167
	Surface - SBE 37SM CTD
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	168
	Surface - load cell
	58 days
	Mon 1/2/06
	Thu 6/1/06
	5.42 days
	99%
	Mark Chaffey[60%],Jim Scholfield[75%],Cheri Everlove[75%]

	169
	Snubber - SBE 37SM CTD
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	170
	Surface - ISUS
	1.67 days
	Mon 2/27/06
	Thu 6/1/06
	158.98 days
	99%
	Lance McBride[60%]

	171
	Surface - ASIMET Barometric pressure
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	172
	Surface - ASIMET Long Wave radation
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	173
	Surface - ASIMET Short Wave radation
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	174
	Surface - ASIMET Temp and Humidity
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	175
	Surface - ASIMET Wind speed/direction
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	176
	Surface - PCO2
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	177
	Surface - Satlantic Hyperspectral Es (air, downwelling)
	2 days
	Mon 2/27/06
	Thu 6/1/06
	158.98 days
	99%
	Lance McBride[50%]

	178
	Snubber - Satlantic Hyperspectral Ed-W (water, downwelling)
	1.67 days
	Mon 2/27/06
	Thu 6/1/06
	158.98 days
	99%
	Lance McBride[60%]

	179
	Snubber - Satlantic Hyperspectral Lu-W (water, upwelling)
	1.67 days
	Mon 2/27/06
	Thu 6/1/06
	158.98 days
	99%
	Lance McBride[60%]

	180
	Snubber - Wetlabs FLNTU-SB
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Lance McBride[6%]

	181
	BIN - RDI Sentinal ADCP
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Mark Chaffey[6%]

	182
	BIN - Nortek Aquadopp HR profiler
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Mark Chaffey[6%]

	183
	BIN - Digital still camera
	33.33 days
	Wed 2/8/06
	Mon 7/10/06
	34.33 days
	5%
	Mark Chaffey[60%]

	184
	BIN - SeaBird SBE 16+
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Mark Chaffey[6%]

	185
	BIN - Wetlabs ECO BB2F triplett
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Mark Chaffey[6%]

	186
	BIN - Aanderaa O2
	16 days
	Wed 2/8/06
	Thu 6/1/06
	158.84 days
	99%
	Mark Chaffey[6%]

	187
	BIN - McLane profiler
	16.5 days
	Wed 2/8/06
	Fri 6/2/06
	157.35 days
	90%
	Andrew Hamilton[6%],Mark Chaffey[6%]

	189
	MTM4 Verify instrument current draw
	0.83 days?
	Mon 5/8/06
	Mon 5/8/06
	13.17 days?
	0%
	Mark Chaffey[60%],Lance McBride[60%]

	190
	MTM4 full system lab testing with BINs
	10 days
	Fri 5/26/06
	Thu 6/8/06
	0 days
	40%
	Mark Chaffey[50%],Andrew Hamilton[17%],Ed Mellinger[50%],Lance McBride[33%],Wayne Radochonski[17%],Tom O'Reilly[67%],Dick Littlefield[75%],Jon Erickson[25%]

	192
	BIN cold room testing
	2 days
	Fri 6/9/06
	Sat 6/10/06
	0 days
	0%
	 

	193
	BIN test tank testing
	2 days
	Sun 6/11/06
	Mon 6/12/06
	0 days
	0%
	 

	200
	MTM4 Install all instruments
	2 days
	Fri 6/9/06
	Sat 6/10/06
	0 days
	0%
	Johnny Ferrira[75%],Lance McBride[60%],Jim Scholfield[75%]

	201
	MTM4 Install power and controller housings
	2 days
	Tue 6/13/06
	Wed 6/14/06
	0 days
	0%
	Ed Mellinger[60%],Johnny Ferrira,Lance McBride

	202
	MTM4 Apply lettering to float
	1 day
	Thu 6/1/06
	Thu 6/1/06
	7 days
	0%
	Mark Chaffey[60%],Johnny Ferrira[75%]

	203
	MTM4 Complete final buoy wiring
	5 days
	Sun 6/11/06
	Thu 6/15/06
	0 days
	0%
	Dick Littlefield[75%],Lance McBride[60%],Ed Mellinger[60%]

	208
	Cable laying toolsled testing
	28 days?
	Thu 2/9/06
	Sat 6/10/06
	10 days?
	71%
	 

	211
	First draft buoy deployment plan
	5 days
	Mon 5/2/05
	Mon 6/5/06
	13.33 days
	40%
	Mark Chaffey[60%],Andrew Hamilton

	212
	Deployment planning meeting with OSG
	0.83 days
	Tue 6/6/06
	Tue 6/6/06
	13.33 days
	0%
	Mark Chaffey[60%],Andrew Hamilton[60%]

	213
	Final draft deployment plan
	0.83 days
	Tue 6/6/06
	Wed 6/7/06
	13.33 days
	0%
	Mark Chaffey[60%],Andrew Hamilton,Mike Kelley

	216
	Final draft installation plan
	10 days
	Fri 1/20/06
	Fri 6/9/06
	11 days
	30%
	Mark Chaffey[60%],Andrew Hamilton


