MOOS Mooring 10/11/06 Meeting Agenda
1) Current mooring status.
a. Loss of Globalstar communications after can swap.

b. Secondary node Globalstar communications.
c. GPS and ISUS jar files and ID’s.
Current task list
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	68
	MTM4 SIAM/MMC Software upgrades
	402 days?
	Tue 4/12/05
	Thu 10/12/06
	58 days?
	84%
	 

	73
	MMC RTC, calibrate RTC register
	1 day
	Thu 6/15/06
	Thu 6/15/06
	146 days
	0%
	 

	75
	MMC Move to ext-3 filesystem
	1 day?
	Wed 9/13/06
	Thu 10/12/06
	1.75 days?
	75%
	 

	76
	MMC Revise Aquadopp summarizer
	1 day?
	Wed 9/13/06
	Thu 10/12/06
	1.5 days?
	50%
	 

	77
	MMC Revise RDI ADCP sampling mode
	1 day?
	Wed 9/13/06
	Thu 10/12/06
	1.75 days?
	75%
	 

	78
	MMC Qualify 8GB flash memory
	6 days
	Wed 9/13/06
	Thu 10/12/06
	1.4 days
	90%
	Brian Kieft

	79
	MMC/SIAM Revise on-board archive system
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	1 day?
	0%
	 

	80
	MMC/SIAM Upgrade config -t for ext-3 filesystem
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	1 day?
	0%
	 

	81
	MMC/SIAM Revise BIN backup power policy
	1 day?
	Wed 9/27/06
	Thu 10/12/06
	1.75 days?
	75%
	 

	82
	MTM4 power system
	335.69 days?
	Mon 2/28/05
	Mon 6/5/06
	156.31 days?
	99%
	 

	96
	MTM4 fabricate and test 3 BIN power systems
	5 days
	Wed 5/10/06
	Thu 6/1/06
	158.75 days
	95%
	Ed Mellinger[60%],Tom Marion[75%]

	112
	MTM4 Benthic cable assemblies
	459 days?
	Fri 3/4/05
	Wed 11/22/06
	29 days?
	83%
	 

	119
	Fabricate replacement Benthic optical cable
	53 days
	Fri 8/11/06
	Fri 10/20/06
	-1 day
	87%
	 

	120
	Terminate Benthic optical cable spare
	4 days
	Mon 10/23/06
	Thu 10/26/06
	0 days
	0%
	Mark Chaffey[13%]

	122
	MTM4 Fabricate copper Benthic instrument cable
	20 days
	Thu 10/12/06
	Wed 11/8/06
	29 days
	0%
	Mark Chaffey[1%],Larry Bird[2%]

	123
	MTM4 Benthic instrument cable schematic
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	53 days?
	0%
	 

	171
	MTM4 System final integration and testing
	413.67 days?
	Sun 5/8/05
	Fri 11/24/06
	27.33 days?
	94%
	 

	205
	BIN receive connectors from ODI
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	2 days?
	0%
	 

	206
	BIN build up AXIS BIN
	5 days
	Fri 10/6/06
	Thu 10/12/06
	2 days
	0%
	 

	245
	Axis BIN Instrument readiness review
	1 day
	Mon 10/16/06
	Mon 10/16/06
	0 days
	0%
	 

	246
	Phase two benthic installation
	17 days?
	Tue 10/17/06
	Wed 11/8/06
	39 days?
	0%
	 

	247
	Phase II Final System Testing
	8 days
	Tue 10/17/06
	Thu 10/26/06
	0 days
	0%
	 

	248
	WF mobilization
	1 day
	Fri 10/27/06
	Fri 10/27/06
	0 days
	0%
	Western Flyer


