MOOS Mooring 10/18/06 Meeting Notes
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Current action items not on main task list:
a. Current schedule for the next week:

b. Current mooring status.

i. Zephyr trip next week? OSG has on schedule for Thursday, Oct. 26th. The plans are to swap the MTM4 freewave radio and depending on the results of current troubleshooting efforts, the Surface cans. Participants from team MOOS still TBD.
ii. Aanderra O2 sensor is not working and has not been reporting data since installed on MTM4 on October 3.
c. Axis cruise current participants. 
i. Mark Chaffey

ii. Kent Headley

iii. Larry Bird
iv. Andy Hamilton
d. Deployed software archiving. Brief discussion on possible method for archiving image of currently deployed software. Go back to /tar file of system? Use Flash memory as archive of image? In current system it is difficult to keep down rev.’s that have exact same configuration for regression testing. 
e. Globalstar cable to Surface can. (Lance) Carolyn has cable drawing should have today.
f. Secondary node Globalstar communications failure. (Kent?) Configuration log check shows incorrect configuration on deployed secondary node.
g. Freewave replacement, cable and setup data. (Lance) Carolyn has cable drawing should have today.
h. Test cables. (Mark C., Lance, Ed) Mark undertaking effort to collect drawings and cable articles for well defined “field kit” of test cables.
i. Test equipment list for WF. (Mark C.) Pending.
j. Medusa code back-revision. Done (after meeting).
Current task list (Critical path = red)
	ID
	Task Name
	Duration
	Start
	Finish
	Remaining Slack
	% Complete
	Resource

	68
	MTM4 SIAM/MMC Software upgrades
	405.05 days?
	Tue 4/12/05
	Wed 10/18/06
	54.95 days?
	89%
	 

	76
	MMC Revise Aquadopp summarizer Done – verifying in instrument review Monday.
	1 day?
	Wed 9/13/06
	Wed 10/18/06
	2.95 days?
	95%
	Tom O'Reilly[60%],Brian Schlining

	77
	MMC Revise RDI ADCP sampling mode Testing – verifying in instrument review Monday.
	1 day?
	Wed 9/13/06
	Wed 10/18/06
	2.95 days?
	95%
	Tom O'Reilly[60%],Karen Salamy

	79
	MMC/SIAM Revise on-board archive system Done.
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	6 days?
	0%
	Kent Headley

	80
	MMC/SIAM Upgrade config -t for ext-3 filesystem. Done.
	1 day?
	Thu 10/12/06
	Thu 10/12/06
	6 days?
	0%
	Kent Headley,Brian Kieft

	81
	MMC/SIAM Revise BIN backup power policy Done.
	1 day?
	Wed 9/27/06
	Wed 10/18/06
	2.95 days?
	95%
	Kent Headley,Brian Kieft

	82
	MTM4 power system
	437.25 days?
	Mon 2/28/05
	Wed 10/18/06
	2.25 days?
	99%
	 

	96
	MTM4 fabricate and test 3 BIN power systems Will have installed Wednesday afternoon.
	5 days
	Wed 5/10/06
	Wed 10/18/06
	2.25 days
	95%
	Ed Mellinger[60%],Tom Marion[75%]

	112
	MTM4 Benthic cable assemblies
	463 days?
	Fri 3/4/05
	Tue 11/28/06
	25 days?
	85%
	 

	119
	Fabricate replacement Benthic optical cable Cable will be shipped by Truck on Friday, 10/20, on schedule.
	52.5 days
	Fri 8/11/06
	Fri 10/20/06
	0.5 days
	95%
	 

	120
	Terminate Benthic optical cable spare Field termination crew on schedule for 10/23 (Monday).
	3 days
	Mon 10/23/06
	Wed 10/25/06
	0 days
	0%
	Mark Chaffey[13%]

	123
	MTM4 Benthic instrument cable schematic
	1 day?
	Wed 10/18/06
	Wed 10/18/06
	49 days?
	0%
	Mark Chaffey[60%]

	171
	MTM4 System final integration and testing
	417.67 days?
	Sun 5/8/05
	Thu 11/30/06
	23.33 days?
	93%
	 

	195
	BIN Install/Check batteries in ADCP's, SBE16 and Wetlabs Have Nortek, will have RDI, will check SBE-16,  uses alkaline.
	1 day?
	Wed 10/18/06
	Wed 10/18/06
	2.5 days?
	0%
	Mark Chaffey[60%],Dick Littlefield[75%]

	206
	BIN Final assembly of SHELF BIN II Must be complete by Friday.
	1 day?
	Wed 10/18/06
	Wed 10/18/06
	2.5 days?
	0%
	Mark Chaffey[60%]

	207
	BIN receive connectors from ODI Due to ship today, arrive tomorrow.
	0.5 days
	Thu 10/19/06
	Thu 10/19/06
	2 days
	0%
	 

	208
	BIN build up AXIS BIN Pending 207. Must be complete by Friday.
	5 days
	Fri 10/6/06
	Thu 10/19/06
	2 days
	50%
	Mark Chaffey[60%]

	209
	Axis and Shelf BIN Instrument readiness review Scheduled for Monday PM.
	0.5 days
	Mon 10/23/06
	Mon 10/23/06
	0 days
	0%
	Tom O'Reilly[60%]

	210
	Phase II Closed housing testing
	2 days
	Mon 10/23/06
	Wed 10/25/06
	0 days
	0%
	 

	211
	Phase II 24 hour Wet/Cold soak Unless cable termination is done will not be a continuous power test, will cold soak and confirm power up boot.
	0.5 days
	Wed 10/25/06
	Wed 10/25/06
	0 days
	0%
	Mark Chaffey[60%]

	212
	Phase II Final dockside testing Pending cable termination completion.
	1 day?
	Thu 10/26/06
	Thu 10/26/06
	0 days?
	0%
	Mark Chaffey[60%]

	251
	Phase two benthic installation
	9 days?
	Fri 10/27/06
	Wed 11/8/06
	39 days?
	0%
	 

	252
	WF mobilization BINs use the ships crane and possibly could load as late as Monday early AM. Toolsled would have to load Friday (plan A) or for second leg if Shelf BIN is installed first (plan B).
	1 day
	Fri 10/27/06
	Fri 10/27/06
	0 days
	0%
	Western Flyer,Mark Chaffey[60%],Larry Bird[75%],Johnny Ferrira[75%]

	253
	WF transit
	1 day
	Mon 10/30/06
	Mon 10/30/06
	0 days
	0%
	Western Flyer


