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For the second MOOS test mooring deployment, it is desirable to expand the scope of the deployment to include the design, implementation, and test of the power and data connections to the benthic cable assembly.  Ideally the test mooring deployment will include a subsequent ROV assisted connection to one BIN located a short distance away from the mooring anchor.  The pre-deployment tasks that need to be completed are all related to the conceptual development, design, and implementation of this system.  This process will require continuous consultation with the ROV pilots.

Task List:

· Definition of requirements and exploration of various concepts – 5 ME days

· Preliminary Design leading to PDR – 6 ME days

· Detailed Design leading to CDR – 8 ME days

· Implementation – 2 ME days, 10 Shop days

· Robustness testing of termination, if not performed as part of riser cable assembly. – 2 ME days, 2 Tech days

· Testing of solution with Ventana in test tank, if deemed necessary – 2 ME days, 1 Ventana tank day.

