## Tasks
Task | Days | Hours
Continuing Work
Continue refining SIFT algorithm and auto-tuning - tune sift parameters in real-time based on feed back from the algorithm. Include a classifier to ignore fish (this might be pie in the sky, not sure we'll ever get it to work.) | 20 | 160
Modify GUI to include image tiles as well as wire frame. GUI will include ability to add way points in real-time and navigate by clicking on the mosaic. | 15 | 120
Continue supporting ocean imaging - this includes working with GT, Rich, and Hans to get all of the real-time software to play together on one machine. I hope to purchase this machine and take it on it's maiden voyage this December. This tasks also includes getting a second machine on Ventana now that it's compatible with Ocean Imaging | 10 | 80
New work
visual feature tracking (fiducial identification) | 10 | 80
Automated sample acquisition | 0 | 0 | do we want to do this? Do we want to just scope it out in 2015? My schedule is filling up fast, I may not have the time to put into this.
Cruises
Joint Ocean Imaging/Precision control survey in Fall with MOB/deMOB (7 days), 2 Precision Control cruises on Rachel Carson with MOB/deMOB (3 days) | 10 | 80
Kikani's Control System |  | 0
Blob tracking - develop blob tracking (AKA jelly tracking) based on prior ARL work and openCV. Stereo camera integration based on openCV libraries | 20 | 160
Integrate blob tracking signal into ROV control system | 10 | 80
Cruise days - 3 cruise total plus a half day MOB/deMOB per cruise | 4.5 | 36
Total | 99.5 | 796

## Budget
Description | Cost
Misc computer harware and cabling | 500
Dedicated Vision Processor for Ventana | 3500
Sensoray 2226S HD capture box | 1500
OWC Mecury Exteme SSD for HD video capture | 500
RAID storage for HD video post processing | 750
6750