Laser Raman Spetrometer 1/19/01

Work Breakdown List

This list was developed after discussion with George Malby regarding work to be performed for the year 2001 on the LRS project.
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Task

Time Estimate (Days)

Comment

Camera Integration (TTL)

Spec & Procure camera

2

Configure Lighting

5

Integrate with existing probe 

head

5

Design Pressure Housing

**

Cylinder

4

2 EA. Endcaps

8

SUB-TOTAL DAYS

24

XYZ Positioner

Formal Requirements

2

Tech search

3

System Engineering

5

Positioner Design

**

Camera/Probe Mount

4

Positioner Table

4

X-AXIS

4

Y-AXIS

4

Z-AXIS

4

Configurable Mount

4

Manifold

4

SUB-TOTAL DAYS

38

Testing & Integration to 

Service

Lab Test

5

Shipboard test

3

SUB-TOTAL DAYS

8

TOTAL DAY ESTIMATE

70


_1041428502.xls
Sheet1

		Description		Task		Time Estimate (Days)		Comment

		Camera Integration (TTL)		Spec & Procure camera		2

				Configure Lighting		5

				Integrate with existing probe head		5

				Design Pressure Housing		**

				Cylinder		4

				2 EA. Endcaps		8

		SUB-TOTAL DAYS				24

		XYZ Positioner

				Formal Requirements		2

				Tech search		3

				System Engineering		5

				Positioner Design		**

				Camera/Probe Mount		4

				Positioner Table		4

				X-AXIS		4

				Y-AXIS		4

				Z-AXIS		4

				Configurable Mount		4

				Manifold		4

		SUB-TOTAL DAYS				38

		Testing & Integration to Service

				Lab Test		5

				Shipboard test		3

		SUB-TOTAL DAYS				8

		TOTAL DAY ESTIMATE				70






