Documentation Outline

System Engineering
Resource Man-Days
Comment

Literature Search
10 days


Analysis of current technology



Vendor Surveys



Define Requirements



Identify risky elements



Statement of work (WBS)



Conceptual Design (With BOM)





Preliminary Design



Prototype risky elements
20 days


Develop conceptual design
15 days


Test reports
1 day


First draft of final test/installation plan
2 days


PDR
1 day




Detailed design



Finish design
15


Finalize test plan
1 day


CDR
1 day


Mech Eng Drawings
8 days


Test procedures
1 day




Fabrication



Monitor fabrication
As required
On going

As-built drawing revisions
2 days




Laboratory Testing



System integration & Q.A
3 days


Subsystem and system testing
3 days


Test report
1 day




Deployment and Field Test



Mobilize for field test
1 day


Test
1-3 days


Field test report
1 day




Documentation & training



Incorporate design revisions
2 days


Operation & Maintenance manual
5 days


Archive Design
1 day














