Task List-LRS Positioning System

System Engineering
Resource Man-Days
Comment

Literature Search
10 days


Analysis of current technology



Vendor Surveys



Define Requirements



Identify risky elements



Statement of work (WBS)



Conceptual Design (With BOM)



Support to System Engineering
10




Preliminary Design



Prototype risky elements
20


Develop conceptual design
15


Test reports
1


First draft of final test/installation plan
2


PDR
1




Detailed design



Finish design
15


Finalize test plan
1


CDR
1


Mech Eng Drawings
8


Test procedures
1




Fabrication



Monitor fabrication
As required
On going

As-built drawing revisions
2




Laboratory Testing



System integration & Q.A
3


Subsystem and system testing
3


Test report
1




Deployment and Field Test



Mobilize for field test
1


Test
1-3


Field test report
1




Documentation & training



Incorporate design revisions
2


Operation & Maintenance manual
5


Archive Design
1










TOTAL
107


